## RICE PIVOT (hidden)
Phase | Phase 1
Deloitte/District Owned | (Multiple Items)
Current State | (All)
Count of RICE ID | Column Labels
Row Labels | Conversion | Extension | Interface | Report | Grand Total
Acquire to Retire | 1 |  | 1 | 7 | 9
5-Complete | 1 |  | 1 | 7 | 9
Budget | 1 |  | 7 |  | 8
3-Build |  |  | 1 |  | 1
5-Complete | 1 |  | 6 |  | 7
Budget Execution |  |  |  | 19 | 19
3-Build |  |  |  | 3 | 3
5-Complete |  |  |  | 16 | 16
Budget to Report | 2 | 1 | 7 | 10 | 20
3-Build |  |  | 1 |  | 1
5-Complete | 2 | 1 | 6 | 10 | 19
Order to Cash | 3 | 1 | 3 | 8 | 15
5-Complete | 3 | 1 | 3 | 8 | 15
Procure to Pay | 5 | 2 | 44 | 23 | 74
0-Not Started |  | 1 |  |  | 1
1-Functional Spec |  |  |  | 4 | 4
2-Technical Spec |  |  | 1 | 1 | 2
3-Build |  |  | 4 | 1 | 5
4-Unit Test |  | 1 | 7 |  | 8
5-Complete | 5 |  | 32 | 17 | 54
Projects and Grants | 7 | 3 | 2 | 10 | 22
3-Build |  | 1 |  |  | 1
5-Complete | 7 | 2 | 2 | 10 | 21
Technical |  |  | 2 |  | 2
5-Complete |  |  | 2 |  | 2
Grand Total | 19 | 7 | 66 | 77 | 169

## Cover
District of Columbia - District Integrated Financial System
Pre-Construction Phase: CLIN 107 - RICE TRACKER
Version: | 1.0
Contract # | CFOPD-19-C-001

## Appendix InterfaceConnectivity (hidden)
App | Agency | System | Direction | Current Integration Pattern | Current Connection Mode | Current Prod Connection Details | Future Integration Pattern | Future Connection Mode | Future Connection Details | Dev/Test Environment | Description | Agency Tech Contact | Comments
1 | OCTO | PeopleSoft | Inbound | Batch | FTP - Pull | FTP psoft-sftp.dc.gov 10.86.36.102 port: 21 | Batch | SFTP - Push | DIFS SFTP Server | TBD | PeopleSoft along with their SOA Bus has the capability to push all batch files to DIFS SFTP server. | Dhiraj Sandil (Dhiraj.Sandil@dc.gov)
2 | OCTO | PeopleSoft | Inbound | Webservices | HTTP | SOAP | Webservices | HTTPS | SOAP/REST | TBD | PeopleSoft will invoke DIFS webservices via HTTPS REST. Transport and Message layer security will be enabled to make this secure. TLSV1.2 at the transport layer and HTTP basic authentication at the message layer. IP Whitelisting and Port should be enabled to give only access to known systems/IP's to make sure more se secure | Dhiraj Sandil (Dhiraj.Sandil@dc.gov)
3 | OCFO/OFT | iNOVAH | Inbound | Batch | FTPS - Pull | 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | Batch | SFTP - Push | DIFS SFTP Server | TBD | SOAR currently is pulling the batch file from iNOVAH SFTP server. For future DIFS preference is iNOVAH should push the file to DIFS SFTP server as it is inbound. The iNOVAH FTP server is under OCIO and the change should be easy. | Anantha Malay
4 | OCFO/OFT | Kyriba/Banks | Inbound | NA | NA | NA | Batch | SFTP - Push | DIFS SFTP Server | TBD | Kyriba is the payment hub and has the capability to push the file to DIFS SFTP server | TMS/Kyriba Team
5 | OCFO | MITS | Inbound | Batch | MainFrame Copy into SOAR | Dataset copied into SOAR | Batch | SFTP - Push | DIFS SFTP Server | TBD | MITS has the capability to push the files on DIFS SFTP server | OCFO/OCIO Kalyan Jillumudi 478-9239
6 | OCFO | TOP | Inbound | Batch | FTPS - Pull | 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | Batch | SFTP - Push | DIFS SFTP Server | TBD | MITS is currently putting all the files on OCIO FTP server. As MITS has the capability going forward all TOP files should be pushed to DIFS SFTP server. | OCFO/OCIO Kalyan Jillumudi 478-9239
7 | OSSE | ONEAPP/NSCAPS/BITSEE/OECD | Inbound | Batch | FTPS- Pull | FTPS Ftps.osse.dc.gov 10.83.3.67 port: 21 | Batch | SFTP - Push | DIFS SFTP Server | TBD | OSSE currently is putting the file on their FTP server. As it's inbound and if they have capability then they should push their files on DIFS SFTP server. If they don't have the capability then DIFS will pull the file from their FTP server. | Teja Adusumalli 202-545-7281 Pushpika Lanka (Project Manager OSSE) 202-744-3546 Don Davis 202-904-0317
9 | OSSE | EGMS | Inbound | Batch | FTPS - Pull | 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | Batch | SFTP - Push | DIFS SFTP Server | TBD | OSSE is currently putting all the files on OCIO FTP server. As it's inbound and if they have capability then they should push their files on DIFS SFTP server. If they don't have the capability then DIFS will pull the file from their FTP server. | Teja Adusumalli 202-545-7281 Pushpika Lanka (Project Manager OSSE) 202-744-3546 Don Davis 202-904-0317
10 | DOES | DUTAS | Inbound | Batch | MainFrame Copy into SOAR | Dataset copied into SOAR | Batch | SFTP - Push | DIFS SFTP Server | TBD | As OCTO is copying into SOAR, we prefer they push the file to DIFS SFTP server. If they can't t then DIFS will pull the file from OCTO FTP server. | Gil DiMattia, Contractor 698-6282 Bobby Tucher 698-5800
11 | DOES | PFLBAS/NEOSURANCE | Inbound | Batch | FTPS- Pull | FTPS DOESPFLTFTP.does.dcgov.priv Port: 990 | Batch | SFTP - Push | DIFS SFTP Server | TBD | DOES currently is putting the file on their FTP server. As it's inbound and if they have capability then they should push their files on DIFS SFTP server. If they don't have the capability then DIFS will pull the file from their FTP server. | Gil DiMattia, Contractor 698-6282 Bobby Tucher 698-5800
13 | CFSA | FACES | Inbound | Batch | MainFrame Copy into SOAR | Dataset on tape | Batch | SFTP - Push | DIFS SFTP Server | TBD | Mainframe tape is being created. If CFSA has the capability they should push the file to DIFS SFTP server. If they don't have the capability then DIFS will pull the file from CFSA FTP server. | Kamal Devabhaktuni 434.0030 Marina Havan (CIO)
14 | DHCF | MMIS | Inbound | Batch | FTP- Pull | FTP 192.168.202.20 (Mainframe) | Batch | SFTP - Push | DIFS SFTP Server | TBD | SOAR currently is pulling the batch file from MMIS FTP server. For future DIFS preference is MMIS should push the file to DIFS SFTP server as it is inbound. If MMIS doesn't have the capability then DIFS will pull the file from MMIS FTP server. | Anthony Johnson (202.906.8315)
15 | DMV | Destiny | Inbound | Batch | FTPS - Pull | FTPS 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | Batch | SFTP - Push | DIFS SFTP Server | TBD | DMV is pushing the file to OCIO FTP server. If DMV has the capability then they should push the file to DIFS SFTP server. If not DIFS will pull the file from OCIO FTP server. | Karen Campbell-Tate 202.719.0694 George Dines, ACFO 671-2201
16 | OCFO/OFT | Kelmar | Inbound | Batch | FTPS- Pull | FTPS 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | Batch | SFTP - Push | DIFS SFTP Server | TBD | Kelmar is pushing the file to OCIO FTP server. If Kelmar has the capability then they should push the file to DIFS SFTP server. If not DIFS will pull the file from OCIO FTP server. Kelmar is the vendor. | Lynn Hall Property Manager 442-8193
17 | DDS | RSA | Inbound | Batch | FTPS - Pull | FTP dcrsa-vrapp.libera.com 52.61.164.182 port: 21 | Batch | SFTP - Push | DIFS SFTP Server | TBD | SOAR currently is pulling the batch file from RSA Libera FTP server. For future DIFS preference is MMIS should push the file to DIFS SFTP server as it is inbound. If RSA Libera doesn't have the capability then DIFS will pull the file from RSA Libera FTP server. | Srinivas Bheemreddy (202) 730 1560
18 | ORM | Erisk | Inbound | Batch | FTPS- Pull | FTPS ent-ftps.dc.gov 10.86.26.91 port: 21 | Batch | SFTP - Push | DIFS SFTP Server | TBD | SOAR currently is pulling the batch file from ERisk FTP server. For future DIFS preference is MMIS should push the file to DIFS SFTP server as it is inbound. If ERisk doesn't have the capability then DIFS will pull the file from ERisk FTP server. | Sanjay Hirani 202-727-5131
19 | DDOT | FMIS | Inbound | Batch | NA | NA | Batch | SFTP - Push | DIFS SFTP Server | TBD | This is new interface which needs to be built. We want DDOT/FMIS to push the file to DIFS SFTP server. If they can't then DIFS will pull the file from their SFTP server | TBD
20 | OCP/OCTO | ARIBA | Inbound | Webservices | HTTP | SOAP | Webservices | HTTPS | SOAP/REST | TBD | ARIBA will invoke DIFS webservices via HTTPS REST. Transport and Message layer security will be enabled to make this secure. TLSV1.2 at the transport layer and HTTP basic authentication at the message layer. IP Whitelisting and Port should be enabled to give only access to known systems/IP's to make sure more se secure | Ajay Damireddy ajay.damireddy@dc.gov
21 | OCFO/OFT | DMS/DBC | Inbound | Batch | FTPS-Pull | FTPS 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | Batch | SFTP - Push | DIFS SFTP Server | TBD | DMS/DBC is currently pushing the file to OCIO FTP server. If they the capability then they should push the file to DIFS SFTP server. If not DIFS will pull the file from OCIO FTP server. | Anantha Malay | This is Debt service posting. Need to find out if this functional will be merged with TMS/Kyriba

## Open Items (hidden)
S.No | Object Type | Item Type | Description | Plan | Comments
1 | Integration | Proms/Grams Decision | - Decision on Proms and Grams replacement needs to be made as it affects the integration list and the over-all scope. - Integration with CFO$OLVE for reports and Proms/Grams need to be finalized. | We had a meeting on 2/16 to finalize the BFA scope for integration with CFO$OLVE and EPM. More follow up meetings are needed as there is dependency on Proms and Grams replacement. Waiting on Proms/Grams decision. | Decision Made. Closed
2 | Integration | TOP, HSEMA & DOC Integrations | Need direction if integrations with Department of Corrections, Homeland Security Emergency Mgmt Agency (HSEMA) and TOP/Parking Meter System are needed or not before implementation starts | Scheduled a meeting on 2/22 with Lyle, Vijay, Ashis and Anu to get direction. | Added these integrations as optional. During implementation a decision will be made to implement these or not. Closed
3 | Report | Budget Reports | Additional discussion is required to identify/finalize the need for FRP, FSR and other recently discussed budget execution reports. These reports are not added into RICE tracker yet. | Additional budget reports will be discussed and finalized during discovery phase
4 | Integration | Covid Data Integration | This is in very early stages and Ashis is waiting for more information from OFOS. This is being implemented with an agency where Deloitte is the SI. He will share more details soon. | Ashis will confirm once he talks to OFOS.

## RICEW Glossary (hidden)
Column | Item | Entry Type | Instructions/Definitions | Drop-Down Options
A | RICE ID | Manual | Enter ID associated with the RICE object | N/A
B | Object Type | Drop-Down | Select appropriate RICE object type | Report, Interface, Conversion, Extension, Workflow, Infrastructure
C | Process Area | Drop-Down | Select appropriate Process Area | Acquire to Retire, Budget to Report, Oracle Planning, Procure to Pay, Projects and Grants, Order to Cash, Intra-District, Budget , Technical, Conversion
D | DIFS Object Name | Manual | Provide the name of the DIFS object | N/A
E | Description | Manual | Provide a description of what the interface contains | N/A
F | Phase | Drop-Down | Select the phase associated with the object | Pre-Construction, Phase 2, Phase 3, Budget Formulation
G | System | Drop-Down | Select appropriate system | ERP Cloud, EPM Cloud, Narrative Reporting, EDW
H | Sprint | Drop-Down | Select the sprint associated with the object | 1, 2, 3, 4, 5, 6, 7, 8
I | Report/Interface Type | Drop-Down | Select the report/interface type associated with the object from | FRS, Smartview, OTBI, BI Publisher, Batch, Online
J | Update COA | Drop-Down | Select whether or not Chart of Accounts has been updated | Yes, No, New Yes - Goes thru crosswalk hub No -
K | Integration Source System | Manual | Enter the integration source system for the object | N/A
L | Integration Target System | Manual | Enter the integration target system for the object | N/A
M | Complexity Level | Drop-Down | Select a complexity level based on the hours required per object (numbers below reflect hours) Reports: Low=104 Hours, Medium=150, High=270 Interface: Low=65, Medium=120, High=200 Conversions: Low=120, Medium=176, High=400 Extensions/Enhancements: Low=112, Medium=160, High=360 | Low, Medium, High
N | Priority (MoSCoW) | Drop-Down | Select appopiate priority according to MoSCoW | Must Have, Should Have, Could Have, Would Have
O | Functional Owner | Manual | Enter the name of the Functional Owner | N/A
P | Technical Owner | Manual | Enter the name of the technical Owner | N/A
Q | Deloitte/District Owned | Drop-Down | Select whether the object is owned by Deloitee or the District from the choices provided in the drop-down list | Deloitte Owned, Deloitte Owned
R | Current State | Auto-Generated | Based on the information provided in the parentheses, the current state of the object will automatically generate. ***You are not required to enter or select any information in this column. | Not Started, Functional Specification, Technical Specification, District Review, Technical Build, Functional Testing, Complete
S | Planned Functional Specification Start Date | Manual | Enter appropriate start date in MM/DD/YYYY format | N/A
T | Planned Functional Specification End Date | Manual | Enter appropriate end date in MM/DD/YYYY format | N/A
U | Actual Functional Specification Start Date | Manual | Enter appropriate start date in MM/DD/YYYY format | N/A
V | Actual Functional Specification End Date | Manual | Enter appropriate end date in MM/DD/YYYY format | N/A
W | Functional Specification Status | Manual | Select appropriate percentage of completion. If not required, select 'N/A'. | N/A, 0% - Not Started, 25% - In Progress, 50% - In Progress, 75% - In Review, 100% - Complete
X | Planned Technical Specification Start Date | Manual | Enter appropriate start date in MM/DD/YYYY format | N/A
Y | Planned Technical Specification End Date | Manual | Enter appropriate end date in MM/DD/YYYY format | N/A
X | Actual Technical Specification Start Date | Manual | Enter appropriate start date in MM/DD/YYYY format | N/A
AA | Actual Technical Specification End Date | Manual | Enter appropriate end date in MM/DD/YYYY format | N/A
AB | Technical Specification Status | Drop-Down | Select appropriate percentage of completion. If not required, select 'N/A'. | N/A, 0% - Not Started, 25% - In Progress, 50% - In Progress, 75% - In Review, 100% - Complete
AC | District Work Product Review, Date Provided to District | Manual | Enter appropriate date in MM/DD/YYYY format | N/A
AD | Expected # of Business Days | Manual | Enter appropriate umber fo business days for District Work Product review | N/A
AE | District Work Product Review, Date Approval Provided From District | Manual | Enter appropriate date in MM/DD/YYYY format | N/A
AF | Planned Technical Build Start Date | Manual | Enter appropriate start date in MM/DD/YYYY format | N/A
AG | Planned Technical Build End Date | Manual | Enter appropriate end date in MM/DD/YYYY format | N/A
AH | Actual Technical Build Start Date | Manual | Enter appropriate start date in MM/DD/YYYY format | N/A
AI | Actual Technical Build End Date | Manual | Enter appropriate end date in MM/DD/YYYY format | N/A
AJ | Build Status | Drop-Down | Select appropriate percentage of completion. If not required, select 'N/A'. | N/A, 0% - Not Started, 25% - In Progress, 50% - In Progress, 75% - In Review, 100% - Complete
AK | Planned Test Start Date | Manual | Enter appropriate start date in MM/DD/YYYY format | N/A
AL | Planned Test End Date | Manual | Enter appropriate end date in MM/DD/YYYY format | N/A
AM | Actual Test Start Date | Manual | Enter appropriate start date in MM/DD/YYYY format | N/A
AN | Actual Test End Date | Manual | Enter appropriate end date in MM/DD/YYYY format | N/A
AO | Test Status | Drop-Down | Select appropriate percentage of completion. If not required, select 'N/A'. | N/A, 0% - Not Started, 25% - In Progress, 50% - In Progress, 75% - In Review, 100% - Complete
AP | Overall Status | Drop-Down | Select appropriate option based on the complete status of the object | Sprinted, Tested, Deployed
AQ | Comments | Manual | Enter any relevant comments. It is preferred that you add the date in MM/DD/YY form. | N/A

## Estimator (hidden)
Interface | Low | InterfaceLow | 30 | 24 | 40 | 10 | 54 | 50 | 104 | 3.75 | 3 | 5 | 1.25
Interface | Medium | InterfaceMedium | 30 | 40 | 60 | 20 | 70 | 80 | 150 | 3.75 | 5 | 7.5 | 2.5
Interface | High | InterfaceHigh | 40 | 80 | 120 | 30 | 120 | 150 | 270 | 5 | 10 | 15 | 3.75
Interface | Very High | InterfaceVery High | 50 | 120 | 160 | 50 | 170 | 210 | 380 | 6.25 | 15 | 20 | 6.25
[7 empty] | 0 | 0 | 0
Conversion | Low | ConversionLow | 30 | 35 | 50 | 5 | 65 | 55 | 120
Conversion | Medium | ConversionMedium | 30 | 48 | 80 | 18 | 78 | 98 | 176
Conversion | High | ConversionHigh | 40 | 100 | 200 | 60 | 140 | 260 | 400
Conversion | Very High | ConversionVery High | 60 | 140 | 260 | 70 | 200 | 330 | 530
[7 empty] | 0 | 0 | 0
Report | Low | ReportLow | 15 | 15 | 30 | 5 | 30 | 35 | 65
Report | Medium | ReportMedium | 25 | 35 | 50 | 10 | 60 | 60 | 120
Report | High | ReportHigh | 25 | 50 | 100 | 25 | 75 | 125 | 200
Report | Very High | ReportVery High | 30 | 60 | 130 | 30 | 90 | 160 | 250
[7 empty] | 0 | 0 | 0
Extension | Low | ExtensionLow | 20 | 28 | 56 | 8 | 48 | 64 | 112
Extension | Medium | ExtensionMedium | 25 | 40 | 80 | 15 | 65 | 95 | 160
Extension | High | ExtensionHigh | 40 | 100 | 180 | 40 | 140 | 220 | 360
Extension | Very High | ExtensionVery High | 50 | 140 | 220 | 50 | 190 | 270 | 460

## LOV (hidden)
N/A
0% - Not Started
25% - In Progress
50% - In Progress
75% - In Review
100% - Complete | 6.4495

## Reports Rebaseline (hidden)
RICE ID | Functional Owner | Technical Owner | Planned Functional Specification Start Date | Planned Functional Specification End Date | Planned Technical Specification Start Date | Planned Technical Specification End Date | Planned Technical Build Start Date | Planned Technical Build End Date | Planned Unit Test Start Date | Planned Unit Test End Date | RICE ID | DIFS Object Name | RICE ID | Planned Functional Specification Start Date | Planned Functional Specification End Date | Planned Technical Specification Start Date | Planned Technical Specification End Date | Planned Technical Build Start Date | Planned Technical Build End Date | Planned Unit Test Start Date | Planned Unit Test End Date
R085 | Tej | Srini | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-28 | 2021-06-28 | 2021-07-14 | 2021-07-15 | 2021-07-20 | R147 | FRP Report | R085 | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-28 | 2021-06-28 | 2021-07-14 | 2021-07-15 | 2021-07-20
R051 | Jessica | Vijay | 2021-06-18 | 2021-06-25 | 2021-06-28 | 2021-07-05 | 2021-07-06 | 2021-07-22 | 2021-07-23 | 2021-07-28 | R138 | Spending Plan Capital Report | R051 | 2021-06-18 | 2021-06-25 | 2021-06-28 | 2021-07-05 | 2021-07-06 | 2021-07-22 | 2021-07-23 | 2021-07-28
R019 | Trinh | Srini | 2021-07-13 | 2021-07-20 | 2021-07-21 | 2021-07-28 | 2021-07-29 | 2021-08-16 | 2021-08-17 | 2021-08-22 | R168 | Prepare a Reprogramming Report to Council | R019 | 2021-07-14 | 2021-07-20 | 2021-07-21 | 2021-07-28 | 2021-07-29 | 2021-08-16 | 2021-08-17 | 2021-08-22
R025 | Trinh | Vijay | 2021-07-15 | 2021-07-22 | 2021-07-23 | 2021-07-30 | 2021-08-02 | 2021-08-18 | 2021-08-19 | 2021-08-24 | R170 | Prepare a Quarterly Intra-District Report | R025 | 2021-07-15 | 2021-07-22 | 2021-07-23 | 2021-07-30 | 2021-08-02 | 2021-08-18 | 2021-08-19 | 2021-08-24
R098 | Tej | Percy | 2021-07-07 | 2021-07-14 | 2021-07-15 | 2021-07-20 | 2021-07-21 | 2021-07-28 | 2021-07-29 | 2021-07-31 | R135 | DCPS Advance Report | R098 | 2021-07-05 | 2021-07-14 | 2021-07-15 | 2021-07-20 | 2021-07-21 | 2021-07-28 | 2021-07-29 | 2021-07-31
R097 | Tej | Srini | 2021-08-09 | 2021-08-16 | 2021-08-17 | 2021-08-20 | 2021-08-23 | 2021-08-30 | 2021-08-31 | 2021-09-01 | R136 | Expenditures by Month Report | R097 | 2021-08-10 | 2021-08-16 | 2021-08-17 | 2021-08-20 | 2021-08-23 | 2021-08-31 | 2021-09-01 | 2021-09-02
R082 | Tej | Srini | 2021-08-11 | 2021-08-18 | 2021-08-19 | 2021-08-27 | 2021-08-30 | 2021-09-15 | 2021-09-16 | 2021-09-21 | R137 | Historical Approved and Revised Budget and Expenditures report | R082 | 2021-08-25 | 2021-08-31 | 2021-09-01 | 2021-09-08 | 2021-09-09 | 2021-09-27 | 2021-09-28 | 2021-10-03
R031 | Trinh | Vijay | 2021-08-23 | 2021-08-30 | 2021-08-31 | 2021-09-03 | 2021-09-06 | 2021-09-15 | 2021-09-16 | 2021-09-18 |  |  | R031 | 2021-08-11 | 2021-08-18 | 2021-08-19 | 2021-08-24 | 2021-08-25 | 2021-09-03 | 2021-09-06 | 2021-09-08
R026 | Jessica | Vijay | 2021-09-08 | 2021-09-15 | 2021-09-16 | 2021-09-23 | 2021-09-24 | 2021-10-12 | 2021-10-13 | 2021-10-18 |  |  | R026 | 2021-08-27 | 2021-09-03 | 2021-09-06 | 2021-09-13 | 2021-09-14 | 2021-09-30 | 2021-10-01 | 2021-10-06
R071 | Prasad | Percy | 2021-07-21 | 2021-07-28 | 2021-07-29 | 2021-08-05 | 2021-08-06 | 2021-08-24 | 2021-08-25 | 2021-08-30 |  |  | R071 | 2021-07-19 | 2021-07-28 | 2021-07-29 | 2021-08-05 | 2021-08-06 | 2021-08-24 | 2021-08-25 | 2021-08-30
R072 | Zemeer | Percy | 2021-08-23 | 2021-08-30 | 2021-08-31 | 2021-09-06 | 2021-09-07 | 2021-09-14 | 2021-09-15 | 2021-09-17 |  |  | R072 | 2021-08-20 | 2021-08-31 | 2021-09-01 | 2021-09-07 | 2021-09-08 | 2021-09-15 | 2021-09-16 | 2021-09-18
R002 | Simon | Srini | 2021-10-05 | 2021-10-12 | 2021-10-13 | 2021-10-20 | 2021-10-21 | 2021-11-08 | 2021-11-09 | 2021-11-14 |  |  | R002 | 2021-09-21 | 2021-09-27 | 2021-09-28 | 2021-10-05 | 2021-10-06 | 2021-10-22 | 2021-10-25 | 2021-10-30
R003 | Simon | Srini | 2021-08-17 | 2021-08-24 | 2021-08-25 | 2021-08-30 | 2021-08-31 | 2021-09-07 | 2021-09-08 | 2021-09-10 |  |  | R003 | 2021-10-18 | 2021-10-22 | 2021-10-25 | 2021-10-28 | 2021-10-29 | 2021-11-05 | 2021-11-08 | 2021-11-10
R048 | Andrew | Vijay | 2021-11-01 | 2021-11-08 | 2021-11-09 | 2021-11-12 | 2021-11-15 | 2021-11-23 | 2021-11-24 | 2021-11-26 |  |  | R048 | 2021-09-23 | 2021-09-30 | 2021-10-01 | 2021-10-06 | 2021-10-07 | 2021-10-15 | 2021-10-18 | 2021-10-20
R041 | Andrew | Srini | 2021-11-01 | 2021-11-08 | 2021-11-09 | 2021-11-16 | 2021-11-17 | 2021-11-24 | 2021-11-25 | 2021-11-27 |  |  | R041 | 2021-11-01 | 2021-11-05 | 2021-11-08 | 2021-11-15 | 2021-11-16 | 2021-11-23 | 2021-11-24 | 2021-11-26
R064 | Prasad | Percy | 2021-09-07 | 2021-09-14 | 2021-09-15 | 2021-09-22 | 2021-09-23 | 2021-10-11 | 2021-10-12 | 2021-10-17 |  |  | R064 | 2021-09-06 | 2021-09-15 | 2021-09-16 | 2021-09-23 | 2021-09-24 | 2021-10-12 | 2021-10-13 | 2021-10-18
R075 | Zemeer | Percy | 2021-11-01 | 2021-11-08 | 2021-11-09 | 2021-11-15 | 2021-11-16 | 2021-11-23 | 2021-11-24 | 2021-11-26 |  |  | R075 | 2021-10-01 | 2021-10-12 | 2021-10-13 | 2021-10-19 | 2021-10-20 | 2021-10-27 | 2021-10-28 | 2021-10-30
R040 | Andrew | Vijay | 2021-10-04 | 2021-10-11 | 2021-10-12 | 2021-10-15 | 2021-10-18 | 2021-10-26 | 2021-10-27 | 2021-10-29 |  |  | R040 | 2021-10-08 | 2021-10-15 | 2021-10-18 | 2021-10-21 | 2021-10-22 | 2021-11-01 | 2021-11-02 | 2021-11-04
R054 | Andrew | Vijay | 2021-11-16 | 2021-11-23 | 2021-11-24 | 2021-12-03 | 2021-12-06 | 2021-12-22 | 2021-12-23 | 2021-12-28 |  |  | R054 | 2021-10-25 | 2021-11-01 | 2021-11-02 | 2021-11-10 | 2021-11-11 | 2021-11-29 | 2021-11-30 | 2021-12-05
R144 | Zemeer | Vijay | 2021-10-19 | 2021-10-26 | 2021-10-27 | 2021-11-01 | 2021-11-02 | 2021-11-10 | 2021-11-11 | 2021-11-13 |  |  | R144 | 2021-11-22 | 2021-11-29 | 2021-11-30 | 2021-12-03 | 2021-12-06 | 2021-12-14 | 2021-12-15 | 2021-12-17
R145 | Zemeer | Percy | 2021-10-04 | 2021-10-11 | 2021-10-12 | 2021-10-18 | 2021-10-19 | 2021-10-26 | 2021-10-27 | 2021-10-29 |  |  | R145 | 2021-10-18 | 2021-10-27 | 2021-10-28 | 2021-11-03 | 2021-11-04 | 2021-11-11 | 2021-11-12 | 2021-11-14
R033 | Tej | Vijay | 2021-11-03 | 2021-11-10 | 2021-11-11 | 2021-11-18 | 2021-11-19 | 2021-12-07 | 2021-12-08 | 2021-12-13 |  |  | R033 | 2021-12-07 | 2021-12-14 | 2021-12-15 | 2021-12-22 | 2021-12-23 | 2022-01-10 | 2022-01-11 | 2022-01-16
R005 | Simon | Vijay | 2021-10-19 | 2021-10-26 | 2021-10-27 | 2021-11-03 | 2021-11-04 | 2021-12-01 | 2021-12-02 | 2021-12-07 |  |  | R005 | 2022-01-03 | 2022-01-10 | 2022-01-11 | 2022-01-18 | 2022-01-19 | 2022-02-03 | 2022-02-04 | 2022-02-09
R058 | Andrew | Vijay | 2021-11-30 | 2021-12-07 | 2021-12-08 | 2021-12-15 | 2021-12-16 | 2022-01-03 | 2022-01-04 | 2022-01-09 |  |  | R058 | 2022-01-27 | 2022-02-03 | 2022-02-04 | 2022-02-11 | 2022-02-14 | 2022-03-02 | 2022-03-03 | 2022-03-08
R062 | Zemeer | Percy | 2021-11-03 | 2021-11-10 | 2021-11-11 | 2021-11-17 | 2021-11-18 | 2021-11-25 | 2021-11-26 | 2021-11-28 |  |  | R062 | 2021-11-02 | 2021-11-11 | 2021-11-12 | 2021-11-18 | 2021-11-19 | 2021-11-26 | 2021-11-29 | 2021-12-01
R080 | Prasad | Srini | 2021-11-24 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-09 | 2021-12-10 | 2021-12-11 |  |  | R080 | 2021-11-17 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-12-03 | 2021-12-06 | 2021-12-07
R037 | Tej | Percy | 2021-11-30 | 2021-12-07 | 2021-12-08 | 2021-12-24 | 2021-12-27 | 2022-01-12 | 2022-01-13 | 2022-01-18 |  |  | R037 | 2021-11-17 | 2021-11-26 | 2021-11-29 | 2021-12-07 | 2021-12-08 | 2021-12-24 | 2021-12-27 | 2022-01-01
R046 | Simon | Srini | 2021-11-18 | 2021-11-25 | 2021-11-26 | 2021-12-14 | 2021-12-15 | 2021-12-31 | 2022-01-03 | 2022-01-08 |  |  | R046 | 2021-11-29 | 2021-12-03 | 2021-12-06 | 2021-12-14 | 2021-12-15 | 2021-12-31 | 2022-01-03 | 2022-01-08
R053 | Andrew | Srini | 2021-12-02 | 2021-12-09 | 2021-12-10 | 2021-12-17 | 2021-12-20 | 2022-01-05 | 2022-01-06 | 2022-01-11 |  |  | R053 | 2021-12-27 | 2021-12-31 | 2022-01-03 | 2022-01-10 | 2022-01-11 | 2022-01-27 | 2022-01-28 | 2022-02-02
R068 | Zemeer | Percy | 2021-11-18 | 2021-11-25 | 2021-11-26 | 2021-12-03 | 2021-12-06 | 2021-12-22 | 2021-12-23 | 2021-12-28 |  |  | R068 | 2021-12-15 | 2021-12-24 | 2021-12-27 | 2022-01-03 | 2022-01-04 | 2022-01-20 | 2022-01-21 | 2022-01-26
R077 | Prasad | Percy | 2021-12-02 | 2021-12-09 | 2021-12-10 | 2021-12-16 | 2021-12-17 | 2021-12-24 | 2021-12-27 | 2021-12-29 |  |  | R077 | 2022-01-11 | 2022-01-20 | 2022-01-21 | 2022-01-27 | 2022-01-28 | 2022-02-04 | 2022-02-07 | 2022-02-09
R095 | Tej | Srini | 2021-12-29 | 2022-01-05 | 2022-01-06 | 2022-01-11 | 2022-01-12 | 2022-01-19 | 2022-01-20 | 2022-01-22 |  |  | R095 | 2022-01-21 | 2022-01-27 | 2022-01-28 | 2022-02-02 | 2022-02-03 | 2022-02-10 | 2022-02-11 | 2022-02-13
TBD | [12 empty] | R183 | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-10 | Chris Chase | Lui Bai
TBD | [12 empty] | R184 | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-10 | John Gualdoni | Lui Bai
TBD | [12 empty] | R185 | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-10 | John Gualdoni | Lui Bai
TBD | [12 empty] | R147 | 2021-08-23 | 2021-09-03 | 2021-08-23 | 2021-09-03 | 2021-09-06 | 2021-10-08 | 2021-09-06 | 2021-10-08 | Samantha Fishel | Lui Bai
TBD | [12 empty] | R138 | 2021-09-06 | 2021-09-17 | 2021-09-06 | 2021-09-17 | 2021-09-20 | 2021-10-08 | 2021-09-20 | 2021-10-08 | Chris Chase | Lui Bai
[13 empty] | R168 | 2021-10-04 | 2021-10-15 | 2021-10-04 | 2021-10-15 | 2021-10-18 | 2021-11-05 | 2021-10-18 | 2021-11-05 | Chris Chase | Lui Bai
[13 empty] | R186 | 2021-10-04 | 2021-10-15 | 2021-10-04 | 2021-10-15 | 2021-10-18 | 2021-11-05 | 2021-10-18 | 2021-11-05 | Brian Odonnel | Lui Bai
[13 empty] | R135 | 2021-11-08 | 2021-11-19 | 2021-11-08 | 2021-11-19 | 2021-11-22 | 2021-12-10 | 2021-11-22 | 2021-12-10 | Brian Odonnel | Lui Bai
[13 empty] | R136 | 2021-11-08 | 2021-11-19 | 2021-11-08 | 2021-11-19 | 2021-11-22 | 2021-12-10 | 2021-11-22 | 2021-12-10 | Chris Chase | Lui Bai
[13 empty] | R137 | 2021-11-08 | 2021-11-19 | 2021-11-08 | 2021-11-19 | 2021-11-22 | 2021-12-10 | 2021-11-22 | 2021-12-10 | Brian Odonnel | Lui Bai
[13 empty] | R170 | 2021-11-18 | 2021-11-29 | 2021-11-18 | 2021-11-29 | 2021-11-30 | 2021-12-03 | 2021-11-30 | 2021-12-03 | Chris Chase | Lui Bai
RICE ID | Functional Owner | Technical Owner | Planned Functional Specification Start Date | Planned Functional Specification End Date | Planned Technical Specification Start Date | Planned Technical Specification End Date | Planned Technical Build Start Date | Planned Technical Build End Date | Planned Unit Test Start Date | Planned Unit Test End Date |  |  | R134 | 2021-11-18 | 2021-11-29 | 2021-11-18 | 2021-11-29 | 2021-11-30 | 2021-12-03 | 2021-11-30 | 2021-12-03 | Brian Odonnel | Lui Bai
R085 | Tej | Srini | 2021-05-17 | 2021-05-18 | 2021-05-19 | 2021-05-28 | 2021-06-28 | 2021-07-14 | 2021-07-15 | 2021-07-15 |  |  | R171 | 2021-11-30 | 2021-12-13 | 2021-11-30 | 2021-12-13 | 2021-12-14 | 2022-01-07 | 2021-12-14 | 2022-01-07 | Chris Chase | Lui Bai
R051 | Jessica | Vijay | 2021-06-18 | 2021-06-25 | 2021-06-28 | 2021-07-05 | 2021-07-06 | 2021-07-22 | 2021-07-23 | 2021-07-23 |  |  | R187 | 2021-11-30 | 2021-12-13 | 2021-11-30 | 2021-12-13 | 2021-12-14 | 2022-01-07 | 2021-12-14 | 2022-01-07 | Brian Odonnel | Lui Bai
R019 | Trinh | Srini | 2021-07-08 | 2021-07-15 | 2021-07-16 | 2021-07-23 | 2021-07-26 | 2021-08-11 | 2021-08-12 | 2021-08-12
R025 | Trinh | Vijay | 2021-07-15 | 2021-07-22 | 2021-07-23 | 2021-07-30 | 2021-08-02 | 2021-08-18 | 2021-08-19 | 2021-08-19
R098 | Tej | Percy | 2021-07-07 | 2021-07-14 | 2021-07-15 | 2021-07-20 | 2021-07-21 | 2021-07-28 | 2021-07-29 | 2021-07-29
R097 | Tej | Srini | 2021-08-04 | 2021-08-11 | 2021-08-12 | 2021-08-17 | 2021-08-18 | 2021-08-25 | 2021-08-26 | 2021-08-26
R082 | Tej | Srini | 2021-08-11 | 2021-08-18 | 2021-08-19 | 2021-08-27 | 2021-08-30 | 2021-09-15 | 2021-09-16 | 2021-09-16
R031 | Trinh | Vijay | 2021-08-18 | 2021-08-25 | 2021-08-26 | 2021-08-31 | 2021-09-01 | 2021-09-10 | 2021-09-13 | 2021-09-13
R026 | Jessica | Vijay | 2021-09-08 | 2021-09-15 | 2021-09-16 | 2021-09-23 | 2021-09-24 | 2021-10-12 | 2021-10-13 | 2021-10-13
R071 | Prasad | Percy | 2021-07-21 | 2021-07-28 | 2021-07-29 | 2021-08-05 | 2021-08-06 | 2021-08-24 | 2021-08-25 | 2021-08-25
R072 | Zemeer | Percy | 2021-08-18 | 2021-08-25 | 2021-08-26 | 2021-09-01 | 2021-09-02 | 2021-09-09 | 2021-09-10 | 2021-09-10
R002 | Simon | Srini | 2021-10-05 | 2021-10-12 | 2021-10-13 | 2021-10-20 | 2021-10-21 | 2021-11-08 | 2021-11-09 | 2021-11-09
R003 | Simon | Srini | 2021-08-17 | 2021-08-24 | 2021-08-25 | 2021-08-30 | 2021-08-31 | 2021-09-07 | 2021-09-08 | 2021-09-08
R048 | Andrew | Vijay | 2021-11-01 | 2021-11-08 | 2021-11-09 | 2021-11-12 | 2021-11-15 | 2021-11-23 | 2021-11-24 | 2021-11-24
R041 | Andrew | Srini | 2021-11-01 | 2021-11-08 | 2021-11-09 | 2021-11-16 | 2021-11-17 | 2021-11-24 | 2021-11-25 | 2021-11-25
R064 | Prasad | Percy | 2021-09-02 | 2021-09-09 | 2021-09-10 | 2021-09-17 | 2021-09-20 | 2021-10-06 | 2021-10-07 | 2021-10-07
R075 | Zemeer | Percy | 2021-11-01 | 2021-11-08 | 2021-11-09 | 2021-11-15 | 2021-11-16 | 2021-11-23 | 2021-11-24 | 2021-11-24
R040 | Andrew | Vijay | 2021-09-29 | 2021-10-06 | 2021-10-07 | 2021-10-12 | 2021-10-13 | 2021-10-21 | 2021-10-22 | 2021-10-22
R054 | Andrew | Vijay | 2021-11-16 | 2021-11-23 | 2021-11-24 | 2021-12-03 | 2021-12-06 | 2021-12-22 | 2021-12-23 | 2021-12-23
R144 | Zemeer | Vijay | 2021-10-14 | 2021-10-21 | 2021-10-22 | 2021-10-27 | 2021-10-28 | 2021-11-05 | 2021-11-08 | 2021-11-08
R145 | Zemeer | Percy | 2021-09-29 | 2021-10-06 | 2021-10-07 | 2021-10-13 | 2021-10-14 | 2021-10-21 | 2021-10-22 | 2021-10-22
R033 | Tej | Vijay | 2021-10-29 | 2021-11-05 | 2021-11-08 | 2021-11-15 | 2021-11-16 | 2021-12-02 | 2021-12-03 | 2021-12-03
R005 | Simon | Vijay | 2021-10-14 | 2021-10-21 | 2021-10-22 | 2021-10-29 | 2021-11-01 | 2021-11-26 | 2021-11-29 | 2021-11-29
R058 | Andrew | Vijay | 2021-11-25 | 2021-12-02 | 2021-12-03 | 2021-12-10 | 2021-12-13 | 2021-12-29 | 2021-12-30 | 2021-12-30
R062 | Zemeer | Percy | 2021-10-29 | 2021-11-05 | 2021-11-08 | 2021-11-12 | 2021-11-15 | 2021-11-22 | 2021-11-23 | 2021-11-23
R080 | Prasad | Srini | 2021-11-19 | 2021-11-26 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-06 | 2021-12-07 | 2021-12-07
R037 | Tej | Percy | 2021-11-25 | 2021-12-02 | 2021-12-03 | 2021-12-21 | 2021-12-22 | 2022-01-07 | 2022-01-10 | 2022-01-10
R046 | Simon | Srini | 2021-11-15 | 2021-11-22 | 2021-11-23 | 2021-12-09 | 2021-12-10 | 2021-12-28 | 2021-12-29 | 2021-12-29
R053 | Andrew | Srini | 2021-11-29 | 2021-12-06 | 2021-12-07 | 2021-12-14 | 2021-12-15 | 2021-12-31 | 2022-01-03 | 2022-01-03
R068 | Zemeer | Percy | 2021-11-15 | 2021-11-22 | 2021-11-23 | 2021-11-30 | 2021-12-01 | 2021-12-17 | 2021-12-20 | 2021-12-20
R077 | Prasad | Percy | 2021-11-29 | 2021-12-06 | 2021-12-07 | 2021-12-13 | 2021-12-14 | 2021-12-21 | 2021-12-22 | 2021-12-22
R095 | Tej | Srini | 2021-12-24 | 2021-12-31 | 2022-01-03 | 2022-01-06 | 2022-01-07 | 2022-01-14 | 2022-01-17 | 2022-01-17
Formulas:
Planned Technical Build End Date = WORKDAY([Planned Technical Build Start Date],12)
Planned Unit Test Start Date = WORKDAY([Planned Technical Build End Date],1)
Planned Unit Test Start Date = WORKDAY([Planned Technical Specification End Date],1,5)
Planned Unit Test End Date = [Planned Unit Test Start Date]+M46
Planned Unit Test End Date = WORKDAY([Planned Technical Specification End Date],19, 5)
Planned Technical Build Start Date = WORKDAY([Planned Technical Specification End Date],1)
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add a column Deloitte Owned District Owned Deloitte Response: Column inserted with the above options
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unit Testing Deloitte Response: Columns AJ-AN reflect Unit Testing
Note on AC1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unit Testing Deloitte Response: Columns AJ-AN reflect Unit Testing
Note on B45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add a column Deloitte Owned District Owned Deloitte Response: Column inserted with the above options
Note on J45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unit Testing Deloitte Response: Columns AJ-AN reflect Unit Testing

## Doc Control Info
Document Control Information
Document Information |  | (C.3.5.1) This tracker includes an itemized list of RICE objects organized by type. This list provides details on the type of object, target Release and Sprint, as well as other attributes that help in traceability of the development teams’ efforts. This list was built during the time period prior to Pre-Construction/Ramp-up Phase and updated throughout each Phase and serves as a working document to track the build, unit test and deployment of each RICE object.
Document Identification |  | RICEW Tracker
Document Name |  | RICEW Tracker
Project Name |  | District Integrated Financial System (DIFS)
Client |  | District of Columbia
Document Author |  | Fayaz Syed/Divya Kotwani
Document Version |  | 1.0
Document Status |  | Initial Draft
Date Released |  | 2021-02-22
Document Edit History
Version | Date | Additions/Modifications | Prepared/Revised By
1 | 2021-02-22 | Initial draft | Fayaz Syed/Divya K
2 | 2021-11-29 | Updated version | Tej M/PMO

## RICEW Master
Oracle Cloud Implementation | [26 empty] | `
RICE Tracker | [5 empty] | x | [13 empty] | 2022-05-13
[20 empty] | DO NOT UPDATE, SET TO FORMULA | [33 empty] | DO NOT UPDATE, SET TO FORMULA
RICE ID | Object Type | Process Area | DIFS Object Name | Description | Phase | System | Sprint/Mock Cycle | Report/Interface Type | Report/Interface Direction | Update COA | ERP/EPM Object Type | System Owner | Source System | Target System | Complexity Level | Priority (MoSCoW) | Functional Owner | Technical Owner | Deloitte/District Owned | Current State (Not Started, Functional Specification, Technical Specification, District Review, Technical Build, Functional Testing, Complete) | Active? | Expected Phase | Current Phase | # Of Days Behind | Spec Status | Planned Functional Specification Start Date | Planned Functional Specification End Date | Actual Functional Specification Start Date | Actual Functional Specification End Date | Functional Specification Status | Planned Technical Specification Start Date | Planned Technical Specification End Date | Actual Technical Specification Start Date | Actual Technical Specification End Date | Technical Specification Status | Last Review update Date | WP Status | District Work Product Review, Date Approval Provided From District | Planned Technical Build Start Date | Planned Technical Build End Date | Actual Technical Build Start Date | Actual Technical Build End Date | Build Status | Planned Unit Test Start Date | Planned Unit Test End Date | Actual Unit Test Start Date | Actual Unit Test End Date | Unit Test Status | Received Actual Source File | Included in Phase/Milestone | Overall Status | Comments | In Scope | Func | Tech | Build | Unit | Estimated Total | Estimated Spec | Estimated Build/Unit | Actual Total | Actual Spec | Actual Build/Unit | Expected Total | Expected Spec | Expected Buil/Unit
C001 | Conversion | Procure to Pay | Suppliers | Includes Suppliers, Supplier Addresses, Supplier Sites, Supplier Site Assignments, Supplier Contacts. | Phase 1 | ERP Cloud | 1 | [7 empty] | Very High |  | Prasad Potturi | Rajbir Virk | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-02-08 | 2021-02-12 | 2021-02-03 | 2021-02-24 | 100% - Complete | 2021-02-16 | 2021-03-05 | 2021-02-26 | 2021-03-08 | 100% - Complete | 2021-04-26 | Approved | 2021-04-26 | 2021-03-08 | 2021-04-09 | 2021-03-15 | 2021-03-29 | 100% - Complete | 2021-04-12 | 2021-04-16 | 2021-04-12 | 2021-04-16 | 100% - Complete |  | RICE 1 |  | District approved with comments on open item."Approved . The only feedback is that open items will need to be addressed as we go along." |  | 60 | 140 | 260 | 70 | 530 | 200 | 330 | 530 | 200 | 330 | 530 | 200 | 330
C002 | Conversion | Order to Cash | Customers | Convert all active Customers, Addresses, and customer contacts related to converted open/historical AR Invoices and Open Grants. | Phase 1 | ERP Cloud | 1 | [7 empty] | Medium |  | Andrew Fedoris | ShashiKumar Govindaiah | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2020-09-28 | 2020-10-02 | 2020-09-28 | 2020-10-02 | 100% - Complete | 2020-10-05 | 2020-10-09 | 2020-10-05 | 2020-10-09 | 100% - Complete | 2020-10-14 | Approved | 2020-10-14 | 2020-10-15 | 2020-11-06 | 2020-10-12 | 2020-11-09 | 100% - Complete | 2020-11-09 | 2020-11-20 | 2020-11-10 | 2021-01-10 | 100% - Complete |  | RICE 1 |  |  |  | 30 | 48 | 80 | 18 | 176 | 78 | 98 | 176 | 78 | 98 | 176 | 78 | 98
C003 | Conversion | Budget to Report | General Ledger Budget Balances | FY22 Original and revised budget will be converted into ERP from SOAR. Carry over funding will be loaded post Go-Live. FY23 Budget will be loaded from BFA at Go-live. | Phase 1 | ERP Cloud | 1 | [7 empty] | High |  | Trinh Trinh | Rajbir Virk | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2020-10-26 | 2020-10-30 | 2020-10-26 | 2020-10-30 | 100% - Complete | 2020-11-02 | 2020-11-13 | 2020-11-04 | 2020-11-15 | 100% - Complete | 2021-12-01 | Approved | 2021-12-01 | 2020-11-17 | 2020-12-11 | 2020-12-21 | 2021-02-19 | 100% - Complete | 2020-12-14 | 2021-01-08 | 2021-02-01 | 2021-02-21 | 100% - Complete |  | RICE 1 |  |  |  | 40 | 100 | 200 | 60 | 400 | 140 | 260 | 400 | 140 | 260 | 400 | 140 | 260
C004 | Conversion | Projects and Grants | Projects | Convert all projects where agency is Active, and the projects have had Financial Project Activity. Financial project activity equates to a remaining budgeted balance > 0, and financial activity based on Project Activity that impacts the budget for the Project. | Phase 1 | ERP Cloud | 1 | [7 empty] | Medium |  | Jagannathan Viswanathan | Pavan Pemavath | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2020-10-05 | 2020-10-09 | 2020-10-05 | 2020-10-07 | 100% - Complete | 2020-10-12 | 2020-10-23 | 2020-10-13 | 2020-10-23 | 100% - Complete | 2021-11-10 | Approved | 2021-11-10 | 2020-10-27 | 2020-11-20 | 2020-10-19 | 2020-11-24 | 100% - Complete | 2020-11-23 | 2020-12-04 | 2020-11-25 | 2021-01-20 | 100% - Complete |  | RICE 1 |  |  |  | 30 | 48 | 80 | 18 | 176 | 78 | 98 | 176 | 78 | 98 | 176 | 78 | 98
C005 | Conversion | Projects and Grants | Project Tasks | Convert all project tasks related to the projects uploaded during Data Conversion. | Phase 1 | ERP Cloud | 1 | [7 empty] | Medium |  | Jagannathan Viswanathan | Pavan Pemavath | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2020-10-05 | 2020-10-09 | 2020-10-05 | 2020-10-07 | 100% - Complete | 2020-10-12 | 2020-10-23 | 2020-10-13 | 2020-10-23 | 100% - Complete | 2020-10-27 | Approved | 2020-10-27 | 2020-10-27 | 2020-11-20 | 2020-10-19 | 2020-11-24 | 100% - Complete | 2020-11-23 | 2020-12-04 | 2020-11-25 | 2021-01-20 | 100% - Complete |  | RICE 1 |  |  |  | 30 | 48 | 80 | 18 | 176 | 78 | 98 | 176 | 78 | 98 | 176 | 78 | 98
C006 | Conversion | Projects and Grants | Awards | Create all project awards related to the projects selected for Data Conversion. In addition, convert all grants as awards where the grants selected should have had Financial grant Activity (remaining budgeted balance > 0) | Phase 1 | ERP Cloud | 1 | [7 empty] | Medium |  | Jagannathan Viswanathan | Pavan Pemavath | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2020-10-12 | 2020-10-16 | 2020-10-13 | 2020-10-15 | 100% - Complete | 2020-10-19 | 2020-10-30 | 2020-10-26 | 2020-10-30 | 100% - Complete | 2020-11-18 | Approved | 2020-11-18 | 2020-11-03 | 2020-11-27 | 2020-11-09 | 2020-12-22 | 100% - Complete | 2020-11-30 | 2020-12-11 | 2021-01-07 | 2021-01-30 | 100% - Complete |  | RICE 1 |  |  |  | 30 | 48 | 80 | 18 | 176 | 78 | 98 | 176 | 78 | 98 | 176 | 78 | 98
C007 | Conversion | Projects and Grants | Project Budgets | Convert the total lifetime budget amount, plus any revisions related to the subset of projects identified as part of projects conversion. | Phase 1 | ERP Cloud | 1 | [7 empty] | Medium |  | Jagannathan Viswanathan | Pavan Pemavath | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-01-19 | 2021-02-01 | 2021-01-25 | 2021-02-05 | 100% - Complete | 2021-02-16 | 2021-02-26 | 2021-02-09 | 2021-02-24 | 100% - Complete | 2021-03-10 | Approved | 2021-03-10 | 2021-03-04 | 2021-03-22 | 2021-03-18 | 2021-04-08 | 100% - Complete | 2021-04-26 | 2021-04-30 | 2021-05-03 | 2021-05-11 | 100% - Complete |  | RICE 1 |  |  |  | 30 | 48 | 80 | 18 | 176 | 78 | 98 | 176 | 78 | 98 | 176 | 78 | 98
C008 | Conversion | Procure to Pay | Requisitions | Convert open requisition balances which will create corresponding pre-encumbrance (commitment) entries. | Phase 1 | ERP Cloud | 2 | [7 empty] | High |  | Prasad Potturi | ShashiKumar Govindaiah | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-03-15 | 2021-03-26 | 2021-03-15 | 2021-03-30 | 100% - Complete | 2021-03-22 | 2021-04-07 | 2021-04-01 | 2021-05-14 | 100% - Complete | 2021-05-24 | Approved | 2021-05-24 | 2021-04-12 | 2021-05-17 | 2021-04-21 | 2021-05-17 | 100% - Complete | 2021-05-17 | 2021-05-19 | 2021-05-17 | 2021-05-21 | 100% - Complete |  | RICE 1 |  | Update on 05/12/2021:Incorporating feedback - more discussion required - feedback will be completed by 05/14/21 |  | 40 | 100 | 200 | 60 | 400 | 140 | 260 | 400 | 140 | 260 | 400 | 140 | 260
C009 | Conversion | Procure to Pay | Purchase Orders | Convert capital PO’s with open balance | Phase 1 | ERP Cloud | 2 | [7 empty] | High |  | Sravana Atmakuru | Rajbir Virk | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-01 | 2021-04-16 | 2021-04-01 | 2021-04-19 | 100% - Complete | 2021-04-07 | 2021-04-21 | 2021-04-08 | 2021-04-21 | 100% - Complete | 2021-06-28 | Approved | 2021-06-28 | 2021-04-26 | 2021-05-21 | 2021-06-07 | 2021-06-21 | 100% - Complete | 2021-05-21 | 2021-05-26 | 2021-07-21 | 2021-07-23 | 100% - Complete |  | RICE 1 |  | 07/08/2021: The Unit Test will be at the end of July - this object is part of the Mock 2 Cycle and will be on hold until the end of Mock 2/End of July |  | 40 | 100 | 200 | 60 | 400 | 140 | 260 | 400 | 140 | 260 | 400 | 140 | 260
C010 | Conversion | Procure to Pay | PO Receipts | Convert open POs and un-invoiced PO receipts in order to match Invoices entered after Go Live. | Phase 1 | ERP Cloud | 2 | [7 empty] | High |  | Sravana Atmakuru | ShashiKumar Govindaiah | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-05-03 | 100% - Complete | 2021-04-26 | 2021-05-07 | 2021-05-03 | 2021-05-07 | 100% - Complete | 2021-07-06 | Approved | 2021-07-06 | 2021-06-03 | 2021-07-09 | 2021-05-12 | 2021-07-23 | 100% - Complete | 2021-07-12 | 2021-07-14 | 2021-07-23 | 2021-07-26 | 100% - Complete |  | RICE 1 |  | 07/15/2021: The Unit Testing will be completed at the end of Mock 2 |  | 40 | 100 | 200 | 60 | 400 | 140 | 260 | 400 | 140 | 260 | 400 | 140 | 260
C011 | Conversion | Procure to Pay | AP Invoices | Convert all unpaid, open or partially-paid invoices along with the PO line and Receipt details (PO amounts related to paid and closed portion of PO will not be converted). | TBD | ERP Cloud | 2 | [7 empty] | High |  | Sravana Atmakuru | ShashiKumar Govindaiah | Deloitte Owned | Offtrack (Active) | Active | N/A | 1-Functional Spec | -266 | Approved | 2021-06-14 | 2021-08-20 | 2021-07-07 |  | 75% - In Review | 2021-06-03 | 2021-06-22 | 2021-07-12 |  | 75% - In Review | N/A | N/A | N/A | 2021-06-07 | 2021-07-13 | 2021-07-26 |  | 25% - In Progress | 2021-07-14 | 2021-07-14 |  |  |  |  | RICE 4 |  | 08/12/2021: Still on hold |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C012 | Conversion | Acquire to Retire | Fixed Asset Mass Additions | Convert all assets that are greater than $5000 in value | Phase 1 | ERP Cloud | 3 | [7 empty] | High |  | Jake Loughridge | Adil Baig | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-03 | 2021-06-18 | 2021-05-03 | 2021-09-01 | 100% - Complete | 2021-06-29 | 2021-07-19 | 2021-08-25 | 2021-09-01 | 100% - Complete | 2021-10-15 | Approved | 2021-10-15 | 2021-07-19 | 2021-08-23 | 2021-08-24 | 2021-09-20 | 100% - Complete | 2021-08-23 | 2021-08-23 | 2021-09-21 | 2021-10-01 | 100% - Complete |  | RICE 2 |  | 09/23/2021: Loading all the data - reviews scheduled |  | 40 | 100 | 200 | 60 | 400 | 140 | 260 | 400 | 140 | 260 | 400 | 140 | 260
C013 | Conversion | Order to Cash | Customers' Open Invoices | Open AR transactions non-related to Projects will be extracted for the conversion. | Phase 1 | ERP Cloud | 3 | [7 empty] | High |  | Andrew Fedoris | Adil Baig | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-10 | 2021-06-30 | 2021-06-07 | 2021-06-21 | 100% - Complete | 2021-06-09 | 2021-06-25 | 2021-06-21 | 2021-07-21 | 100% - Complete | 2021-08-06 | Approved | 2021-08-06 | 2021-06-28 | 2021-08-03 | 2021-07-30 | 2021-08-04 | 100% - Complete | 2021-08-03 | 2021-08-05 | 2021-08-05 | 2021-08-20 | 100% - Complete |  | RICE 2 |  | 08/12/2021: No SR needed able to resolve |  | 40 | 100 | 200 | 60 | 400 | 140 | 260 | 400 | 140 | 260 | 400 | 140 | 260
C014 | Conversion | Projects and Grants | Project Costs | Convert the inception to date costs related to the projects and award selected for the Data Conversion. | Phase 1 | ERP Cloud | 1 | [7 empty] | High |  | Jagannathan Viswanathan | Pavan Pemavath | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-02-02 | 2021-02-16 | 2021-01-25 | 2021-02-05 | 100% - Complete | 2021-02-17 | 2021-03-01 | 2021-02-09 | 2021-02-24 | 100% - Complete | 2021-03-08 | Approved | 2021-03-08 | 2021-03-25 | 2021-04-07 | 2021-03-29 | 2021-04-09 | 100% - Complete | 2021-04-15 | 2021-04-30 | 2021-05-03 | 2021-05-12 | 100% - Complete |  | RICE 1 |  |  |  | 40 | 100 | 200 | 60 | 400 | 140 | 260 | 400 | 140 | 260 | 400 | 140 | 260
C015 | Conversion | Projects and Grants | Project & Grants Billing events | Convert the inception to date Cash and Accured revenue related to the projects selected for project conversion. These amounts are for grants only. | Phase 1 | ERP Cloud | 3 | [7 empty] | Medium |  | Jagannathan Viswanathan | Pavan Pemavath | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-25 | 2021-05-31 | 2021-05-18 | 2021-05-31 | 100% - Complete | 2021-06-01 | 2021-06-07 | 2021-05-27 | 2021-06-07 | 100% - Complete | 2021-06-23 | Approved | 2021-06-23 | 2021-06-01 | 2021-06-14 | 2021-06-04 | 2021-06-18 | 100% - Complete | 2021-06-22 | 2021-06-22 | 2021-08-09 | 2021-08-10 | 100% - Complete |  | RICE 1 |  | 08/05/2021: issues have pushed unit testing date again |  | 30 | 48 | 80 | 18 | 176 | 78 | 98 | 176 | 78 | 98 | 176 | 78 | 98
C016 | Conversion | Projects and Grants | Project & Grants Revenue events | Based upon Billing data extract for the selected Projects for Data Conversion, Revenue Events will be created to generate Projects Revenue. | Phase 1 | ERP Cloud | 3 | [7 empty] | High |  | Jagannathan Viswanathan | Pavan Pemavath | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-17 | 2021-05-21 | 2021-05-18 | 2021-05-31 | 100% - Complete | 2021-06-15 | 2021-07-01 | 2021-05-27 | 2021-06-07 | 100% - Complete | 2021-07-23 | Approved | 2021-07-23 | 2021-07-01 | 2021-08-06 | 2021-06-04 | 2021-06-18 | 100% - Complete | 2021-08-09 | 2021-08-11 | 2021-08-09 | 2021-08-10 | 100% - Complete |  | RICE 1 |  | We plan to have the functional walk through of both C015 and C016 below on June-2, Wednesday. Jake- Please schedule at least 1.5 hours as covering C015 will make covering C016 simpler |  | 40 | 100 | 200 | 60 | 400 | 140 | 260 | 400 | 140 | 260 | 400 | 140 | 260
C017 | Conversion | Order to Cash | AR Receipts | Convert the inception to date revenue related to the projects selected for data conversion. Cash Revenue amounts are converted as Project Receipts. Actual AR transactions for conversion will need to be determined. | Phase 1 | ERP Cloud | 3 | [7 empty] | Medium |  | Jagannathan Viswanathan | Pavan Pemavath | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-15 | 2021-06-18 | 2021-06-07 | 2021-06-11 | 100% - Complete | 2021-07-12 | 2021-07-20 | 2021-06-11 | 2021-06-11 | 100% - Complete | 2021-07-12 | Approved | 2021-07-12 | 2021-07-22 | 2021-08-05 | 2021-08-02 | 2021-08-09 | 100% - Complete | 2021-08-03 | 2021-08-05 | 2021-08-10 | 2021-08-11 | 100% - Complete |  | RICE 1 |  | 08/09/2021: Need to talk to Keenan and review lean spec |  | 30 | 48 | 80 | 18 | 176 | 78 | 98 | 176 | 78 | 98 | 176 | 78 | 98
C018 | Conversion | Budget to Report | GL Balances | Convert all actual balances and subsequent transactions for FY21 and FY22 | Phase 1 | ERP Cloud | 1 | [7 empty] | Medium |  | Trinh Trinh | Rajbir Virk | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2020-10-19 | 2020-10-23 | 2020-10-21 | 2020-10-23 | 100% - Complete | 2020-10-26 | 2020-11-06 | 2020-10-29 | 2020-11-06 | 100% - Complete | 2021-11-20 | Approved | 2021-11-20 | 2020-11-10 | 2020-12-04 | 2020-12-14 | 2021-02-12 | 100% - Complete | 2020-12-07 | 2020-12-18 | 2021-02-01 | 2021-02-19 | 100% - Complete |  | RICE 1 |  |  |  | 30 | 48 | 80 | 18 | 176 | 78 | 98 | 176 | 78 | 98 | 176 | 78 | 98
C019 | Conversion | Procure to Pay | Supplier Bank Account, Assignment and External Payee | Convert all bank accounts related to the suppliers uploaded during Data Conversion. | Phase 1 | ERP Cloud | 1 | [7 empty] | Very High |  | Prasad Potturi | Rajbir Virk | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-02-23 | 2021-02-26 | 2021-02-19 | 2021-02-26 | 100% - Complete | 2021-02-26 | 2021-03-05 | 2021-03-01 | 2021-03-15 | 100% - Complete | 2021-04-01 | Approved | 2021-04-01 | 2021-04-26 | 2021-04-30 | 2021-03-15 | 2021-03-29 | 100% - Complete | 2021-05-03 | 2021-05-07 | 2021-05-03 | 2021-05-07 | 100% - Complete |  | RICE 1 |  |  |  | 60 | 140 | 260 | 70 | 530 | 200 | 330 | 530 | 200 | 330 | 530 | 200 | 330
C020 | Conversion | Budget | General Ledger Budget Balances (BFA to EPM) | Convert FY23 Approved Budget from BFA to EPM | Phase 1 | EPM Cloud | 5 | [5 empty] | BFA | EPM | Low |  | Sushant Deshpande | Rajbir/Pavan | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-06 | 2021-10-22 | 2021-07-30 | 2021-11-05 | 100% - Complete | 2021-07-19 | 2021-07-23 | 2021-11-08 | 2021-12-03 | 100% - Complete | 2022-01-07 | Approved | 2022-01-07 | 2021-08-09 | 2021-08-27 | 2021-12-07 | 2022-01-07 | 100% - Complete | 2021-08-30 | 2021-09-10 | 2022-12-07 | 2022-01-07 | 100% - Complete |  | RICE 3 |  | 11/04/2021: New File received - team still reviewing the new file 11/05/2021 - Functional specs complete |  | 30 | 35 | 50 | 5 | 120 | 65 | 55 | 120 | 65 | 55 | 120 | 65 | 55
C021 | Conversion | Budget to Report | Original 6-year Budget Authority for Capital Projects | Convert Original 6-year Budget Authority for Capital Projects from SOAR to EPM | Phase 2 | EPM Cloud | [6 empty] | SOAR | EPM | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E001 | Extension | Procure to Pay | Liability Offsets | Liability Offsets - Federal Liability Offset | Phase 1 | ERP Cloud | Sprint 11 | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Very High |  | Andrew Fedoris | Hima | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 4-Unit Test | -105 | In Review | 2021-10-18 | 2021-11-01 | 2021-10-26 | 2021-12-20 | 100% - Complete | 2021-11-09 | 2022-01-14 | 2022-01-04 | 2022-01-14 | 100% - Complete | 2022-02-18 | 1st Walkthrough Complete |  | 2021-12-02 | 2022-01-13 | 2022-01-13 | 2022-02-14 | 100% - Complete | 2022-01-14 | 2022-01-28 | 2022-02-01 |  | 75% - In Review |  | RICE 4 |  | 02/17/2022: might be different/obsolete after the meeting with District today - liability offsets might look different going forward. Will sprint what we have but the go forward might be different 02/15/2022: Walkthrough on 02/18/2022 for E001 02/03/2022: dependent on other integrations - if no more changes close next week 07/08/2021: Shifting Offset Liability dates - CR 728636 | Yes | 50 | 140 | 220 | 50 | 460 | 190 | 270 | 447.5 | 190 | 257.5 | 460 | 190 | 270
E002 | Extension | Projects and Grants | Funding Patterns | Funding Patterns | Phase 1 | ERP Cloud | Sprint 10 | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Very High |  | Rohan Patel | Lalitha Gollapudi | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-05 | 2021-07-26 | 2021-08-05 | 2021-08-20 | 100% - Complete | 2021-08-10 | 2021-08-30 | 2021-08-27 | 2021-09-08 | 100% - Complete | 2021-10-07 | Approved | 2021-10-07 | 2021-08-31 | 2021-10-08 | 2021-09-10 | 2021-09-24 | 100% - Complete | 2021-10-12 | 2021-10-25 | 2021-09-27 | 2021-10-04 | 100% - Complete |  | RICE 2 | Sprinted | 09/16/2021: Review call scheduled | Yes | 50 | 140 | 220 | 50 | 460 | 190 | 270 | 460 | 190 | 270 | 460 | 190 | 270
E003 | Extension | Budget To Report | Legacy Crosswalk Generation | Extension for reverse crosswalk from DIFS COA/PATEO to SOAR COA and Index/PCA. This is needed when new DIFS values are added so that existing agency systems such as PASS, PeopleSoft, MMIS etc. can consume these values in SOAR structure. | Phase 1 | ERP Cloud | Sprint 09 | Online | Bidirectional | Y | ERP | OCFO | ERP | TBD | Very High |  | Rohan Patel | Hima | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-15 | 2021-10-29 | 2021-09-15 | 2021-11-04 | 100% - Complete | 2021-11-01 | 2021-11-17 | 2021-10-25 | 2021-11-09 | 100% - Complete | 2021-11-09 | Approved | 2021-11-09 | 2021-11-18 | 2021-12-31 | 2021-11-01 | 2021-12-01 | 100% - Complete | 2021-12-14 | 2021-12-28 | 2021-11-22 | 2022-01-27 | 100% - Complete |  | RICE 3 |  | this was approved(1/22/2021) and tested during the pre-construction and the RICE ID was I005. |  | 50 | 140 | 220 | 50 | 460 | 190 | 270 | 460 | 190 | 270 | 460 | 190 | 270
E004 | Extension | Projects and Grants | P&G Hold Unpaid Expenses for Billing | P&G Hold Unpaid Expenses for Billing | Phase 1 | ERP Cloud | Sprint 10 | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Medium |  | Tej Mehta | ShashiKumar Govindaiah | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-29 | 2021-12-03 | 2021-11-29 | 2021-12-07 | 100% - Complete | 2021-12-16 | 2022-01-30 | 2021-12-16 | 2022-01-26 | 100% - Complete | 2022-02-15 | Approved | 2022-02-15 | 2022-01-31 | 2022-02-14 | 2022-01-26 | 2022-02-02 | 100% - Complete | 2022-02-15 | 2022-02-18 | 2022-02-01 | 2022-02-04 | 100% - Complete |  | RICE 4 |  | 02/03/2022: Tej will update the Spec 1/17/2022 - Opened an SR with Oracle; Solution not achievable via API; May have to revisit the approach |  | 25 | 40 | 80 | 15 | 160 | 65 | 95 | 160 | 65 | 95 | 160 | 65 | 95
E005 | Extension | Order to Cash | The Receivables Invoice Segregation of Duty Page Customization | • Need a page customization for AR invoice creation process. This will ensure Segregation of Duty. • The role, DIFS Customer Maintenance JR, will have the Complete function greyed out or taken away on the invoice page. | Phase 1 | ERP Cloud |  | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Medium |  | Andrew Fedoris | Hima | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2022-01-12 | 2022-01-20 | 2022-01-11 | 2022-01-20 | 100% - Complete | 2022-01-20 | 2022-01-25 | 2022-01-20 | 2022-01-21 | 100% - Complete | 2022-02-24 | Walkthrough Scheduled |  | 2022-01-25 | 2022-01-28 | 2022-01-20 | 2022-01-21 | 100% - Complete | 2022-01-28 | 2022-02-18 | 2022-01-21 | 2022-02-17 | 100% - Complete |  |  |  | 02/10/2022: additional updates requested - Andrew work with Reddy 02/03/2022: Change made today and retested - hope to be done tomorrow TWO CRS: 754533 and 756783 01/27/2022: Andrew has added what would have been E007 to the Functional Spec |  | 25 | 40 | 80 | 15 | 160 | 65 | 95 | 160 | 65 | 95 | 160 | 65 | 95
E006 | Extension | Projects and Grants | P&G Receipt Accrual Extension | Create receipt accrual for Projects and awards, to reflect the Projects accruals correctly. | Phase 1 | ERP Cloud | Sprint 11 | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Medium |  | Tej Mehta | ShashiKumar Govindaiah | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 4-Unit Test | -84 | In Review | 2022-01-17 | 2022-01-24 | 2022-01-24 | 2022-02-02 | 100% - Complete | 2022-01-24 | 2022-01-28 | 2022-02-02 | 2022-02-04 | 100% - Complete | 2022-02-04 | Specification Ready |  | 2022-02-11 | 2022-02-18 | 2022-02-11 | 2022-02-18 | 100% - Complete | 2022-02-18 | 2022-02-22 | 2022-02-18 |  | 75% - In Review |  |  |  | 02/10/2022: working through API issues CR 755308 |  | 25 | 40 | 80 | 15 | 160 | 65 | 95 | 156.25 | 65 | 91.25 | 160 | 65 | 95
E007 | Extension | Procure to Pay | Extension for ACH Acknowledgement Files | After ACH payments are processed through the bank, they send back a confirmation message about which payments successfully transmitted and which ones failed validations and could not be issued. Oracle Cloud currently does not have the capability to read these files and update the payment status automatically. The District currently has a custom program written in SOAR to read these files, automatically update the payment to failed and end date the supplier bank account so that it cannot be used again. We will need to build a custom extension in DIFS to produce the same outcome, voiding the payment and end dating the supplier bank account. | Phase 1 | ERP Cloud | Sprint 11 | [7 empty] | High |  | Muralidhar Pedasanaganti |  | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 0-Not Started | -64 | #N/A | 2022-03-01 | 2022-03-10 |  |  |  | 2022-03-11 | 2022-03-20 |  |  |  | #N/A | #N/A |  | 2022-03-21 | 2022-03-31 |  |  |  | 2022-04-01 | 2022-04-04 | [6 empty] | CR 758998
I001 | Interface | Budget To Report | PeopleSoft - Payroll Costs | Receive Payroll Data of employees and retirees (pensioners) and record them as journal entries in DIFS. Files are sent by payroll group. Multiple files with same file format. This is needed for DIFS for inbound accounting data into Oracle GL. | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | New | Create Journal Entries | OCTO | PeopleSoft | ERP | Medium |  | Jessica Rubin | Divya Teja | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-29 | 2021-05-05 | 2021-05-17 | 2021-05-28 | 100% - Complete | 2021-05-06 | 2021-05-19 | 2021-05-20 | 2021-06-01 | 100% - Complete | 2021-07-11 | Approved | 2021-06-24 | 2021-06-04 | 2021-06-24 | 2021-06-01 | 2021-06-18 | 100% - Complete | 2021-07-13 | 2021-07-15 | 2021-06-21 | 2021-06-25 | 100% - Complete |  | RICE 1 | Tested | 05/05/2021: updated Functional owner to Jagannathan Viswanathan per Fayaz - Need to follow up with Rohan with actual owner - 05/18/2021 Looks like Jessica named Func owner. 05/26/2021 note from Jessica: The functional specs are mainly done, just need to update the mapping information. We have a meeting today at 5:30pm EST to review the tech design – after this meeting, I can give you an official update on the status. Please let me now if you have any questions. | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I002 | Interface | Budget To Report | Peoplesoft - Monthly Payroll Cost Accrual/Reversal | Receive Monthly Payroll cost accrual and reversal data from PeopleSoft. This is needed for DIFS for inbound accounting data into Oracle GL. Client wants to keep it manual and this will be revisited during implementation phase. PS will keep it manual. more details later. | Phase 1 - Manual | ERP Cloud | Sprint 09 | Batch | Inbound | New | Create Journal Entries | OCTO | PeopleSoft | ERP | Medium |  | 0 | 0 | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | 1/18/22: Tushar to follow up with Dheeraj and Fayaz to get the file in oracle format | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I003 | Interface | Budget To Report | PeopleSoft - Yearly Payroll Cost Accrual/Reversal | Receive Yearly Payroll cost accrual and reversal data from PeopleSoft. This is needed for DIFS for inbound accounting data into Oracle GL. Client wants to keep it manual and this will be revisited during implementation phase | Phase 1 - Manual | ERP Cloud | Sprint 09 | Batch | Inbound | New | Create Journal Entries | OCTO | PeopleSoft | ERP | Medium |  | 0 | 0 | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | 1/18/22: Tushar to follow up with Dheeraj and Fayaz to get the file in oracle format | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I004 | Interface | Budget To Report | Peoplesoft - COA Data | Send chart of accounts data from Oracle ERP to PeopleSoft. Peoplesoft will change possibly after phase 2 (Not only segments but also all relational master data) | Phase 1 | ERP Cloud | Sprint 09 | Batch | Outbound | New | Sync COA | OCFO | ERP | PeopleSoft | Medium |  | Trinh Trinh | Lalitha | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-08 | 2021-04-20 | 2021-04-13 | 2021-05-05 | 100% - Complete | 2021-04-21 | 2021-05-18 | 2021-04-21 | 2021-05-05 | 100% - Complete | 2021-05-18 | Approved | 2021-05-18 | 2021-05-10 | 2021-05-31 | 2021-04-29 | 2021-05-07 | 100% - Complete | 2021-07-09 | 2021-07-13 | 2021-05-10 | 2021-05-18 | 100% - Complete |  | RICE 1 | Tested | 05/19/2021 Anu gave approval without consulting additional resource - this will be discussed PMO - there is a pending District decision - item approved prior to decision completed - Action Item? 06/17/2021 - New enhancements, next week | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I005 | Interface | Budget To Report | WMATA - Benefits Interface | Record the expenditures related to union employee (Metro Smart Trip – Transportation Benefit). Every month the employees are allotted $25 to commute to work based on contractual agreement. This interface/file is used to record the expense. This is needed for DIFS for an inbound accounting data into Oracle GL. | Phase 1 - Manual | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Journal Entries | WMATA | NA | ERP | Medium |  | 0 | 0 | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I006 | Interface | Budget To Report | WMATA - Benefits Interface Debit | Record the unused portion of the $25 benefit that employees receive. Every month the employees are allotted $25 to commute to work based on contractual agreement. This interface/file is used to reduce the expenditure for the unused portion. This is needed for DIFS for an inbound accounting data into Oracle GL | Phase 1 - Manual | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Journal Entries | WMATA | NA | ERP | Medium |  | 0 | 0 | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I007 | Interface | Budget To Report | PeopleSoft - Health Fees Allocation Refund of charges | Allocate Health Fees back to agency budgets and to federal grants. Peoplesoft has over-collected health fees (if they are grants, projects they need to be reallocated). It's cross agency-intra district. Its just a journal entry. This needs to be automated if possible in the new DIFS system. This is needed for DIFS for an inbound accounting data into Oracle GL | Phase 1 - Manual | ERP Cloud | Sprint 10 | Batch | Inbound | New | Create Journal Entries | OCTO | PeopleSoft | ERP | Medium |  | 0 | 0 | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I008 | Interface | Budget To Report | GSC - Leave Allocation | Allocation of Employee Leave. Leave Allocation of Financial Management GSC. This is needed for DIFS for an inbound accounting data into Oracle GL. This is agency specific and belongs to cluster GSC. | Phase 1 - Manual | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Journal Entries | GSC | NA | ERP | Medium |  | 0 | 0 | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I009 | Interface | Order To Cash | iNOVAH - Cash Collection | Receive cash collection data from all agencies into iNOVAH which sends this data everyday to SOAR. They send two files, the first file which comes at 7pm everyday. The second file comes after 15 minutes of the first file and has any missing transactions. Both files/interfaces have the same data format and data. This data needs to come to DIFS going forward. Merged the two files as one interface | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | Y | Create Journal Entries | OCFO/OFT | iNOVAH | ERP | Medium |  | Andrew Fedoris | Lalitha | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-19 | 2021-07-28 | 2021-07-28 | 2021-09-04 | 100% - Complete | 2021-08-26 | 2021-09-09 | 2021-09-08 | 2021-09-10 | 100% - Complete | 2021-12-02 | Approved | 2021-12-02 | 2021-09-13 | 2021-10-05 | 2021-09-16 | 2021-10-13 | 100% - Complete | 2021-10-19 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 100% - Complete |  | RICE 3 |  | 09/23/2021: Walk through scheduled with the District, 10/20/2021: R043 is dependent on I009 completing; As per Srini.C's ask, Andrew and Fayaz are going to have another meeting with the GL team since it might need config changes; Fayaz will schedule it on or after 11/30 since Rohan is OOO till 11/30 | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I010 | Interface | Order To Cash | OFT DMS/DBC - Debt Service Payment Postings | Crediting Cash and paying out expenditures Recorded as journal entries. Bookings for bonds, debt etc. Data Source DMS/DBC system from OFT. Potentially replaced by Kyriba Treasury. Need to confirm with JoseLuis if this will be replaced by Kyriba or the interface stays. | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | Y | Create Journal Entries | OCFO/OFT | DMS/DBC | ERP | Medium |  | Andrew Fedoris | Lalitha | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-11 | 2021-07-08 | 2021-07-28 | 2021-09-04 | 100% - Complete | 2021-08-25 | 2021-08-31 | 2021-09-08 | 2021-09-16 | 100% - Complete | 2021-11-23 | Approved | 2021-11-23 | 2021-09-01 | 2021-09-10 | 2021-09-16 | 2021-10-08 | 100% - Complete | 2021-09-13 | 2021-09-14 | 2021-10-14 | 2021-10-29 | 100% - Complete |  | RICE 3 |  | 09/23/2021: Walk through scheduled with the District | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I011 | Interface | Order To Cash | Banks - Bank Statements Reconciliation & ACH Return/Rejection File From Banks | Receive daily bai2 files for bank account reconciliation. It comes from banks. It will be multiple banks. This has been updated from Kyriba to Banks as process has changed. The files from banks will be consumed by both Kyriba and ERP. | Phase 1 | ERP Cloud | Sprint 10 | Batch | Inbound | N | Create Bank Statement Lines | OCFO | BANKS | ERP | High |  | Rajshekar Amme | Hima | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-02 | 2021-09-09 | 2021-09-16 | 2021-09-23 | 100% - Complete | 2022-09-23 | 2021-10-06 | 2021-09-30 | 2021-10-08 | 100% - Complete | 2022-01-06 | Approved | 2022-01-06 | 2021-10-25 | 2021-11-16 | 2022-11-15 | 2021-01-03 | 100% - Complete | 2021-12-24 | 2021-12-29 | 2022-01-03 | 2022-01-21 | 100% - Complete |  | RICE 3 |  | 01/20/2022: need screenshots for proof of testing - Andrew will complete and use the template 11/04/2021: Functional folks doing the configuration - scheduling the job to run to pick up the file - will test | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 190 | 40 | 150
I012 | Interface | Order To Cash | Kyriba - GL Posting Entries | Receive journal entry data for movement of cash between bank accounts of different agencies or payment made directly from Kyriba. | TBD | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Journal Entries | OCFO | KYRIBA | ERP | Medium |  | Rajshekar Amme | Lalitha | Deloitte Owned | Offtrack (Active) | Active | N/A | 3-Build | -184 | Approved | 2021-09-23 | 2021-09-29 | 2021-10-05 | 2021-11-29 | 100% - Complete | 2021-10-25 | 2021-10-29 | 2021-10-27 | 2021-12-17 | 100% - Complete | N/A | N/A | N/A | 2021-11-01 | 2021-11-10 | 2021-12-24 |  | 75% - In Review | 2021-11-29 | 2021-11-30 |  |  |  |  | RICE 3 |  | 02/10/2022: CR 759000 has been submitted to Descope per the team 02/03/2022: meeting scheduled 02/07/2022 and will get answer 01/27/2022: Some stuff going on beforew we can close - Andrew, Lyle, Eric met with Gina - confirming if it's automated - Lyle and Eric will follow up 01/20/2022: Potentially descoped Fayaz to buy drinks for Andrew 12/16/2021 - Raj and Lalitha working 12/02/2021 - Discuss with Rohan | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I013 - Descoped | Interface | Order To Cash | MITS - Tax Revenue Collection | Receive tax revenue collected by MITS and enter as journal entries (manual JV). This needs to be automated as currently it's entered manually in SOAR. | TBD | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Journal Entries | OCFO/OFT | MITS | ERP | Medium |  | Andrew Fedoris | Lalitha | Deloitte Owned | Offtrack (Active) | Active | N/A | 1-Functional Spec | -273 | Approved | 2021-05-07 | 2021-08-13 | 2021-05-12 |  | 75% - In Review | 2021-08-24 | 2021-09-06 | 2021-09-01 |  | 75% - In Review | N/A | N/A | N/A | 2021-10-29 | 2021-11-23 |  |  |  | 2021-12-17 | 2021-12-21 | [6 empty] | 11/16/2021: CR 748190 approved - descoping per PMO 11/04/2021: waiting for Eric to respond to an email as it sounds like these will be descoped - we need confirmation | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I014 | Interface | Order To Cash | Wells Fargo - Remote Deposit and Lockbox | Record the checks deposited using Wells Fargo Remote Deposit Application and Lockboxes. A notification be sent out to respective AR Personnel for the status of the deposits. | TBD | ERP Cloud |  | Batch | Inbound | Y | Create Receipts | Wells Fargo | NA | ERP | High |  | Rajshekar Amme | DEV 7 | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I015 | Interface | Order To Cash | Well Fargo - Record Interest Income | Record Interest income in an automated manner upon receipt and processing of Bank Statements. | TBD | ERP Cloud |  | Batch | Inbound | Y | Create Receipts | Wells Fargo | NA | ERP | Medium |  | Rajshekar Amme | DEV 7 | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I016- Descoped | Interface | Order To Cash | MITS - Real Property Tax Revenue & Lockbox Payments | Receive real property tax revenue and lockbox payments from MITS new real property system. Its manual right now but needs to be automated in DIFS. Legacy system is county fusion. | TBD | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Journal Entries | OCFO/OFT | MITS | ERP | Medium |  | Rajshekar Amme | Lalitha | Deloitte Owned | Offtrack (Active) | Active | N/A | 2-Technical Spec | -219 | Approved | 2021-05-20 | 2021-08-25 | 2021-05-17 |  | 100% - Complete | 2021-09-30 | 2021-10-06 | 2021-09-01 |  | 75% - In Review | N/A | N/A | N/A | 2021-10-29 | 2021-11-10 |  |  |  | 2021-11-29 | 2021-12-01 | [6 empty] | 11/16/2021: CR 748190 approved - descoping per PMO | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I017 | Interface | Budget | QuickBase - Performance Plans (KPI) | Performance Plan Data (KPI) from agencies goes into Oracle Planning. The data is from the QuickBase app. | Phase 2 | EPM Cloud |  | Batch | Inbound | Y | Create Performance Plans | Mayor/OCTO | QuickBase | Oracle Planning | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | 11/04/2021: waiting for Eric to respond to an email as it sounds like these will be descoped - we need confirmation | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I018 | Interface | Budget | PeopleSoft - Position Data | Position data from PeopleSoft to Oracle Planning. ALL Active and Inactive positions within the HCM system; includes both filled and vacant. | Phase 2 | EPM Cloud |  | Batch | Inbound | New | Sync Position Master Data | OCTO | PeopleSoft | Oracle Planning | High |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I019 | Interface | Budget | PeopleSoft - Employee Data | Employee Master Data from PeopleSoft to Oracle Planning | Phase 2 | EPM Cloud |  | Batch | Inbound | New | Sync Employee Master Data | OCTO | PeopleSoft | Oracle Planning | Medium |  |  |  | Deloitte Owned | Offtrack (Active) | Active | N/A | 0-Not Started | -197 | Approved | 2021-10-25 | 2021-10-28 |  |  |  | 2021-11-02 | 2021-11-09 |  |  |  | N/A | N/A | N/A | 2021-11-09 | 2021-11-19 |  |  |  | 2021-11-17 | 2021-11-19 | [7 empty] | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I020 | Interface | Budget | PeopleSoft - Salary Data | Salary Master Data from PeopleSoft to Oracle Planning | Phase 2 | EPM Cloud |  | Batch | Inbound | New | Sync Salary Master Data | OCTO | PeopleSoft | Oracle Planning | High |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I021 | Interface | Budget | Oracle Planning - Award Funding Update | Update award fund, funding amount and funding amount summary from Oracle Planning to Oracle PPM. Decision based on proms and grams replacement. Need to be validated for phase1 or phase2. Made this integration out of scope as awards will be created in ERP PPM now not EPM. Awards will be synched with EPM as part of I022 | TBD | EPM Cloud |  | Online | Outbound | New | Create Award Funding | OCFO | Oracle Planning | ERP | High |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | 09/30/2021: There is a request to combine I021 and I026, design will be redone and adding award funding to this object | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I022 | Interface | Budget | ERP - P&G Master & Award Data | Projects and Grants and Awards Master data from Oracle ERP PPM to Oracle Planning. Depends on proms and grams replacement if phase1 or phase2. As per discussion, awards will be created in ERP and along with P/G master data awards will also be synched to EPM as part of this integration | Phase 1 | EPM Cloud | Sprint 10 | Batch | Outbound | New | Sync P&G Master Data | OCFO | ERP | Oracle Planning | High |  | Ahamed Rauf | Divya Teja | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-08 | 2021-07-14 | 2021-07-06 | 2021-07-16 | 100% - Complete | 2021-07-15 | 2021-07-28 | 2021-07-06 | 2021-07-30 | 100% - Complete | 2021-08-17 | Approved | 2021-08-17 | 2021-07-30 | 2021-08-18 | 2021-08-02 | 2021-08-27 | 100% - Complete | 2021-08-19 | 2021-08-23 | 2021-08-30 | 2021-09-17 | 100% - Complete | No | RICE 2 |  | 09/09/2021: Everything is complete however there is an enhancement request | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I023 | Interface | Budget | ERP - Projects Actuals | Projects Actuals data from Oracle PPM to Oracle Planning. Oracle released a built adapter recently. Need to figure out if custom development is needed or not | Phase 1 | EPM Cloud | Sprint 10 | Batch | Outbound | New | Create Project Actuals | OCFO | ERP | EPM | High |  | Ahamed Rauf | Chitra S | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-28 | 2021-07-29 | 2021-07-28 | 2021-07-29 | 100% - Complete | 2021-08-03 | 2021-08-13 | 2021-08-03 | 2021-08-13 | 100% - Complete | 2021-08-25 | Approved | 2021-08-25 | 2021-08-13 | 2021-08-26 | 2021-08-13 | 2021-08-26 | 100% - Complete | 2021-08-30 | 2021-08-30 | 2021-08-28 | 2021-09-09 | 100% - Complete | No | RICE 2 |  | Load issue - ticket open with Oracle support | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I024 | Interface | Budget | ERP - Chart of Accounts | Chart of accounts segments data from ERP to Oracle Planning | Phase 1 | EPM Cloud | Sprint 09 | Batch | Outbound | New | Sync COA | OCFO | ERP | EPM | Low |  | Sushant Deshpande | Ahamed Rauf | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 3-Build | -280 | Approved | 2021-06-28 | 2021-07-08 | 2021-06-28 | 2021-07-08 | 100% - Complete | 2021-07-06 | 2021-07-30 | 2021-07-06 | 2021-07-30 | 100% - Complete | 2021-07-30 | Approved | 2020-12-19 | 2021-07-29 | 2021-08-06 | 2021-07-01 |  | 75% - In Review | 2021-08-09 | 2021-08-11 | 2021-07-26 |  | 75% - In Review |  | RICE 3 |  | 02/17/2022: ran into some issues getting ready for SIT1 - Divya Y will take a look 02/10/2022: making some additional changes Phase1 for Budget Execution 1004 Preconstruction and approved in Proconstruction out of box | Yes | 30 | 24 | 40 | 10 | 104 | 54 | 50 | 91.5 | 54 | 37.5 | 104 | 54 | 50
I025 | Interface | Budget | ERP - GL Actuals | GL actuals (excluding project and award) data from Oracle ERP GL to Oracle Planning. This is via in-built adapter | Phase 1 | EPM Cloud | Sprint 09 | Batch | Outbound | New | Send GL Actuals and Budget | OCFO | ERP | EPM | Low |  | Sushant Deshpande | Ahamed Rauf | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-28 | 2021-07-08 | 2021-06-28 | 2021-07-08 | 100% - Complete | 2021-07-06 | 2021-07-30 | 2021-07-06 | 2021-07-30 | 100% - Complete | 2021-07-30 | Approved | 2021-03-26 | 2021-07-01 | 2021-07-23 | 2021-07-01 | 2021-07-23 | 100% - Complete | 2021-07-26 | 2021-07-30 | 2021-07-26 | 2021-07-30 | 100% - Complete |  | RICE 3 |  | Phase1 for Budget Execution I005 Preconstruction and approved in Proconstruction out of box | Yes | 30 | 24 | 40 | 10 | 104 | 54 | 50 | 104 | 54 | 50 | 104 | 54 | 50
I026 | Interface | Budget | Oracle Planning - Project Budget Requests | Project Budget data from Oracle Planning to Oracle ERP PPM. This needs to go-live after budget is formulated in Oracle Planning. This interface will also be used for reprogramming and modifications. Oracle released recently a built-in adapter for this. Need to check if adapter or custom. | Phase 1 | EPM Cloud | Sprint 10 | Batch | Outbound | New | Create Project Budget | OCFO | EPM | ERP | High |  | Ahamed Rauf | Chitra S | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-02 | 2021-08-06 | 2021-08-02 | 2021-08-06 | 100% - Complete | 2021-09-01 | 2021-09-17 | 2021-09-01 | 2021-11-26 | 100% - Complete | 2022-12-10 | Approved | 2022-01-12 | 2021-09-14 | 2021-10-04 | 2021-09-17 | 2021-10-15 | 100% - Complete | 2021-10-05 | 2021-10-08 | 2021-10-21 | 2021-10-29 | 100% - Complete | No | RICE 3 |  | 11/12/2021 - Ahmed will provide sample file on 11/12 on Dev7. Testing is still 75% as the new file format need to be validated and tested 12/02/2021: File format keeps changing - requires rework | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I027 | Interface | Budget | Oracle Planning - Approved GL Budget | Approved GL budget from Oracle Planning to Oracle ERP GL. This is via in-built adapter. This needs to go-live after budget is formulated in Oracle Planning. This interface will also be used for reprogramming and modifications. | Phase 1 | EPM Cloud | Sprint 09 | Batch | Outbound | New | Send GL Actuals and Budget | OCFO | EPM | ERP | Low |  | Sushant Deshpande | Ahamed Rauf | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-18 | 2021-10-22 | 2021-10-18 | 2021-10-22 | 100% - Complete | 2021-10-18 | 2021-10-21 | 2021-10-18 | 2021-10-21 | 100% - Complete | 2021-10-21 | Approved | 2021-10-21 | 2021-10-22 | 2021-10-28 | 2021-09-17 | 2021-11-12 | 100% - Complete | 2021-10-29 | 2021-10-30 | 2021-09-17 | 2021-11-12 | 100% - Complete |  | RICE 3 |  | 11/04/2021 - New Oracle ticket on ERP environment. Missing table during migration - SR open for the table issue - Rohan is following up 11/11/2021 - Ticket resolved 11/18/2021 - Demonstrated in B2R - do we Sprint in 2022 - Anju and Sushant working on approval Approved during pre-construction | Yes | 30 | 24 | 40 | 10 | 104 | 54 | 50 | 104 | 54 | 50 | 104 | 54 | 50
I028 | Interface | Budget | CARSS - Requested Budget | Requested budget for all capital projects from Oracle Planning to CARSS. Currently this data goes from PROMS to CARSS. Once proms and grams decision is made need to be validated if phase1 or phase2 | Phase 3 | EPM Cloud |  | Batch | Outbound | Y | Send Budget Data | OCFO | Oracle Planning | CARSS | Medium |  | Brian O'Donnell | Lalitha | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Moved to Phase 1 as PROMS/GRAMS is being replaced. | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I029 | Interface | Budget | QuickBase - Budget | Budget from QuickBase DCPS to Oracle Planning. Sushant to confirm if phase1 or phase2. | Phase 2 | EPM Cloud |  | Batch | Inbound | Y | Create Budget Data | DCPS | QuickBase | Oracle Planning | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I030 | Interface | Projects and Grants | Peoplesoft - Payroll Costs | Payroll costs (payroll, deductions, expenses) should go into PPM from PeopleSoft | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | New | Accumulate Labor Costs | OCTO | PeopleSoft | ERP | Medium |  | Jessica Rubin | Divya Teja | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-06 | 2021-05-12 | 2021-05-17 | 2021-05-21 | 100% - Complete | 2021-06-02 | 2021-06-09 | 2021-05-20 | 2021-06-01 | 100% - Complete | 2021-06-24 | Approved | 2021-06-24 | 2021-07-13 | 2021-07-23 | 2021-06-04 | 2021-06-25 | 100% - Complete | 2021-07-22 | 2021-07-26 | 2021-06-28 | 2021-07-09 | 100% - Complete |  | RICE 1 | Sprinted | Start in parallel with I001 - will start follow up with Rohan 05/18/2021 Looks like Jessica named Func owner 05/26/2021 note from Jessica: The functional specs are mainly done, just need to update the mapping information. We have a meeting today at 5:30pm EST to review the tech design – after this meeting, I can give you an official update on the status. Please let me now if you have any questions. | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I031 | Interface | Projects and Grants | PeopleSoft - Employee Data | Employee Master Data from PeopleSoft to ERP PPM along with Employee expenditures. | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | New | Sync Employee Master Data | OCTO | PeopleSoft | ERP | Medium |  | Jagannathan Viswanathan | Divya Teja | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-12 | 2021-04-15 | 2021-04-12 | 2021-04-20 | 100% - Complete | 2021-04-26 | 2021-05-03 | 2021-04-20 | 2021-05-06 | 100% - Complete | 2021-05-18 | Approved | 2021-05-18 | 2021-05-20 | 2021-06-02 | 2021-05-03 | 2021-05-14 | 100% - Complete | 2021-06-17 | 2021-06-21 | 2021-05-14 | 2021-05-21 | 100% - Complete |  | RICE 1 | Sprinted | 05/05/21 - I think we should wrap up the functional aspect of the FS doc by the earliest this Friday. | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I032 | Interface | Projects and Grants | EGMS - Events Revenue & Billing | EGMS (OSSE) – Electronic Grants Management System expenditures. The reimbursable portion needs to be billed and revenue be generated. | TBD | ERP Cloud |  | Batch | Inbound | Y | Accumulate Labor Costs | OSSE | EGMS | ERP | Medium |  | Tej Mehta | DEV 6 | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I033 | Interface | Acquire To Retire | CARSS - Assets Extract | Takes data from all these systems and formulates budget plan for asset. DIFS needs to feed asset data to CARSS. | Phase 1 | ERP Cloud | Sprint 8.5 | Batch | Outbound | Y | Send Asset Data | OCFO | ERP | CARSS | Medium |  | Simon Lu | Divya Teja | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-31 | 2021-09-03 | 2021-09-09 | 2021-09-23 | 100% - Complete | 2021-09-27 | 2021-10-01 | 2021-09-28 | 2021-10-01 | 100% - Complete | 2021-11-18 | Approved | 2021-11-18 | 2021-10-04 | 2021-10-13 | 2021-10-04 | 2021-10-22 | 100% - Complete | 2021-10-14 | 2021-10-15 | 2021-10-21 | 2021-10-29 | 100% - Complete |  | RICE 3 |  | 09/23/2021: Walk through scheduled | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I034 | Interface | Procure To Pay | OSSE OECD - Day Care Grant Vendor Payment | Grant vendor voucher data from OSSE OECD system. The data is not in DAFRIN format. SOAR converts the incoming data into DAFRIN before loading into the system. | Phase 1 | ERP Cloud | Sprint 8.5 | Batch | Inbound | Y | Create Invoice | OSSE | OECD | ERP | Medium |  | Pandu Sadam | Khalid Khan | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-20 | 2021-08-12 | 2021-08-12 | 2021-09-02 | 100% - Complete | 2021-09-09 | 2021-09-16 | 2021-09-02 | 2021-09-10 | 100% - Complete | 2021-10-18 | Approved | 2021-10-18 | 2021-09-15 | 2021-09-30 | 2021-09-14 | 2021-10-01 | 100% - Complete | 2021-09-30 | 2021-10-01 | 2021-10-04 | 2021-10-29 | 100% - Complete |  | RICE 2 |  |  | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I035 | Interface | Procure To Pay | MMIS - Medicaid Vendor Payment | Medicaid payables daily data from DHCF. Medicaid Payments including for alliance vendor. It's not in DAFRIN but gets converted in soar. The data which comes is not in one record. It's in 3 lines. Three records constitute one transaction. Merged the alliance vendor file with this one as same file format. Two files are being sent by MMIS. One for all vendors and one for alliance. They also send one time vendors and these need to be created in DIFS as well along with create invoice. | Phase 1 | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Invoice | DHCF | MMIS | ERP | High |  | Muralidhar Pedasanaganti | Khalid Khan | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-19 | 2021-08-25 | 2021-08-05 | 2021-09-10 | 100% - Complete | 2021-08-26 | 2021-09-09 | 2021-09-09 | 2022-01-14 | 100% - Complete | 2022-02-17 | Approved | 2022-02-17 | 2021-09-20 | 2021-10-25 | 2021-09-20 | 2022-01-28 | 100% - Complete | 2021-10-26 | 2022-02-14 | 2022-01-27 | 2022-02-18 | 100% - Complete |  | RICE 3 |  | 02/15/2022: going to District for approval 02/08/2022: Call scheduled to confirm with 02/08/2022: Call scheduled to confirm with MMIS and Meg 02/03/2022: Build and Test for 95% of the scenarios good - last 5% next week 02/01/2022: Review scheduled Wednesday 02/02/2022 01/25/2022: Review scheduled next Wednesday 01/19/2022: Meeting today - will use Deck from Meeting to move foward 01/13/2022: Coordinating the Review next week 12/07/2021 - Meeting with PDMS on 12/08 to get clarification - once the meeting is over Murali will have a better idea on what direction to move forward 12/02/2021 - Meeting with MMIS next week | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I036 | Interface | Procure To Pay | MMIS - Medicaid Vendor Payment Response | Payment status response back to MMIS. This is currently no there in SOAR but will be implemented going forward. | Phase 1 | ERP Cloud | Sprint 10 | Batch | Outbound | Y | Send Payment Status | OCFO | ERP | MMIS | Medium |  | Muralidhar Pedasanaganti | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-30 | 2021-09-03 | 2021-09-06 | 2021-09-10 | 100% - Complete | 2021-10-18 | 2021-10-22 | 2021-09-08 | 2022-01-14 | 100% - Complete | 2022-02-17 | Approved | 2022-02-17 | 2021-09-29 | 2021-10-08 | 2021-09-29 | 2022-01-28 | 100% - Complete | 2021-11-02 | 2021-11-08 | 2022-01-27 | 2022-02-11 | 100% - Complete |  | RICE 3 |  | 02/08/2022: Call scheduled to confirm with MMIS and Meg 02/03/2022: Build and Test for 95% of the scenarios good - last 5% next week 02/01/2022: Review scheduled Wednesday 02/02/2022 01/19/2022: Meeting today - will use Deck from Meeting to move foward 01/13/2022: Coordinating the Review next week 12/07/2021 - Meeting with PDMS on 12/08 to get clarification - once the meeting is over Murali will have a better idea on what direction to move forward | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I037 | Interface | Procure To Pay | CFSA Faces - Child Care Provider Payment | Child care provider payment data from CFSA. Payment status files go back to CFSA for updates. They also send one time vendors and these need to be created in DIFS as well along with create invoice. | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | Y | Create Invoice | CFSA | Faces | ERP | High |  | Sravana Atmakuru | Khalid Khan | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-09 | 2021-09-15 | 2021-10-04 | 2021-10-15 | 100% - Complete | 2021-10-29 | 2021-11-12 | 2021-11-06 | 2021-12-10 | 100% - Complete | 2022-01-28 | Approved | 2022-01-28 | 2021-11-15 | 2021-12-08 | 2021-12-15 | 2021-12-27 | 100% - Complete | 2021-11-01 | 2021-11-03 | 2022-01-05 | 2022-01-17 | 100% - Complete |  | RICE 3 |  | 12/14/2021: One open item to work through 12/07/2021: CFSA - hadmeeting with the team - Prasad will meet with Sravana to discuss. Sravana has updated the inbound with the supplier info but the outbound info is depended on information from CFSA team | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I038 | Interface | Procure To Pay | CFSA Faces - Child Care Provider Payment Response | Payment status response back to CFSA | Phase 1 | ERP Cloud | Sprint 09 | Batch | Outbound | Y | Send Payment Status | CFSA | ERP | Faces | Medium |  | Sravana Atmakuru | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-16 | 2021-09-22 | 2021-10-05 | 2021-12-30 | 100% - Complete | 2021-11-26 | 2021-12-02 | 2021-10-13 | 2022-01-06 | 100% - Complete | 2022-01-28 | Approved | 2022-01-28 | 2021-10-18 | 2021-10-27 | 2021-10-28 | 2022-01-28 | 100% - Complete | 2021-10-27 | 2021-10-29 | 2022-01-18 | 2022-01-21 | 100% - Complete |  | RICE 3 |  | 01/19/2022: Spec reviewd 01/14/2022 12/21/2021: Outbound - need confirmation from CFSA - Fayaz has sent an email 12/14/2021: Waiting on response from CFSA FACES 12/07/2021: CFSA - hadmeeting with the team - Prasad will meet with Sravana to discuss. Sravana has updated the inbound with the supplier info but the outbound info is depended on information from CFSA team | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I039 | Interface | Procure To Pay | DDS RSA - Grant Vendor Payment | Grant vendor payment request data from Department of Disability Services. It is managed by their Vendor Libera and system is RSA | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | Y | Create Invoice | DDS | RSA | ERP | Medium |  | Pandu Sadam | Nirmala | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-23 | 2021-09-28 | 2021-08-27 | 2021-09-10 | 100% - Complete | 2021-10-13 | 2021-10-21 | 2021-09-14 | 2021-09-17 | 100% - Complete | 2022-01-11 | Approved | 2022-01-11 | 2021-10-21 | 2021-11-02 | 2021-09-17 | 2021-10-22 | 100% - Complete | 2021-10-21 | 2021-10-25 | 2021-10-21 | 2022-01-10 | 100% - Complete |  | RICE 3 |  | 12/21/2021: Open comments on the spec - Fayaz has emailed Keenan Waiting for spec approval to mark it as 100% complete | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I040 | Interface | Procure To Pay | DDS RSA - Grant Vendor Payment Response | Payment status response back to DDS RSA | Phase 1 | ERP Cloud | Sprint 09 | Batch | Outbound | Y | Send Payment Status | DDS | ERP | RSA | Medium |  | Pandu Sadam | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-28 | 2021-10-04 | 2021-09-28 | 2021-09-30 | 100% - Complete | 2021-11-02 | 2021-11-09 | 2021-09-24 | 2021-09-27 | 100% - Complete | 2021-12-10 | Approved | 2021-12-10 | 2021-11-09 | 2021-11-19 | 2021-09-29 | 2021-10-06 | 100% - Complete | 2021-10-12 | 2021-11-24 | 2021-10-12 | 2021-12-06 | 100% - Complete |  | RICE 3 |  |  | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I041 | Interface | Procure To Pay | DMV Destiny- Refund of Traffic Fines | Receive traffic fines refund data and issue payments to DC residents | Phase 1 | ERP Cloud | Sprint 08 | Batch | Inbound | Y | Create Invoice | DMV | Destiny | ERP | Medium |  | Sravana Atmakuru | Himabindu Veganur | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-15 | 2021-11-22 | 2021-09-09 | 2021-09-22 | 100% - Complete | 2021-12-14 | 2021-12-22 | 2021-09-22 | 2021-09-24 | 100% - Complete | 2022-01-05 | Approved | 2022-01-05 | 2021-09-27 | 2021-10-18 | 2021-09-27 | 2021-11-29 | 100% - Complete | 2021-10-28 | 2021-10-29 | 2021-10-12 | 2021-12-01 | 100% - Complete |  | RICE 3 |  | Waiting for spec approval to mark it as 100% complete | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I042 | Interface | Procure To Pay | DMV Destiny- Refund of Traffic Fines Response | Payment status back to DMV from DIFS for the traffic fines refund payments. | Phase 1 | ERP Cloud | Sprint 08 | Batch | Outbound | Y | Send Payment Status | DMV | ERP | Destiny | Medium |  | Sravana Atmakuru | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-22 | 2021-11-26 | 2021-09-09 | 2021-09-24 | 100% - Complete | 2021-12-09 | 2021-12-16 | 2021-09-27 | 2021-09-29 | 100% - Complete | 2021-12-31 | Approved | 2021-12-31 | 2021-09-29 | 2021-12-29 | 2021-09-29 | 2021-07-09 | 100% - Complete | 2021-10-12 | 2021-10-25 | 2021-10-12 | 2021-01-04 | 100% - Complete |  | RICE 3 |  |  | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I043 | Interface | Procure To Pay | OFT - Unclaimed Property | Unclaimed Property data from OFT's Third party vendor system by Kelmar. Payment requests to issue checks | Phase 1 | ERP Cloud | Sprint 08 | Batch | Inbound | Y | Create Invoice | OCFO/OFT | Kelmar | ERP | High |  | Sravana Atmakuru | Hima | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-06 | 2021-10-14 | 2021-09-08 | 2021-09-10 | 100% - Complete | 2021-11-19 | 2021-12-08 | 2021-09-13 | 2021-09-17 | 100% - Complete | 2021-10-29 | Approved | 2021-10-29 | 2021-12-09 | 2021-12-31 | 2021-09-16 | 2021-10-11 | 100% - Complete | 2021-10-12 | 2022-01-10 | 2021-10-18 | 2021-11-05 | 100% - Complete |  | RICE 4 |  |  | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I044 | Interface | Procure To Pay | OSSE ONEAPP - University Payments | Payment request data from OSSE for universities | Phase 1 | ERP Cloud | Sprint 08 | Batch | Inbound | Y | Create Invoice | OSSE | ONEAPP | ERP | Medium |  | Prasad Potturi | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-04 | 2021-06-11 | 2021-06-03 | 2021-06-15 | 100% - Complete | 2021-07-06 | 2021-07-14 | 2021-06-17 | 2021-06-23 | 100% - Complete | 2021-08-17 | Approved | 2021-08-17 | 2021-07-13 | 2021-07-22 | 2021-07-06 | 2021-07-15 | 100% - Complete | 2021-07-23 | 2021-07-27 | 2021-07-15 | 2021-07-19 | 100% - Complete |  | RICE 2 | Tested | Functional Owner Updated | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I045 | Interface | Procure To Pay | OSSE ONEAPP - University Payments Response | Payment status response to OSSE | Phase 1 | ERP Cloud | Sprint 08 | Batch | Outbound | Y | Send Payment Status | OSSE | ERP | ONEAPP | Medium |  | Sravana Atmakuru | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-11 | 2021-06-17 | 2021-06-11 | 2021-06-18 | 100% - Complete | 2021-07-26 | 2021-08-02 | 2021-06-18 | 2021-06-22 | 100% - Complete | 2021-09-03 | Approved | 2021-09-03 | 2021-08-02 | 2021-08-11 | 2021-06-25 | 2021-07-09 | 100% - Complete | 2021-08-12 | 2021-08-13 | 2021-07-09 | 2021-07-16 | 100% - Complete |  | RICE 1 | Tested | Functional Owner Updated | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I046 | Interface | Procure To Pay | OSSE NSCAPS - Nutrition Services Payment Request | Payment request data from OSSE for nutrition services | Phase 1 | ERP Cloud | Sprint 8.5 | Batch | Inbound | Y | Create Invoice | OSSE | NSACPS | ERP | Medium |  | Prasad Potturi | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-25 | 2021-05-28 | 2021-05-25 | 2021-05-28 | 100% - Complete | 2021-06-18 | 2021-06-25 | 2021-06-14 | 2021-06-18 | 100% - Complete | 2021-08-19 | Approved | 2021-08-19 | 2021-06-07 | 2021-06-17 | 2021-06-21 | 2021-07-06 | 100% - Complete | 2021-06-17 | 2021-06-18 | 2021-07-06 | 2021-07-15 | 100% - Complete |  | RICE 2 | Tested | Functional Owner Updated; 06/02: I updated I046 – OSSE NSCAPS Payment Request Functional Specification Status as “50% - In Progress” in the RICE Tracker. I have a meeting with OSSE NSCAPS team today afternoon and will complete the spec by Friday. | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I047 | Interface | Procure To Pay | OSSE NSCAPS - Nutrition Services Payment Response | Payment status response data from ERP to OSSE for nutrition services | Phase 1 | ERP Cloud | Sprint 8.5 | Batch | Outbound | Y | Send Payment Status | OSSE | ERP | NSACPS | Medium |  | Sravana Atmakuru | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-31 | 2021-06-04 | 2021-05-28 | 2021-06-08 | 100% - Complete | 2021-06-17 | 2021-06-24 | 2021-06-24 | 2021-06-24 | 100% - Complete | 2021-07-12 | Approved | 2021-07-12 | 2021-06-24 | 2021-07-06 | 2021-06-13 | 2021-07-09 | 100% - Complete | 2021-06-09 | 2021-06-10 | 2021-07-09 | 2021-07-16 | 100% - Complete |  | RICE 1 | Tested | Functional Owner Updated 06/24/2021: Review back from District with comments | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I048 | Interface | Procure To Pay | DOES - Employers Unemployment Contribution Refunds | Receive employer unemployment contribution refund data from DOES | Phase 1 | ERP Cloud | Sprint 8.5 | Batch | Inbound | Y | Create Invoice | DOES | DUTAS (District Unemployment Tax Accounting System) | ERP | Medium |  | Muralidhar Pedasanaganti | Nirmala | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-20 | 2021-04-27 | 2021-04-05 | 2021-05-10 | 100% - Complete | 2021-04-30 | 2021-05-07 | 2021-04-30 | 2021-05-10 | 100% - Complete | 2021-08-30 | Approved | 2021-08-30 | 2021-05-07 | 2021-05-19 | 2021-05-10 | 2021-05-28 | 100% - Complete | 2021-05-19 | 2021-05-20 | 2021-05-19 | 2021-06-04 | 100% - Complete |  | RICE 2 | Tested | 05/56/2021 By this weekend by 29th dev | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I049 | Interface | Procure To Pay | OSSE BITSEE- Special Education Not Encumbered Payment Requests | Payment Request for special education services from OSSE BITSEE system. | Phase 1 | ERP Cloud | Sprint 8.5 | Batch | Inbound | Y | Create Invoice | OSSE | BITSEE | ERP | Medium |  | Prasad Potturi | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-26 | 2021-04-30 | 2021-04-27 | 2021-05-09 | 100% - Complete | 2021-05-10 | 2021-05-14 | 2021-05-10 | 2021-05-14 | 100% - Complete | 2021-07-06 | Approved | 2021-07-06 | 2021-05-17 | 2021-05-27 | 2021-05-17 | 2021-06-20 | 100% - Complete | 2021-05-20 | 2021-05-31 | 2021-05-20 | 2021-06-20 | 100% - Complete |  | RICE 2 | Tested | 05/05/21: Can Fayaz ask Prasad to Prioritize: 05/26/2021: dev almost done unit test by end of week | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I050 | Interface | Procure To Pay | OSSE BITSEE- General and Special Education Payment Response | Payment status response for general and special education services back to OSSE BITSEE system. | Phase 1 | ERP Cloud | Sprint 8.5 | Batch | Outbound | Y | Send Payment Status | OSSE | ERP | BITSEE | Medium |  | Sravana Atmakuru | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-30 | 2021-05-07 | 2021-05-07 | 2021-06-07 | 100% - Complete | 2021-05-26 | 2021-06-03 | 2021-05-26 | 2021-06-04 | 100% - Complete | 2021-07-12 | Approved | 2021-07-12 | 2021-06-09 | 2021-06-18 | 2021-06-07 | 2021-07-09 | 100% - Complete | 2021-06-21 | 2021-06-23 | 2021-07-09 | 2021-07-16 | 100% - Complete |  | RICE 1 | Tested | 05/05/21: Can Fayaz ask Prasad to Prioritize 05/18/2021 Functional owner updated to Sravana 05/26/2021 did a technical review today & technical build holdup by funct | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I051 | Interface | Procure To Pay | OSSE EGMS -Payment Request | Intra district funds transfer and payment data (daycare, academy's and institutions) from EGMS OSSE. This may need to be split into two (funds transfer & payments) | Phase 1 | ERP Cloud | Sprint 08 | Batch | Inbound | Y | Create Invoice/Credit Memo and Create Journal Entries | OSSE | EGMS | ERP | High |  | Pandu Sadam | Nirmala | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-02 | 2021-08-06 | 2021-08-02 | 2021-08-06 | 100% - Complete | 2021-08-12 | 2021-08-25 | 2021-08-06 | 2021-08-19 | 100% - Complete | 2021-09-28 | Approved | 2021-09-28 | 2021-09-08 | 2021-10-25 | 2021-09-08 | 2021-10-27 | 100% - Complete | 2021-09-21 | 2021-09-23 | 2021-10-20 | 2021-10-27 | 100% - Complete |  | RICE 2 |  |  | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I052 | Interface | Procure To Pay | MITS - State Income Liability Offset (SITLP) | State Income Liability Offset. This data comes from MITS system (SITLP). This will record in O2C also as revenue collection. | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | Y | Create Invoice/Credit Memo and Create Journal Entries | OCFO/OFT | MITS | ERP | Very High |  | Andrew Fedoris | DEV 6 | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-10 | 2021-05-18 | 2021-05-10 | 2021-06-14 | 100% - Complete | 2021-05-18 | 2021-06-10 | 2021-06-15 | 2021-06-18 | 100% - Complete | 2021-07-27 | Approved | 2021-07-27 | 2021-06-15 | 2021-07-15 | 2021-06-21 | 2021-06-28 | 100% - Complete | 2021-07-29 | 2021-08-05 | 2021-06-29 | 2021-07-07 | 100% - Complete |  | RICE 2 | Tested | 07/08/2021: Shifting Offset Liability dates - CR 728636 | Yes | 50 | 120 | 160 | 50 | 380 | 170 | 210 | 380 | 170 | 210 | 380 | 170 | 210
I053 | Interface | Procure To Pay | MITS - DC Vendor Offset | DC Vendor Offset Data from MITS. After the offset, SOAR sends back 3 status files to MITS. After the offset ITS legacy system sends notices to the vendor. This will record in O2C as well. Offset receivable balance in AR and notice back to MITS to send it to vendor | Phase 1 | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Invoice/Credit Memo and Create Journal Entries | OCFO/OFT | MITS | ERP | High |  | Andrew Fedoris | Himabindu Veganur | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 4-Unit Test | -84 | In Review | 2021-11-01 | 2021-11-15 | 2021-11-16 | 2021-12-02 | 100% - Complete | 2021-11-01 | 2022-01-07 | 2021-12-06 | 2022-01-14 | 100% - Complete | 2022-02-18 | 1st Walkthrough Complete |  | 2021-11-10 | 2021-12-03 | 2021-12-23 | 2022-02-11 | 100% - Complete | 2021-12-06 | 2022-02-18 | 2022-02-09 |  | 75% - In Review |  | RICE 3 |  | 02/17/2022: Sprint what we have might look different going forward 02/15/2022: Walkthrough Scheduled 02/18/2022 02/10/2022: Sprint week of 02/21/2022 02/03/2022: Will there be changes based on the MITS feedback received - confusion on TOPS or DC VOS go first - the District can manually change TOPS - but it's rare. Walk through schedule next week 07/08/2021: Shifting Offset Liability dates - CR 728636 | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 262.5 | 120 | 142.5 | 270 | 120 | 150
I054 | Interface | Procure To Pay | MITS - DC Vendor Offset Response | Outbound response to MITS for DC Vendor Offset | Phase 1 | ERP Cloud | Sprint 10 | Batch | Outbound | Y | DC Vendor Liability Offset Response | MITS | ERP | MITS | High |  | Andrew Fedoris | Himabindu Veganur | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 4-Unit Test | -84 | In Review | 2021-11-15 | 2021-11-22 | 2021-11-16 | 2021-12-02 | 100% - Complete | 2021-12-06 | 2022-01-07 | 2021-12-06 | 2022-01-07 | 100% - Complete | 2022-02-18 | 2nd Walkthrough Complete |  | 2021-12-21 | 2022-01-13 | 2021-12-22 | 2022-02-14 | 100% - Complete | 2022-01-14 | 2022-02-18 | 2022-02-09 |  | 75% - In Review |  | RICE 4 |  | 02/17/2022: Sprint what we have might look different going forward 02/15/2022: Walkthrough Scheduled 02/18/20220 2/10/2022: Sprint week of 02/21/2022 02/03/2022: - Schedule walk through next week 07/08/2021: Shifting Offset Liability dates - CR 728636 | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 262.5 | 120 | 142.5 | 270 | 120 | 150
I055 | Interface | Procure To Pay | TOP - State Federal Liability Offset | State Federal Liability Offset - MITS/TOP. This interface has many files going back and forth between MITS/TOP and ERP with multiple steps. Updated the direction to both as files have to go back to TOP as well. | Phase 1 | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Invoice/Credit Memo and Create Journal Entries | OCFO/OFT | MITS/TOP | ERP | Very High |  | Andrew Fedoris | Chitra S | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 4-Unit Test | -84 | In Review | 2021-10-05 | 2021-10-11 | 2021-10-05 | 2021-12-01 | 100% - Complete | 2021-10-21 | 2022-01-07 | 2021-10-22 | 2022-01-14 | 100% - Complete | 2022-02-18 | 3rd Walkthrough Complete |  | 2021-11-15 | 2021-12-13 | 2021-12-22 | 2022-02-11 | 100% - Complete | 2021-12-14 | 2022-02-18 | 2022-02-09 |  | 75% - In Review |  | RICE 3 |  | 02/17/2022: Sprint what we have might look different going forward 02/15/2022: Walkthrough Scheduled 02/18/2022 02/10/2022: Sprint week of 02/21/2022 02/03/2022: - Schedule walk through next week 11/04/2021: Andrew updating func spec | Yes | 50 | 120 | 160 | 50 | 380 | 170 | 210 | 367.5 | 170 | 197.5 | 380 | 170 | 210
I056 | Interface | Procure To Pay | TOP - State Federal Liability Offset Response | State Federal Liability Offset - MITS/TOP response to MITS from ERP. This interface has many files going back and forth between MITS/TOP and ERP with multiple steps. Updated the direction to both as files have to go back to TOP as well. | Phase 1 | ERP Cloud | Sprint 10 | Batch | Outbound | N | TOP Liability Offset Response | MITS/TOP | ERP | MITS/TOP | High |  | Andrew Fedoris | Chitra S | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 4-Unit Test | -74 | In Review | 2021-10-12 | 2021-10-18 | 2021-10-12 | 2021-10-29 | 100% - Complete | 2021-12-14 | 2022-01-07 | 2021-10-22 | 2022-01-07 | 100% - Complete | 2022-02-18 | 4th Walkthrough Complete |  | 2021-12-31 | 2022-01-25 | 2021-12-22 | 2022-02-14 | 100% - Complete | 2022-01-26 | 2022-02-28 | 2022-02-09 |  | 75% - In Review |  | RICE 4 |  | 02/17/2022: Sprint what we have might look different going forward 02/15/2022: Walkthrough Scheduled 02/18/2022 02/10/2022: Sprint week of 02/21/2022 02/03/2022: - Schedule walk through next week 11/04/2021: Tech team has asked for more updates to Func Spec | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 262.5 | 120 | 142.5 | 270 | 120 | 150
I057 | Interface | Procure To Pay | Banks - ACH Payments | Send ACH payment data to Wells Fargo and Citibank | Phase 1 | ERP Cloud | Sprint 10 | Batch | Outbound | N | Create ACH Payment File | OCFO | ERP | KYRIBA | Medium |  | Muralidhar Pedasanaganti | Divya Teja | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-11 | 2021-10-19 | 2021-10-18 | 2021-10-22 | 100% - Complete | 2021-10-27 | 2021-11-10 | 2021-10-22 | 2021-12-30 | 100% - Complete | 2022-02-07 | Approved | 2022-02-07 | 2021-11-15 | 2021-12-06 | 2021-11-04 | 2022-01-28 | 100% - Complete | 2022-01-05 | 2022-01-07 | 2022-01-27 | 2022-02-04 | 100% - Complete |  | RICE 4 |  | 02/01/2022: Send feedback to District - asking for error handling on the out of the box functionality - how can the errors be identified - should show up on the log for process job - will it go into job error on dashboard - training issue 01/27/2022: Addressing comments 01/25/2022: Comments due from District tomorrow 01/19/2022: Ashish sent sample checks today and will confirm scenarios 12/14/2021 - Today we got response what will be handled by Kyriba - Fayaz to follow up and Keenan will pick up progress on ACH and Checkwrite with Murali out 12/07/2021 - Is this going to be descoped? Confirm what is in Kyriba Scope - confirm that along with wire transactions the ACH transactions will be going through Kyriba 01/27/2022: Addressing comments 01/25/2022: Comments due from District tomorrow 01/19/2022: Ashish sent sample checks today and will confirm scenarios 12/14/2021 - Today we got response what will be handled by Kyriba - Fayaz to follow up and Keenan will pick up progress on ACH and Checkwrite with Murali out 12/07/2021 - Is this going to be descoped? Confirm what is in Kyriba Scope - confirm that along with wire transactions the ACH transactions will be going through Kyriba | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I058 | Interface | Procure To Pay | Checkwrite - Warrant and Invoice file | Send Payments checks via the check write system | Phase 1 | ERP Cloud | Sprint 10 | Batch | Outbound | Y | Create Check Payment File | OCFO | ERP | KYRIBA | High |  | Muralidhar Pedasanaganti | Divya Teja | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 4-Unit Test | -84 | In Review | 2021-11-24 | 2021-12-01 | 2021-11-09 | 2021-12-21 | 100% - Complete | 2021-12-07 | 2021-12-20 | 2021-11-23 | 2022-01-28 | 100% - Complete | 2022-02-04 | 1st Walkthrough Complete |  | 2021-12-22 | 2022-01-14 | 2022-01-20 | 2022-02-17 | 100% - Complete | 2022-01-17 | 2022-02-18 | 2022-02-16 |  | 75% - In Review |  | RICE 4 |  | 02/17/2022: District review completed today 02/10/2022: Move to week of 02/21/2022 02/08/2022: new logic WIP 02/01/2022: Spec review scheduled Friday, 02/04/2022 - need new files from the bank 01/27/2022: Spec review scheduled next Friday 01/25/2022: Spec has been updated -spec review meeting next week @Fayaz? 12/07/2021 - The Spec has been updated with the mapping 11/18/2021: Schedule the review? Subrah has asked about rejection files - wants as much automation as possible - Kyriba meeting Monday | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 262.5 | 120 | 142.5 | 270 | 120 | 150
I059 - Remove from scope | Interface | Procure To Pay | IRS - 1099M Processing | Send 1099 yearly data. This is a report in Oracle. | TBD | ERP Cloud | Sprint 11 | Batch | Outbound | Y | Create Report - 1099 | IRS | ERP | IRS | Low |  | Pandu Sadam | Lalitha Gollapudi | Deloitte Owned | Offtrack (Active) | Active | N/A | 1-Functional Spec | -213 | Approved | 2021-10-06 | 2021-10-12 | 2021-10-06 |  | 75% - In Review | 2021-12-23 | 2021-12-29 |  |  |  | N/A | N/A | N/A | 2021-12-29 | 2022-01-13 |  |  |  | 2022-01-13 | 2022-01-14 | [6 empty] | 11/16/2021: Descoped per PMO meeting - CR 746434 Approved 10/21/21: CR submitted to descope the integration and use report to create the annual upload | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I060 | Interface | Procure To Pay | E-Risk - PSWCP Vendor Payments | Payment request data from PSWCP from E-Risk system | Phase 1 | ERP Cloud | Sprint 08 | Batch | Inbound | Y | Create Invoice | ORM | ERISK | ERP | Medium |  | Prasad Potturi | Nirmala | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-04 | 2021-08-12 | 2021-08-04 | 2021-08-12 | 100% - Complete | 2021-08-12 | 2021-10-05 | 2021-08-12 | 2021-09-03 | 100% - Complete | 2021-09-29 | Approved | 2021-09-29 | 2021-09-08 | 2021-10-25 | 2021-09-08 | 2021-11-11 | 100% - Complete | 2021-11-22 | 2021-12-02 | 2021-11-01 | 2021-11-29 | 100% - Complete |  | RICE 3 |  |  | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I061 | Interface | Procure To Pay | E-Risk - PSWCP Vendor Payment Response | Payment status response data from ERP to PSWCP E-Risk system | Phase 1 | ERP Cloud | Sprint 09 | Batch | Outbound | Y | Send Payment Status | ORM | ERP | ERISK | Medium |  | Prasad Potturi | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-07 | 2021-10-15 | 2021-08-12 | 2021-10-11 | 100% - Complete | 2021-08-13 | 2021-10-18 | 2021-08-13 | 2021-10-15 | 100% - Complete | 2021-12-10 | Approved | 2021-12-10 | 2021-10-18 | 2021-10-28 | 2021-10-25 | 2021-10-29 | 100% - Complete | 2021-11-18 | 2022-01-28 | 2021-11-02 | 2021-11-22 | 100% - Complete |  | RICE 3 |  |  | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I062 | Interface | Procure To Pay | PeopleSoft - Payroll Tax Deductions | Payroll tax deduction payment request data from PeopleSoft. These are payments to IRS, States etc. | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | New | Create Invoice | OCTO | PeopleSoft | ERP | Medium |  | Prasad Potturi | Nirmala | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-20 | 2021-06-02 | 2021-05-20 | 2021-06-01 | 100% - Complete | 2021-06-29 | 2021-07-06 | 2021-06-17 | 2021-06-24 | 100% - Complete | 2021-12-07 | Approved | 2021-12-07 | 2021-08-18 | 2021-08-27 | 2021-06-28 | 2021-07-12 | 100% - Complete | 2021-08-27 | 2021-08-31 | 2021-07-12 | 2021-07-16 | 100% - Complete |  | RICE 3 | Tested | Design discussions not happened. Co-ordinating with Fayaz to schedule. The delay is due to the prior items still in discussion. 05/26/2021 Jags will have completed by end of week | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I063 | Interface | Procure To Pay | ERP - Supplier Master | Supplier Master(Vendor Master) Feed from DIFS to PeopleSoft, ARIBA, PDMS and other interested agencies such as CFSA, OSSE to keep vendor data in-sync. These updates need to go to parties who send payment invoices | Phase 1 | ERP Cloud | Sprint 08 | Batch | Outbound | N | Sync Supplier Data | OCP | ERP | PSFT/ARIBA/PDMS | High |  | Prasad Potturi | Lalitha | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-26 | 2021-04-30 | 2021-05-21 | 2021-05-21 | 100% - Complete | 2021-05-31 | 2021-06-14 | 2021-06-15 | 2021-07-14 | 100% - Complete | 2021-09-28 | Approved | 2021-09-28 | 2021-06-30 | 2021-07-22 | 2021-07-14 | 2021-07-23 | 100% - Complete | 2021-07-29 | 2021-08-02 | 2021-07-26 | 2021-08-04 | 100% - Complete |  | RICE 2 |  | 07/08/2021: The team is very close to making the decision on the best way forwrad on the Tech Spec. Anil will try his best to incorporporate new rules, etc. and complete Tech Spec. | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I064 | Interface | Procure To Pay | PeopleSoft - Union Dues Refund | Over-collected union dues refunds to employees from PeopleSoft. | Phase 1 - Manual | ERP Cloud | Sprint 10 | Batch | Inbound | New | Create Invoice | OCTO | PeopleSoft | ERP | Medium |  | Pandu Sadam | Lalitha | Deloitte Owned | Offtrack (Active) | Active | N/A | 0-Not Started | -164 | Approved | 2021-11-23 | 2021-11-30 |  |  |  | 2021-12-14 | 2021-12-20 |  |  |  | N/A | N/A | N/A | 2021-12-07 | 2021-12-17 |  |  |  | 2021-12-17 | 2021-12-20 | [7 empty] | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I065 | Interface | Procure To Pay | Banks - PCard Allocation | The process in DIFS is changing. Bank will send a card transaction file daily and DIFS will create payment request and send it to the bank to issue checks. Moving forward with the assumption that we will use Expenses in Oracle and hence is required. | Phase 1 | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Expense Items | OCP/Banks | NA | ERP | Medium |  | Muralidhar Pedasanaganti | Divya Teja | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-11-30 | 2021-12-03 | 2021-11-18 | 2021-12-13 | 100% - Complete | 2021-12-03 | 2021-12-09 | 2021-12-13 | 2022-02-14 | 100% - Complete | 2022-02-14 | Specification Ready |  | 2021-12-10 | 2021-12-23 | 2022-12-20 | 2022-01-21 | 100% - Complete | 2021-12-23 | 2021-12-28 | 2022-02-25 | 2022-01-28 | 100% - Complete |  | RICE 3 |  | 02/10/2022: send contracts so that the team can talk to the bank 02/08/2022: Meet with bank and get Mastercard data 02/03/2022: Fayaz, Keenan, Murali, anyone that will be in meeting with the bank will sign the agreement 02/01/2022: Agreement is in hand who needs to sign it - Fayaz working with Lyle to meet with Bank 01/27/2022: Unit testing with files okay - SIT will do the actual testing with the bank - capture the screenshots 01/25/2022: Files are in, testing is WIP - looking to do some validation - no need to validate employees but need to validate errors where it's failing due to something else 02/01/2022: Agreement is in hand who needs to sign it - Fayaz working with Lyle to meet with Bank 01/19/2022: Escalating to get feedback from the bank 12/21/2021: Waiting on info from Rosalia 12/14/2021: Design is done - Divya will have the SPEC ready and Murali will move forward 09/230/2021: updated dates to be inline with IMS baseline - what should the dates be? | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I066 | Interface | Procure To Pay | ARIBA OnPrem - ERP Create and Update (chg/cancel) Requisitions On Prem | Create and Update (change/cancel) Requisitions in ERP from Ariba OnPrem. Merged Funds Check here as it is part of this interface. | Phase 1 | ERP Cloud | Sprint 11 | Online | Inbound | Y | Create and Update Requisitions | OCP | ARIBA-OnPrem | ERP | Very High |  | Prasad Potturi | Nirmala | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 4-Unit Test | -77 | In Review | 2021-11-29 | 2021-12-10 | 2021-11-29 | 2021-12-14 | 100% - Complete | 2021-11-29 | 2021-12-17 | 2021-06-01 | 2022-01-06 | 100% - Complete | 2022-02-17 | 2nd Walkthrough Complete |  | 2022-12-20 | 2022-01-15 | 2022-01-10 | 2022-02-07 | 100% - Complete | 2022-01-24 | 2022-02-25 | 2022-02-10 |  | 50% - In Progress |  | RICE 3 |  | 02/15/2022: Addressing comments and testing with OCTO 02/10/2022: Met with OCTO and have some feedback 02/03/2022: Start Testing on Tuesday - confirm the 3rd parties ready to test - Req number use REST or SOAP API - interface doesn't change b/t PASS 01/19/2022: Review Scheduled next week 12/21/2021: Phani will work on this when he returns from break 09/02/2021: Receipts were reviewed today - do we assume they are going to send us receipts. There is no integration from Pass to Soar - the issue is getting receipts from the legacy system. 10/14/2021: On Hold Getting Direction | Yes | 50 | 120 | 160 | 50 | 380 | 170 | 210 | 355 | 170 | 185 | 220 | 170 | 50
I067 | Interface | Procure To Pay | ARIBA Cloud - ERP Create and Update Requisitions | Create and Update Requisitions in ERP from Ariba Cloud. Merged Funds Check here as it is part of this interface. | TBD | ERP Cloud |  | Online | Inbound With ACK | New | Create and Update Requisitions | OCP | ARIBA-Cloud | ERP | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I068 | Interface | Procure To Pay | ARIBA OnPrem - ERP Create and Update Purchase Orders | Create and Update Purchase Orders in ERP from Ariba OnPrem. Merged Funds Check here as it is part of this interface. | Phase 1 | ERP Cloud | Sprint 11 | Online | Inbound | Y | Create and Update Purchase Orders (PO) | OCP | ARIBA-OnPrem | ERP | Very High |  | Sravana Atmakuru | Lalitha | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 3-Build | -84 | In Review | 2021-11-29 | 2021-12-10 | 2021-11-29 | 2021-12-01 | 100% - Complete | 2021-11-29 | 2021-12-17 | 2021-11-29 | 2022-01-28 | 100% - Complete | 2022-02-03 | 1st Walkthrough Complete |  | 2022-01-19 | 2022-02-18 | 2022-01-20 |  | 75% - In Review | 2022-02-07 | 2022-03-04 |  |  |  |  | RICE 4 |  | 02/15/2022: Looking for District response 02/10/2022: reviewed with District - waiting on feedback 02/03/2022: Walkthrough completed moving forward on build 02/01/2022: Internal review and review this week 01/25/2022: Hope to review next week 01/19/2022: will be reviewing their SPEC 12/21/2022: Haad meeting with PASS and got the required mapping 09/02/2021: Receipts were reviewed today - do we assume they are going to send us receipts. There is no integration from Pass to Soar - the issue is getting receipts from the legacy system | Yes | 50 | 120 | 160 | 50 | 380 | 170 | 210 | 290 | 170 | 120 | 380 | 170 | 210
I069 | Interface | Procure To Pay | ARIBA Cloud - ERP Create and Update Purchase Orders | Create and Update Purchase Orders in ERP from Ariba Cloud. Merged Funds Check here as it is part of this interface. | TBD | ERP Cloud |  | Online | Inbound With ACK | New | Create and Update Purchase Orders (PO) | OCP | ARIBA-Cloud | ERP | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I070 | Interface | Procure To Pay | ARIBA OnPrem - ERP Create and Update Suppliers | Create and Update Suppliers in ERP from Ariba OnPrem. | Phase 1 | ERP Cloud | Sprint 11.5 | Online | Inbound | Y | Create and Update Suppliers | OCP | ARIBA-OnPrem | ERP | High |  | Prasad Potturi | Lalitha Gollapudi | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 3-Build | -347 | Approved | 2021-04-02 | 2021-04-09 | 2021-04-02 | 2021-04-12 | 100% - Complete | 2021-04-12 | 2021-04-23 | 2021-04-12 | 2021-05-12 | 100% - Complete | 2021-06-30 | Approved | 2021-06-30 | 2021-05-10 | 2021-05-31 | 2021-05-12 |  | 75% - In Review | 2021-06-01 | 2021-06-03 | 2021-06-01 |  | 75% - In Review |  | RICE 1 | Tested | 02/15/2022: Starting either this week or next after review with OCP 05/05/21 - I have updated the RICE tracker and marked it as 75% complete, the only step pending is to review with District and we have planned for a demo this Friday. There are no roadblocks, we had some delay for delivering spec but there will not be any change in time for completing the Dev & Testing. 05/26/2021: Phani: By this weekend by 29th dev and unit testing 06/22/2021: update related to External Specifications section on IMS for this ID: No, don’t think they even started on this. I believe Scott is in the process of getting their dates 06/22/2021: updates related to Review Status: Prasad has promised me to give the updated the doc tomorrow(6/23). Once I will review it , will be send over to District for approval. 1/24/2022: With new DIFS-PASS direction there might be some changes to this integration. Once we review this with PASS team as per the dates this will be closed. Updated both build and unit testing status to 75% | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 232.5 | 120 | 112.5 | 270 | 120 | 150
I071 | Interface | Procure To Pay | ARIBA Cloud - ERP Create and Update Suppliers | Create and Update Suppliers in ERP from Ariba Cloud. | TBD | ERP Cloud |  | Online | Inbound | New | Create and Update Suppliers | OCP | ARIBA-Cloud | ERP | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I072 | Interface | Procure To Pay | ERP - ARIBA Cloud Create and Update Invoices | Create and Update Invoices in Ariba OnPrem from ERP. Added this as per new project direction and some functionality from ARIBA OnPrem is being brought over to ERP. Currently they don't do have an outbound interface with SOAR. | TBD | ERP Cloud |  | Online | Outbound | New | Sync Invoices | OCP | ERP | ARIBA-Cloud | High |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I073 | Interface | Procure To Pay | ERP - ARIBA OnPrem Procurement Payment Status | Update Payment Status back in ARIBA OnPrem. ARIBA OnPrem is getting payment status from CFO$OLVE. With new project direction we need this. Currently they don't do have an outbound interface with SOAR. | Phase 1 | ERP Cloud | Sprint 11.5 | Online | Inbound | Y | Sync Procurement Payment Status | OCP | ERP | ARIBA-OnPrem | High |  | Pandu Sadam | Sri Hari | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 3-Build | -84 | In Review | 2022-01-10 | 2022-01-21 | 2022-01-13 | 2022-01-26 | 100% - Complete | 2022-01-24 | 2022-02-04 | 2022-01-28 | 2022-02-11 | 100% - Complete | 2022-02-11 | Specification Ready |  | 2022-02-07 | 2022-02-18 | 2022-02-17 |  | 25% - In Progress | 2022-02-21 | 2022-03-04 |  |  |  |  | RICE 4 |  | 02/15/2022: Internal review today 02/10/2022: Pull the financial agency? 02/01/2022: not going to do API 09/30/2021: Requirements meeting next week | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 150 | 120 | 30 | 270 | 120 | 150
I074 | Interface | Procure To Pay | ERP - ARIBA Cloud Procurement Payment Status | Update Payment Status back in ARIBA Cloud. Added this as per new project direction and some functionality from ARIBA OnPrem is being brought over to ERP. Currently they don't do have an outbound interface with SOAR. | TBD | ERP Cloud |  | Online | Outbound | New | Sync Procurement Payment Status | OCP | ERP | ARIBA-Cloud | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I075 | Interface | Procure To Pay | ERP- Ariba OnPrem Sync COA Master Data | Send COA Segment data to Ariba OnPrem. Currently ARIBA pulls this data from SOAR tables on a daily basis. This data is sent as part of the request from ARIBA OnPrem to SOAR. | Phase 1 | ERP Cloud | Sprint 11.5 | Online | Outbound | Y | Sync COA | OCP | ERP | ARIBA-OnPrem | Medium |  | Trinh Trinh | Lalitha | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 2-Technical Spec | -123 | Not Submitted | 2021-12-06 | 2021-12-17 | 2022-02-01 | 2021-02-10 | 100% - Complete | 2021-12-20 | 2022-01-10 | 2022-02-14 |  | 50% - In Progress |  | N/A |  | 2022-01-17 | 2022-01-28 |  |  |  | 2022-01-31 | 2022-02-07 |  |  |  |  | RICE 4 |  | 02/15/2022: checking to see what priority as balancing the resources 02/10/2022: Rohan has given the spec draft to Fayaz and he is reviewing - might change Func resource Out of scope as new extension is being built for this. Making it in-scope as PASS team wants to move to new DIFS COA. OCP needs to confirm | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 50 | 50 | 0 | 150 | 70 | 80
I076 | Interface | Procure To Pay | ERP - Ariba Cloud Sync COA Master Data | Send COA Segment data to Ariba Cloud. This data is needed when ARIBA is creating Req's and PO's in DIFS. | TBD | ERP Cloud |  | Online | Outbound | New | Sync COA | OCP | ERP | ARIBA-Cloud | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I077 | Interface | Procure To Pay | ERP - ARIBA OnPrem Sync Projects & Grants Master Data | Projects and Grants master data from Oracle ERP PPM to ARIBA Cloud. Currently ARIBA pulls this data from SOAR tables on a daily basis. This data is sent as part of the request from ARIBA OnPrem to SOAR. | TBD | ERP Cloud |  | Online | Outbound | Y | Sync P&G Master Data | OCP | ERP | ARIBA-OnPrem | High |  | Prasad Potturi | Lalitha | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Out of scope as new extension is being built for this. Making it in-scope as PASS team wants to move to new DIFS COA. OCP needs to confirm | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I078 | Interface | Procure To Pay | ERP - ARIBA Cloud Sync Projects & Grants Master Data | Projects and Grants master data from Oracle ERP PPM to ARIBA Cloud. This is needed as there will be no PCA/Index in DIFS and this data should part of the request. | TBD | ERP Cloud |  | Online | Outbound | New | Sync P&G Master Data | OCP | ERP | ARIBA-Cloud | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved |  |  |  | 2021-06-25 | [6 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I079 | Interface | Budget To Report | UDC & Retirement Board - Payroll Reclass | Reclassifying UDC and retirement board payroll from expenditures to receivables. The receivables comes to ATO. | Phase 1 - Manual | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Journal Entries | UDC | NA | ERP | Medium |  | 0 | 0 | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I080 | Interface | Budget To Report | ERP - CFO$OLVE/DW Master Data | Updating this as per new direction for reporting. Mastter data from ERP to CFO$OLVE/DW for reporting purpose Decision needs to be made if this is still needed based on reports strategy. Will involve crosswalk as well before loading the data. Below is not applicable anymore Extract all Oracle ERP Cloud master data daily to CFO$OLVE for reporting. This is the full dump as per current functionality. This involves all crosswalk, transformation and lookup into the SOAR format which CFO$OLVE is expecting. This is a reporting interface. Updated the process area column as per Scott's request. Moved to Phase1 and in-scope as this data is needed CFO$OLVE | TBD | ERP Cloud | Sprint 10 | Batch | Outbound |  | Send ERP Master Data | OCFO | ERP | DW | Very High |  | Rohan Patel | DEV 8 | Deloitte Owned | Offtrack (Active) | Active | N/A | 0-Not Started | -192 | Approved | 2021-10-25 | 2021-11-02 |  |  |  | 2021-11-03 | 2021-11-26 |  |  |  | N/A | N/A | N/A | 2021-11-29 | 2021-12-28 |  |  |  | 2021-12-29 | 2022-01-06 |  |  |  |  | TBD |  | CR 754147 has been approved and now executed - I080 rolling into I081 12/16/2021: Reddy to Follow up with Amy 11/11/2021: On hold pending meetings with CFOSolve | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I081 | Interface | Budget To Report | ERP - CFO$OLVE/DW Transactional Data | Updating this as per new direction for reporting. Transactional data from ERP to CFO$OLVE/DW for reporting purpose Decision needs to be made if this is still needed based on reports strategy. Will involve crosswalk as well before loading the data. Below is not applicable anymore, Extract daily all incremental transactional data from ERP to CFO$OLVE for reporting. All transactions which have been posted, deleted and pending (suspense) in the ERL GL subledger. This is the incremental dump as per current functionality. This involves all crosswalk, transformation and lookup into the SOAR format which CFO$OLVE is expecting. Updated the process area column as per Scott's request. Moved to Phase1 and in-scope as this data is needed CFO$OLVE | Phase 1 | ERP Cloud | Sprint 11 | Batch | Outbound | Y | Send ERP Transactional Data | OCFO | ERP | DW | Very High |  | Rohan Patel | Divya Teja | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-10-14 | 2021-11-26 | 2021-10-18 | 2021-11-05 | 100% - Complete | 2021-11-29 | 2021-12-20 | 2021-10-18 | 2021-11-11 | 100% - Complete | 2022-01-11 | 2nd Submission Feedback Received |  | 2021-12-21 | 2022-01-21 | 2021-12-01 | 2021-12-15 | 100% - Complete | 2022-01-24 | 2022-02-18 | 2021-12-16 | 2022-02-11 | 100% - Complete |  | RICE 4 |  | 01/27/2022: Call today - District wants Deloitte to end more data to their Informatica server - will check with Anu - close next week? 11/04/2021: Reddy sending to Rohan | Yes | 50 | 120 | 160 | 50 | 380 | 170 | 210 | 380 | 170 | 210 | 380 | 170 | 210
I082 | Interface | Budget To Report | EPM - CFO$OLVE/DW Transactional & Master Data | Updating this as per new direction for reporting. Master & Transactional data from EPM to CFO$OLVE/DW. This is needed for reports and a decision has to be made if we still need this integration based on reporting strategy. Will involve crosswalk as well before loading the data. Moved to Phase1 and in-scope as this data is needed CFO$OLVE | Phase 1 | EPM Cloud | Sprint 11 | Batch | Outbound | Y | Send Oracle Planning Transactional Data | OCFO | ERP | DW | Very High |  | Sushant Deshpande | DEV6 | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | In Review | 2022-03-14 | 2022-03-22 | 2021-12-20 | 2022-02-11 | 100% - Complete | 2022-03-23 | 2022-04-13 | 2022-02-14 | 2022-02-15 | 100% - Complete | 2022-02-15 | Specification Ready |  | 2022-04-19 | 2022-05-19 |  |  |  | 2022-05-20 | 2022-05-30 |  |  |  |  | RICE 4 |  | 02/17/2022: Tej has some inputs - will be discussing with Rohan on the design and will connect with Bhaskar and Vijay 02/10/2022: Keeping in B2R - remove all tasks from Budget and EPM in the IMS and reassign to B2R 02/03/2022: File format finalized team double checking with Rohan if data can be provided from ERP 01/27/2022: Narayan and Randall owe some responses - moving from EPM to ERP - will update the Funct and Tech owners - is this going to be a report, an 10/14/2021: On hold pending meetings with CFOSolve | Yes | 50 | 120 | 160 | 50 | 380 | 170 | 210 | 170 | 170 | 0 | 298 | 170 | 128
I083 | Interface | Order To Cash | Kyriba - Transactions Cash Forecasting | Send all cash related transactions that can be used for cash forecasting, cash reconciliation and cash balances from ERP to Kyriba | TBD | ERP Cloud | Sprint 10 | Batch | Outbound | Y | Send Payments, Deposits, Cash Transfers & Journal Entries | OCFO | ERP | KYRIBA | Medium |  | Rajshekar Amme | Divya Teja | Deloitte Owned | Offtrack (Active) | Active | N/A | 2-Technical Spec | -196 | Approved | 2021-09-17 | 2021-09-23 | 2021-10-05 | 2021-10-18 | 100% - Complete | 2021-10-25 | 2021-10-29 |  |  |  | N/A | N/A | N/A | 2021-11-01 | 2021-11-12 |  |  |  | 2021-11-25 | 2021-11-29 |  |  |  |  | RICE 3 |  | 12/7/2021: CR is in progress to remove it from scope 09/30/2021: Oh hold some questions with Kyriba | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I084 | Interface | Budget To Report | DOES - Paid Family Leave (PFL) Benefit Program Accounting Entries | Paid Family leave (PFL) benefit program for all small business. Beneficiaries are paid directly by DOES. It is only recording GL accounting entries in DIFS/SOAR. New interface being developed with SOAR. This is as per details from Ashis after his meeting with DOES on 12/17 | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | Y | Create Journal Entries | DOES | PFLBAS (PFL-Benefit) | ERP | Medium |  | Trinh Trinh | Lalitha | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-26 | 2021-04-30 | 2021-04-27 | 2021-05-07 | 100% - Complete | 2021-05-06 | 2021-05-12 | 2021-05-06 | 2021-05-12 | 100% - Complete | 2021-06-04 | Approved | 2021-06-04 | 2021-05-13 | 2021-05-25 | 2021-05-14 | 2021-05-27 | 100% - Complete | 2021-09-03 | 2021-09-07 | 2021-05-20 | 2021-05-28 | 100% - Complete |  | RICE 2 | Tested | Walk thru with client on 05/14 4pm. 05/26/2021: By this weekend by 29th dev and unit testing | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I085 | Interface | Procure To Pay | DOES - Paid Family Leave (PFL) Benefit Program Employer Tax Refunds | Paid Family leave (PFL) benefit program for all small business. Refund payments to small businesses for any payments. New interface being developed with SOAR. More details from Ashis after his meeting with DOES on 12/17 | Phase 1 | ERP Cloud | Sprint 8.5 | Batch | Inbound | Y | Create Invoice | DOES | NEOSURANCE (PFL-TAX) | ERP | Medium |  | Muralidhar Pedasanaganti | Nirmala | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-08 | 2021-04-13 | 2021-04-01 | 2021-04-02 | 100% - Complete | 2021-04-13 | 2021-04-20 | 2021-04-13 | 2021-04-22 | 100% - Complete | 2021-08-30 | Approved | 2021-08-30 | 2021-04-20 | 2021-04-30 | 2021-04-26 | 2021-05-06 | 100% - Complete | 2021-04-30 | 2021-05-03 | 2021-05-06 | 2021-05-14 | 100% - Complete |  | RICE 2 | Tested | The design might change. If it changes need to update and retest | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I086 | Interface | Procure To Pay | PeopleSoft - Payroll Expenses (Vendor Payments) | Payroll expenses payment request data from PeopleSoft. These are payments for employee expenses (insurance and other expenses) to different providers. | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | New | Create Invoice | OCTO | PeopleSoft | ERP | High |  | Prasad Potturi | Nirmala | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-20 | 2021-06-01 | 2021-05-20 | 2021-06-01 | 100% - Complete | 2021-06-15 | 2021-06-28 | 2021-06-15 | 2021-06-23 | 100% - Complete | 2021-10-27 | Approved | 2021-10-27 | 2021-07-28 | 2021-08-17 | 2021-06-25 | 2021-07-09 | 100% - Complete | 2021-06-18 | 2021-06-22 | 2021-07-12 | 2021-07-16 | 100% - Complete |  | RICE 3 | Tested | 12/02/2021 - Meeting with MMIS next week | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I087 | Interface | Procure To Pay | ARIBA OnPrem - ERP Create and Update PO Receipts | Create and Update PO Receipts in ERP from Ariba OnPrem. On-Prem ARIBA to ERP will be only inbound as per current ARIBA-SOAR implementation. | Phase 1 | ERP Cloud | Sprint 11.5 | Online | Inbound | Y | Create and Update PO Receipts | OCP | ARIBA-OnPrem | ERP | Very High |  | Sravana Atmakuru | Sri | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-18 | 2021-06-24 | 2021-07-15 | 2021-08-02 | 100% - Complete | 2021-08-12 | 2021-10-27 | 2021-08-12 | 2021-11-22 | 100% - Complete | 2021-12-31 | Approved | 2021-12-31 | 2021-10-28 | 2021-11-18 | 2021-09-01 | 2021-09-24 | 100% - Complete | 2021-09-29 | 2022-02-14 | 2021-09-29 | 2022-02-07 | 100% - Complete |  | RICE 4 |  | 02/01/2022: Testing since morning - WIP 01/19/2022: In testing 11/11/2021: Not in Scope? On Hold | Yes | 50 | 120 | 160 | 50 | 380 | 170 | 210 | 380 | 170 | 210 | 380 | 170 | 210
I088 | Interface | Procure To Pay | ARIBA Cloud - ERP Create and Update PO Receipts | Create and Update PO Receipts in ERP from Ariba Cloud. | TBD | ERP Cloud |  | Online | Inbound With ACK | New | Create and Update PO Receipts | OCP | ARIBA-Cloud | ERP | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I089 | Interface | Procure To Pay | ERP - ARIBA Cloud Update PO Receipts | Update PO Receipts from ERP to Ariba Cloud. | TBD | ERP Cloud |  | Online | Outbound | New | Sync PO Receipts | OCP | ERP | ARIBA-Cloud | Very High |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I090 | Interface | Procure To Pay | E-Invoice Portal - Create and Update Invoices | Create and Update Invoices in ERP from E-Invoice Portal. This is needed in Phase2 as per new project direction and will not be needed in Phase3. During preconstruction validation it was decided it's not needed. | Phase 1 | ERP Cloud | Sprint 11 | Batch | Inbound | Y | Create and Update Invoice | OCP | E-Invoice-Portal | ERP | High |  | Pandu Sadam | Lalitha | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 4-Unit Test | -77 | In Review | 2021-12-20 | 2022-01-07 | 2021-12-20 | 2022-01-07 | 100% - Complete | 2022-01-10 | 2022-01-21 | 2022-01-06 | 2022-01-18 | 100% - Complete | 2022-02-07 | 1st Submission |  | 2022-01-24 | 2022-02-11 | 2022-01-19 | 2022-01-31 | 100% - Complete | 2022-02-14 | 2022-02-25 | 2022-01-27 |  | 75% - In Review |  |  |  | 02/15/2022: Move forward strategy confirmed - will move forward 02/03/2022: Testing continued and capture results 02/01/2022: Received update today and change should be tolerable 01/25/2022: Scheduled the first review next Tue | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 262.5 | 120 | 142.5 | 270 | 120 | 150
I091 | Interface | Projects and Grants | DDOT - FMIS Budget Reallocation | Moves budget from one project to another for grants from Federal Highway Trust Funds. DC pays 20% and Feds 80%. This is currently manual by entering data into SOAR. Excel and other documents are emailed to Alex. As per Dave the current manual interface from DDOT FMIS should be automated. Alex is the point of contact for this | Phase 2 | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Budget Adjustment | DDOT | FMIS | ERP | Medium |  | Tej Mehta | Himabindu Veganur | Deloitte Owned | Offtrack (Active) | Active | N/A | 0-Not Started | -171 | Approved | 2021-11-16 | 2021-11-23 |  |  |  | 2021-11-24 | 2021-12-01 |  |  |  | N/A | N/A | N/A | 2021-12-02 | 2021-12-14 |  |  |  | 2021-12-15 | 2021-12-16 |  |  |  |  | TBD |  | CR 753504 was approved - I091 is moving to Phase 2 - workaround will be used in Phase 1 11/11/2021: on hold - DOT FMIS Conversions CR coming | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I092 | Interface | Budget | Oracle Planning - Approved Project Requests | Approved project requests from Oracle Planning to Oracle ERP PPM. This is needed as part of the project creation process requirement. Depends on proms and grams replacement if phase1 or phase2. | Phase 1 | EPM Cloud | Sprint 10 | Batch | Inbound | New | Create Project Requests | OCFO | Oracle Planning | ERP | High |  | Ahamed Rauf | Hima | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-19 | 2021-07-23 | 2021-06-28 | 2021-07-08 | 100% - Complete | 2021-07-26 | 2021-08-06 | 2021-07-06 | 2021-08-06 | 100% - Complete | 2021-08-18 | Approved | 2021-08-18 | 2021-07-28 | 2021-08-18 | 2021-08-12 |  | 100% - Complete | 2021-08-19 | 2021-08-23 | 2021-08-30 | 2021-09-10 | 100% - Complete | No | RICE 2 |  |  | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I093 | Interface | Budget | Oracle Planning - New Capital Project Requests | New Capital project requests from Oracle Planning to CARSS. This is needed as part of the project creation process requirement. This data currently goes from PROMS to CARSS. Depends on proms and grams replacement if phase1 or phase2 | TBD | EPM Cloud |  | Batch | Outbound | Y | Sync New Capital Project Requests | OCFO | Oracle Planning | CARSS | Medium |  | Sushant Deshpande | Lalitha | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Moved to Phase 1 as PROMS/GRAMS is being replaced. 09/23/2021: Oracle SRs open - Decision Points are due by 10/04 | Removed from Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I094 | Interface | Budget | CARSS - Approved Capital Project Requests | Approved Capital project requests from CARSS to Oracle Planning. This is needed as part of the project creation process requirement. Depends on proms and grams replacement if phase1 or phase2. | Phase 2 | EPM Cloud | Sprint 10 | Batch | Inbound | Y | Sync Approved Capital Project Requests | OCFO | CARSS | Oracle Planning | Medium |  | Ahamed Rauf | Divya Teja | Deloitte Owned | Offtrack (Active) | Active | N/A | 1-Functional Spec | -203 | Approved | 2021-10-11 | 2021-10-22 | 2021-10-11 |  | 25% - In Progress | 2021-10-25 | 2021-10-29 |  |  |  | N/A | N/A | N/A | 2021-11-01 | 2021-11-12 |  |  |  | 2021-11-15 | 2021-11-16 |  |  |  |  | TBD |  | 10/20/2021 - Working on moving to Phase II | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I095 | Interface | Technical | Common Error Handling & Setup | Common Error Handling Framework and Build Framework needs to be built to log and send email notifications to O&M team and for deployment of code into different instances. Infrastructure for integrations needs to be setup before starting development. This includes instance creation, firewall setup, IP Whitelisting, Port opening, setup of SFTP server etc. This is needed for all environments. | Phase 1 | ERP Cloud | Sprint 09 | Online | Bidirectional | NA | NA | OCFO | NA | NA | High |  | N/A | Divya Teja | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-03-08 | 2021-03-19 | 2021-03-08 | 2021-03-19 | 100% - Complete | 2021-03-08 | 2021-03-19 | 2021-03-08 | 2021-03-19 | 100% - Complete | 2021-06-17 | Approved | 2021-06-17 | 2021-03-23 | 2021-04-02 | 2021-03-23 | 2021-04-02 | 100% - Complete | 2021-04-05 | 2021-04-09 | 2021-04-05 | 2021-04-09 | 100% - Complete |  | RICE 1 | Tested |  | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I096 | Interface | Technical | DIFS Transformation Hub and Crosswalk | For all agencies common between DIFS and SOAR, a transformation hub needs to be built on the Cloud Integration Platform which will pick up the batch files and split them into two files based on agency codes. One for DIFS needs to be placed on the DIFS SFTP server and one for SOAR needs to be placed on the SOAR FTPs server. | Phase 1 | ERP Cloud | N/A | Online | Bidirectional | NA | NA | OCFO | NA | NA | High |  | N/A | Lalitha Gollapudi | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-03-08 | 2021-03-19 | 2021-03-08 | 2021-03-19 | 100% - Complete | 2021-03-08 | 2021-03-19 | 2021-03-08 | 2021-03-19 | 100% - Complete | 2021-03-19 | Approved | 2021-02-01 | 2021-03-23 | 2021-04-02 | 2021-03-23 | 2021-04-02 | 100% - Complete | 2021-04-05 | 2021-04-09 | 2021-04-05 | 2021-04-09 | 100% - Complete |  | RICE 3 | Tested | I001 in Preconstruction | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 270 | 120 | 150 | 270 | 120 | 150
I098 | Interface | Acquire To Retire | FASTER - Assets | Faster system - Manages all fleet vehicles. Financial transactions need to be entered and managed in DIFS. Need to be confirmed If they need this during implementation phase. Jake is still confirming if we need this or not. | TBD | ERP Cloud |  | Batch | Outbound | Y | Send Asset Data | OCFO | ERP | FASTER | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I099 | Interface | Procure To Pay | BOE - Poll Workers Payment | Poll Workers Payment Request. Currently it’s a manual/semi-automated process | Phase 1 - Manual | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Invoice | Board of Elections | NA | ERP | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I106 | Interface | Budget To Report | ICS - Lottery Gaming | Taking summed up transaction data and inputting into ERP GL. The transactions are people buying lotteries, sports betting etc. | TBD | ERP Cloud |  | Batch | Inbound | Y | Create Journal Entries | DC0 | ICS | ERP | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I107 | Interface | Budget To Report | DOES - Payroll Data | DOES Payroll data. This will be recorded as journal entries in DIFS. This is a new SOAR interface currently in production | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | Y | Create Journal Entries | DOES | PeopleFirst Payroll System | ERP | Medium |  | Jessica Rubin | Lalitha | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-04-19 | 2021-04-23 | 2021-04-27 | 2021-05-07 | 100% - Complete | 2021-04-26 | 2021-04-30 | 2021-05-06 | 2021-05-13 | 100% - Complete | 2021-06-04 | Approved | 2021-06-04 | 2021-05-03 | 2021-05-12 | 2021-05-14 | 2021-05-27 | 100% - Complete | 2021-05-12 | 2021-05-14 | 2021-05-20 | 2021-05-28 | 100% - Complete |  | RICE 2 | Tested | 05/05/21 - I think we should wrap up the functional aspect of the FS doc by the earliest this Friday. Tech review started to go over functional on 05/07 meet with client 05/14 - 05/19/21 Additional discussion regarding batches | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I108 | Interface | Procure To Pay | DIFS - ERP/PASS - Invoice Outbound | Create and Update Invoices from ERP to ARIBA. This was during Preconstruction validation. Invoices will be created and updated in ERP which will sent to ARIBA. The interface from E-Invoice Portal to ERP is not needed as invoices will be created/updated in DIFS | TBD | ERP Cloud |  | Batch | Outbound | Y | Send Invoice | OCP | ERP | ARIBA-OnPrem | Very High |  | Pandu Sadam | Lalitha Gollapudi | Deloitte Owned | Offtrack (Active) | Complete | N/A | 5-Complete | -196 | Approved | 2021-07-13 | 2021-07-19 | 2021-07-21 | 2021-08-06 | 100% - Complete | 2021-08-16 | 2021-08-13 | 2021-08-06 | 2021-08-13 | 100% - Complete | N/A | N/A | N/A | 2021-08-16 | 2021-09-06 | 2021-08-16 | 2021-09-10 | 100% - Complete | 2021-10-27 | 2021-10-29 | 2021-09-06 | 2021-10-01 | 100% - Complete |  | RICE 2 |  | 09/30/2021: Update waiting on OCP more comments on Spec, Spec not approved | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I109 | Interface | Procure To Pay | ARIBA OnPrem - ERP Create and Update PO Receipts (Timesheets) | Create and Update PO timesheet Receipts in ERP from Ariba OnPrem. This was added as part of preconstruction validation. During the design phase need to look into if this can be merged with the PO receipts interface | TBD | ERP Cloud |  | Online | Inbound | Y | Create and Update PO Receipts | OCP | ARIBA-OnPrem | ERP | High |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Out of scope. Merging with ARIBA PO Receipts. | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I110 | Interface | Procure To Pay | OFT - Unclaimed Property Response | Unclaimed Property data response to OFT's Third party vendor system by Kelmar. Response to payment requests to issue checks. This is an existing interface and added during preconstruction validation | Phase 1 | ERP Cloud | Sprint 09 | Batch | Outbound | Y | Send Payment Status | OCFO | ERP | Kelmar | Medium |  | Sravana Atmakuru | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-14 | 2021-10-21 | 2021-09-09 | 2021-09-22 | 100% - Complete | 2021-12-15 | 2021-12-23 | 2021-09-22 | 2021-09-24 | 100% - Complete | 2022-01-11 | Approved | 2022-01-11 | 2021-12-23 | 2022-01-04 | 2021-09-29 | 2021-10-22 | 100% - Complete | 2021-10-12 | 2021-10-25 | 2021-10-12 | 2022-01-10 | 100% - Complete |  | RICE 3 |  |  | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I111 | Interface | Procure To Pay | MMIS PDMS - Create and Update Vendors | New Interface, In the future interface Medicaid provider information along with banking information directly from DHCF PDMS to DIFS. Medicaid providers (vendors) currently use DHCF PDMS system to create and update their info along with banking information. This is currently sent to PASS manually and then is interfaced to SOAR. In the future it needs to go directly from PDMS to DIFS. | Phase 1 | ERP Cloud | Sprint 11 | Online | Inbound | Y | Create and Update Suppliers | DHCF | PDMS | ERP | High |  | Prasad Potturi | Lalitha | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 3-Build | -150 | In Review | 2021-10-27 | 2021-11-02 | 2021-10-28 | 2021-11-30 | 100% - Complete | 2021-11-03 | 2021-11-18 | 2021-12-02 | 2022-01-14 | 100% - Complete | 2022-01-14 | Specification Ready |  | 2021-11-22 | 2021-12-14 | 2022-01-18 |  | 50% - In Progress | 2022-02-18 | 2022-02-25 |  |  |  |  | RICE 3 |  | 02/17/2022: Spec updated - Fayaz will send out to PDMS team - development starting next week 02/15/2022: Move forward strategy confirmed - will move forward 02/10/2022: Meeting today - there are some technical challenges but have common ground with the District to move forward/agreed on the design with Meg 02/03/2022: working on design - team to discuss - storing provider at site level 01/25/2022: Two PDMS meetings scheduled tomorrow 01/19/2022: Set up call then send specs and spreadsheet - adding attachment as well 12/21/2021: Call with Agency on 12/21/2021 - Provided Data Elements to the PDMS Team - Lalitha will start working on Jan 3 12/07/2021: Prasad and Lalitha meeting with PDMS on 12/08/2021 10/07/2021: 1035 is dependent on 1111 and &1112 | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 150 | 180 | 120 | 60 | 270 | 120 | 150
I112 | Interface | Procure To Pay | DIFS - PDMS Supplier Sync | New interface, vendor updates from DIFS to DHCF PDMS. Keeping most of the P2P as bi-directional. During implementation need to figure out if outbound is needed or just inbound if enough. PDMS is the source system where Medicaid providers are created/updated along with their banking information. | TBD | ERP Cloud |  | Online | Outbound | Y | Sync Supplier Data | DHCF | ERP | PDMS | Medium |  | Prasad Potturi | Nirmala | Deloitte Owned | Offtrack (Active) | Active | N/A | 0-Not Started | -172 | Approved | 2021-11-17 | 2021-11-22 |  |  |  | 2021-12-16 | 2021-12-23 |  |  |  | N/A | N/A | N/A | 2021-12-23 | 2021-01-06 |  |  |  | 2021-01-07 | 2021-01-10 |  |  |  |  | TBD |  | 10/07/2021: 1035 is dependent on 1111 and &1112 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I113 | Interface | Procure To Pay | DIFS - PASS OnPrem Sync Suppliers | Any changes to suppliers in DIFS need to be updated back PASS. | TBD | ERP Cloud |  | Online | Outbound | N | Sync Supplier Data | OCP | ERP | ARIBA-OnPrem | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I114 | Interface | Budget To Report | Department Of Corrections (DOC) - DIFS Journal Entries | Potential new interface with Department of Corrections (DOC). DOC has shown interest in integrating with DIFS. They currently manual enter their journal transactions. The approxinate load is 6-10 records. Making it this optional after discussing with the team. | TBD | ERP Cloud |  | Batch | Inbound | Y | Create Journal Entries | DOC | DOC | ERP Cloud | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I115 | Interface | Budget To Report | HSEMA - DIFS Journal Entries | Potential new interface with Homeland Security Emergency Agency (HSEMA). DIFS may potentially have to manage with HSEMA. HSEMA's central tracking system is currently siloed and is going to be integrated to DIFS per Mayor's recommendation. Making it optional after discussing it with the District team | TBD | ERP Cloud |  | Batch | Inbound | Y | Create Journal Entries | HSEMA | HSEMA | ERP Cloud | Medium |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I116 | Interface | Procure To Pay | TOPS Metering System - DIFS Refunds | Potential new interface with TOPS and the Parking Meter System. Both are revenue tracking systems currently being used by the District (a central tool for tracking the status of re-programmings). This integration is for refunds. Making it optional after discussing it with the District team | Phase 2 | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Invoice | DC Mayor | TOPS | ERP Cloud | High |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I117 | Interface | Procure To Pay | ERP - ARIBA OnPrem Create and Update Suppliers Outbound | Create and Update Suppliers in PASS from ERP. PASS suppliers can be created and updated in ERP and these need to be updated back in PASS OnPrem. | TBD | ERP Cloud |  | Online | Outbound | Y | Sync Supplier Data | OCP | ARIBA-OnPrem | ERP Cloud | High |  |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I118 | Interface | Budget | EPM - BFA Project Structure | Project structure along with implementing Agency, phases with Programs and Cost Centers, real project number and associated Awards with owning Agency and Fund information. Project Profile information for budget book reporting. Approved project information will be sent to BFA since BFA will be used for budgeting for FY23 and FY24 | TBD | EPM Cloud |  | Batch | Outbound | Y | Sync Project Structure | OCFO | EPM | BFA | Medium |  | Ahamed Rauf | Lalitha | Deloitte Owned | Offtrack (Active) | Active | N/A | 1-Functional Spec | -287 | Approved | 2021-07-26 | 2021-07-30 | 2021-07-22 |  | 50% - In Progress | 2021-08-02 | 2021-08-13 | 2021-07-22 |  |  | N/A | N/A | N/A | 2021-08-17 | 2021-09-08 |  |  |  | 2021-09-09 | 2021-09-13 | [6 empty] | 07/15/2021: The District Doesn't want this integration - they want to do this manually - Sushant and Reddy to discuss | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I119 | Interface | Budget To Report | DOES - GL Data | GL data from DOES will be recorded as journal entries into DIFS. This is a new inbound integration which is currently being developed adn tested between DOES and SOAR. They plan to go live in April 2021 | Phase 1 | ERP Cloud | Sprint 10 | Batch | Inbound | Y | Create Journal Entries | DOES | ESSP | ERP | Medium |  | Trinh Trinh | Lalitha | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-15 | 2021-10-29 | 2021-10-18 | 2021-12-16 | 100% - Complete | 2021-11-03 | 2021-11-10 | 2021-12-10 | 2021-12-16 | 100% - Complete | 2022-12-21 | Approved | 2022-01-12 | 2021-11-10 | 2021-11-23 | 2021-12-16 | 2021-12-28 | 100% - Complete | 2021-11-18 | 2021-11-23 | 2021-12-17 | 2022-01-10 | 100% - Complete |  | RICE 3 |  | [11/23/21] Working on functional spec | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I120 | Interface | Procure To Pay | DIFS - DOES Employer Unemployment Contribution Refund Payment Response | Payment response from DIFS to DOES for Employer Unemployment contribution refund payment response. This is an existing integration with SOAR in production | Phase 1 | ERP Cloud | Sprint 8.5 | Batch | Outbound | Y | Payment Response | DOES | ERP | DUTAS | Medium |  | Muralidhar Pedasanaganti | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-30 | 2021-08-12 | 2021-07-30 | 2021-08-04 | 100% - Complete | 2021-08-23 | 2021-08-24 | 2021-08-04 | 2021-08-06 | 100% - Complete | 2021-08-31 | Approved | 2021-08-31 | 2021-08-09 | 2021-08-18 | 2021-08-09 | 2021-08-25 | 100% - Complete | 2021-08-18 | 2021-08-20 | 2021-08-26 | 2021-09-17 | 100% - Complete | NA | RICE 2 |  |  | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I121 | Interface | Procure To Pay | DIFS - EGMS Payment Response | Payment response from DIFS to OSSE EGMS for payment requests (daycare, academy's and institutions). This is an existing integration with SOAR in production | Phase 1 | ERP Cloud | Sprint 8.5 | Batch | Outbound | Y | Payment Response | OSSE | ERP | EGMS | Medium |  | Pandu Sadam | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-12 | 2021-08-18 | 2021-09-01 | 2021-09-21 | 100% - Complete | 2021-08-30 | 2021-09-03 | 2021-09-21 | 2021-09-27 | 100% - Complete | 2021-12-10 | Approved | 2021-12-10 | 2021-09-06 | 2021-09-15 | 2021-09-29 | 2021-10-06 | 100% - Complete | 2021-09-15 | 2021-09-17 | 2021-10-12 | 2021-10-22 | 100% - Complete |  | RICE 3 |  | 09/16/2021: will schedule District review call | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
I122 | Interface | Procure To Pay | DIFS - DOES PFL Small Business Tax Refunds Payment Response | Payment response from DIFS to DOES for PFL small Business tax refunds payment response. This is currently being developed with SOAR and not yet in production. | Phase 1 | ERP Cloud | Sprint 8.5 | Batch | Outbound | Y | Payment Response | DOES | ERP | PFLBAS | Medium |  | Muralidhar Pedasanaganti | Sri Hari | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-05 | 2021-10-13 | 2021-07-30 | 2021-08-04 | 100% - Complete | 2021-10-13 | 2021-10-28 | 2021-08-04 | 2021-08-06 | 100% - Complete | 2021-08-31 | Approved | 2021-08-31 | 2021-10-29 | 2021-11-23 | 2021-08-09 | 2021-08-25 | 100% - Complete | 2021-11-23 | 2021-11-29 | 2021-08-26 | 2021-09-17 | 100% - Complete | NA | RICE 3 |  |  | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 80 | 150 | 70 | 80 | 150 | 70 | 80
R001 | Report | Acquire To Retire | Asset Impairment Questionnaire | Asset Impairment Questionnaire | TBD | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Could Have | Chilakamarri, Srinivas | Krishna Aravapalli | District Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | 10/04/2021: Per A2R team, this report is no longer is required in DIFS. A CR will be submitted to descope this |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R002 | Report | Acquire To Retire | Asset Register | Asset Register | Phase 1 | ERP Cloud | Sprint 8.5 | OTBI | Inbound | NA |  |  | NA | NA | High | Must Have | Simon Lu | Sriniivas Kompalli | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-21 | 2021-09-27 | 2021-09-01 | 2021-09-20 | 100% - Complete | 2021-09-28 | 2021-10-05 | 2021-10-12 | 2021-10-18 | 100% - Complete | 2021-11-12 | Approved | 2021-11-12 | 2021-10-26 | 2021-11-12 | 2021-10-19 | 2021-11-11 | 100% - Complete | 2021-11-15 | 2021-11-19 | 2021-11-15 | 2021-11-19 | 100% - Complete |  | RICE 3 |  | Report Resolves a Gap Process |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R003 | Report | Acquire To Retire | Asset Transaction Report | Asset Transaction Report | Phase 1 | ERP Cloud | Sprint 8.5 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Simon Lu | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-18 | 2021-10-22 | 2021-09-01 | 2021-10-08 | 100% - Complete | 2021-10-25 | 2021-10-28 | 2021-10-11 | 2021-10-21 | 100% - Complete | 2021-10-29 | Approved | 2021-10-29 | 2021-10-26 | 2021-11-02 | 2021-10-26 | 2021-11-11 | 100% - Complete | 2021-11-03 | 2021-11-05 | 2021-11-02 | 2021-11-11 | 100% - Complete |  | RICE 2 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R004 | Report | Acquire To Retire | Capital Invoice Reconciliation Report | Capital Invoice Reconciliation Report | Phase 1 | ERP Cloud | Sprint 8.5 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Simon Lu | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-27 | 2021-09-30 | 2021-10-20 | 2021-12-09 | 100% - Complete | 2021-12-22 | 2022-01-04 | 2021-12-09 | 2021-12-09 | 100% - Complete | 2022-02-04 | Approved | 2022-02-04 | 2022-01-05 | 2022-01-24 | 2021-12-09 | 2021-12-23 | 100% - Complete | 2022-01-25 | 2022-01-28 | 2021-12-23 | 2021-01-06 | 100% - Complete |  | RICE 3 |  | 11/15/2021: NArayan to confirm by CoB 11/16/2021 if this report can be ready for December Sprint. 11/8/2021: Met with Jake/Stover, func spec should be completed by EOD 11/8/2021. ETA for Tech Spec is by 11/12/2021 10/04/2021: ETA is to start the requirements/func spec the week of 10/04/2021 10/25/2021: Planning to meet A2R team this week to discuss requirements and review the report that Deloitte has put together and build on those reports |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 110 | 60 | 50 | 120 | 60 | 60
R005 | Report | Acquire To Retire | Category Reconciliation Report | Category Reconciliation Report | Phase 1 | ERP Cloud | Sprint 8.5 |  | Inbound | NA |  |  | NA | NA | High | Should Have | Simon Lu | Sriniivas Kompalli | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2022-01-03 | 2022-01-10 | 2021-09-01 | 2021-09-20 | 100% - Complete | 2022-02-03 | 2022-02-10 | 2021-11-01 | 2021-11-03 | 100% - Complete | 2021-11-12 | Approved | 2021-11-12 | 2022-02-11 | 2022-02-28 | 2021-10-27 | 2021-11-11 | 100% - Complete | 2022-03-01 | 2022-03-04 | 2021-11-16 | 2021-12-14 | 100% - Complete |  | RICE 3 | Tested |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R006 | Report | Acquire To Retire | Detail Asset CIP Report | Detail Asset CIP Report | Phase 1 | ERP Cloud | Sprint 8.5 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Chilakamarri, Srinivas | Krishna Aravapalli | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-08 | 2021-10-14 | 2021-10-05 | 2021-11-24 | 100% - Complete | 2022-01-25 | 2022-02-03 | 2021-11-08 | 2021-11-15 | 100% - Complete | N/A | N/A | N/A | 2022-02-04 | 2022-02-21 | 2021-11-16 | 2021-11-30 | 100% - Complete | 2022-02-22 | 2022-02-24 | 2021-12-01 | 2021-12-07 | 100% - Complete |  |  |  | 11/22/2021: Report should be ready for sprinting in December per schedule 11/15/2021: NArayan to confirm by CoB 11/16/2021 if this report can be ready for December Sprint. 11/8/2021: Func spec should be completed by 11/17/2021 10/25/2021: Planning to meet A2R team this week to discuss requirements |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R007 | Report | Acquire To Retire | Intangible Assets Questionnaire | Intangible Assets Questionnaire | TBD | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Could Have | Chilakamarri, Srinivas | Krishna Aravapalli | District Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | 10/04/2021: Per A2R team, this report is no longer is required in DIFS. A CR will be submitted to descope this |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R008 | Report | Acquire To Retire | Multi Funded Assets Report | Multi Funded Assets Report | Phase 1 | ERP Cloud | Sprint 8.5 |  | Inbound | NA |  |  | NA | NA | Medium | Should Have | Simon Lu | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-11-18 | 2021-11-24 | 2021-11-25 | 2021-12-02 | 100% - Complete | 2021-11-24 | 2021-12-06 | 2021-12-09 | 2021-12-13 | 100% - Complete | 2022-02-04 | Approved | 2022-02-04 | 2021-12-06 | 2021-12-23 | 2021-12-13 | 2021-12-13 | 100% - Complete | 2021-12-23 | 2021-12-29 | 2021-12-13 | 2021-12-17 | 100% - Complete |  | RICE 4 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 110 | 60 | 50 | 120 | 60 | 60
R009 | Report | Acquire To Retire | Pollution Remediation Questionnaire | Pollution Remediation Questionnaire | TBD | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Could Have | Chilakamarri, Srinivas | Krishna Aravapalli | District Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | 10/04/2021: Per A2R team, this report is no longer is required in DIFS. A CR will be submitted to descope this |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R010 | Report | Acquire To Retire | Service Concession Agreement Questionnaire | Service Concession Agreement Questionnaire | TBD | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Could Have | Chilakamarri, Srinivas | Krishna Aravapalli | District Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | 10/04/2021: Per A2R team, this report is no longer is required in DIFS. A CR will be submitted to descope this |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R011 | Report | Acquire To Retire | Summarized Asset Closing report | Summarized Asset Closing report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R012 | Report | Acquire To Retire | Summary Asset CIP Report | Summary Asset CIP Report | Phase 1 | ERP Cloud | Sprint 8.5 |  | Inbound | NA |  |  | NA | NA | Medium | Should Have | Chilakamarri, Srinivas | Krishna Aravapalli | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-22 | 2021-10-27 | 2021-10-05 | 2021-11-24 | 100% - Complete | 2022-02-22 | 2022-03-03 | 2021-11-08 | 2021-11-15 | 100% - Complete | N/A | N/A | N/A | 2022-03-04 | 2022-03-21 | 2021-11-16 | 2021-11-30 | 100% - Complete | 2022-03-22 | 2022-03-24 | 2021-12-01 | 2021-12-07 | 100% - Complete |  |  |  | 11/22/2021: Report should be ready for sprinting in December per schedule 11/15/2021: NArayan to confirm by CoB 11/16/2021 if this report can be ready for December Sprint. 11/8/2021: Func spec should be completed by 11/17/2021 |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R013 | Report | Budget To Report | "Everything" report | "Everything" report | Phase 2 | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R014 | Report | Budget To Report | Bank reconciliation report | Bank reconciliation report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R015 | Report | Budget To Report | Bank Statement Reconciliation report | Bank Statement Reconciliation report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R016 | Report | Budget Execution | CY Budget vs Historical Actuals report | CY Budget vs Historical Actuals report | TBD | EPM Cloud | Sprint 11 |  | Inbound | NA |  |  | NA | NA | Medium | Should Have | Sid Gayam | Venkata NagaBhatla (Ravi) | District Owned | Offtrack (Active) | Active | N/A | 0-Not Started | -91 | Approved | 2022-02-07 | 2022-02-11 |  |  |  | 2022-02-14 | 2022-02-21 |  |  |  | N/A | N/A | N/A | 2022-03-03 | 2022-03-18 |  |  |  | 2021-03-30 | 2022-04-05 | [6 empty] | 01/10/2022: Merged with R137: 12/13/2021: CR(751775) has been logged to move the report to EPM 11/22/2021: Meeting scheduled for tomorrow (11/23) to discuss with Budget team to move the report to EPM CR is approved to realign this report from ERP to EPM. Narayn to provide resource and schedule for this report |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R017 | Report | Budget To Report | Due to, Due From report | Due to, Due From report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R018 | Report | Budget Execution | ERP and EPM comparison report | ERP and EPM comparison report | Phase 1 | EPM Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Medium | Could Have | Sid Gayam | Venkata NagaBhatla (Ravi) | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-12-01 | 2021-12-17 | 2021-12-01 | 2022-01-14 | 100% - Complete | 2021-12-20 | 2022-01-07 | 2022-01-11 | 2022-01-14 | 100% - Complete | N/A | N/A | N/A | 2022-01-10 | 2022-01-21 | 2022-01-18 | 2022-01-26 | 100% - Complete | 2022-01-24 | 2022-01-28 | 2022-01-26 | 2022-01-28 | 100% - Complete |  |  |  | 01/04/2022: Should the ownership be changed to Deloitte from District? 12/13/2021: CR(751775) has been logged to move the report to EPM |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R019 | Report | Budget To Report | Expenditure and revenue report | Expenditure and revenue report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Trinh Trinh | Percy Mangwiro | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-09 | 2021-07-20 | 2021-05-17 | 2021-08-02 | 100% - Complete | 2021-07-21 | 2021-07-28 | 2021-06-28 | 2021-08-16 | 100% - Complete | 2021-11-29 | Approved | 2021-11-29 | 2021-07-29 | 2021-08-16 | 2021-08-17 | 2021-09-01 | 100% - Complete | 2021-09-27 | 2021-10-18 | 2021-09-27 | 2021-12-02 | 100% - Complete |  | RICE 3 |  | 10/21/2021 - check with Trinh - scope is changing? Call 10/22/2021 |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R020 | Report | Budget To Report | Financial Audit report | Financial Audit report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R021 | Report | Budget Execution | Financial Status Report extract | Financial Status Report extract | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Must Have | Sid Gayam | Venkata NagaBhatla (Ravi) | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-12-06 | 2021-12-17 | 2021-12-01 | 2022-01-06 | 100% - Complete | 2021-12-20 | 2022-01-07 | 2021-12-28 | 2022-01-11 | 100% - Complete | N/A | N/A | N/A | 2022-01-10 | 2022-01-21 | 2022-01-18 |  | 100% - Complete | 2022-01-24 | 2022-01-28 | 2022-02-15 | 2022-02-18 | 100% - Complete |  |  |  | 02/14/2022: Targeted to complete build this week and start unit testing next week. 01/04/2022: Should the ownership be changed to Deloitte from District? 12/13/2021: CR(751775) has been logged to move the report to EPM 11/29/2021: Narayan to get the CR created to move the report from ERP to EPM 11/22/2021: Meeting scheduled for tomorrow (11/23) to discuss with Budget team to move the report to EPM 11/15/2021: Narayan to confirm if this report can be moved to EPM |  | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R022 | Report | Budget To Report | Fund Balance report | Fund Balance report | Phase 1 | ERP Cloud | Sprint 11 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Goel; Nidhi (OCFO-Contractor) | Narayan Ayyagari | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-16 | 2021-06-22 | 2021-06-18 | 2021-07-08 | 100% - Complete | 2021-07-07 | 2021-07-16 | 2021-07-21 | 2021-08-10 | 100% - Complete | N/A | N/A | N/A | 2021-07-19 | 2021-08-03 | 2021-08-16 | 2021-08-27 | 100% - Complete | 2021-08-04 | 2021-08-06 | 2021-09-06 | 2021-09-10 | 100% - Complete |  |  |  | Plan is to complete the unit testing the week of 8/30/2021 |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R023 | Report | Budget To Report | GL Detail Transaction Extract | GL Detail Transaction Extract | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Goel; Nidhi (OCFO-Contractor) | Narayan Ayyagari | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-01 | 2021-07-09 | 2021-07-09 | 2021-07-30 | 100% - Complete | 2021-08-05 | 2021-08-13 | 2021-08-02 | 2021-08-20 | 100% - Complete | N/A | N/A | N/A | 2021-08-16 | 2021-08-31 | 2021-08-18 | 2021-08-27 | 100% - Complete | 2021-09-01 | 2021-09-03 | 2021-08-31 | 2021-09-10 | 100% - Complete | [5 empty] | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R024 | Report | Order To Cash | Inovah Verification report | Inovah Verification report | Phase 1 | ERP Cloud | Sprint 11 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Srinivas C. | Narayan Ayyagari | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-10 | 2021-11-17 | 2022-01-12 | 2022-01-21 | 100% - Complete | 2021-12-06 | 2021-12-14 | 2022-01-18 | 2022-01-25 | 100% - Complete | N/A | N/A | N/A | 2021-12-15 | 2022-01-04 | 2022-01-26 | 2022-01-28 | 100% - Complete | 2022-01-05 | 2022-01-07 | 2022-01-27 | 2022-01-28 | 100% - Complete |  |  |  | 12/23/2021: Plan to merge with R043, will confirm by 12/20 11/29/2021: Narayan to confim with Meg/Subrah if report can be merged with R043 report 11/22/2021: Narayan to follow up with the team and confirm by 12/6/2021 if this can be merged with R043 |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R025 | Report | Budget To Report | Budgetary Control Analysis Report | Non Personnel Service (NPS) Budget Reports | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Trinh Trinh | Percy Mangwiro | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2022-07-15 | 2021-07-22 | 2021-08-16 | 2021-07-22 | 100% - Complete | 2021-07-23 | 2021-07-30 | 2021-07-26 | 2021-08-19 | 100% - Complete | 2021-10-14 | Approved | 2021-10-14 | 2021-08-02 | 2021-08-18 | 2021-08-19 | 2021-09-27 | 100% - Complete | 2021-09-27 | 2022-02-18 | 2021-09-27 |  | 100% - Complete |  | RICE 3 |  | 02/21/2021: YTD solution provided and build completed. Trinh is validating the report 02/17/2022: Requirement to add to YTD amount. Trinh will update the specs. Percy to research and advise 02/07/2022 : Trinh had requested some changes. Percy is working on the changes 02/03/2021 : Report changes completed. Trinh is testing the Report. 01/13/2022 : Fixing isseus and completing unit testing by 01/14/2022 12/16/2021 : not returning data when it should - Percy will figure it out - similar issue to R019 make this a priority 10/21/2021: issue identified will work with Percy on the issue |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 175 | 50 | 125
R026 | Report | Budget To Report | Chart of Account Profile Data Report | Org/Program report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Jessica Rubin | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-19 | 2021-07-27 | 2021-07-19 | 2021-07-27 | 100% - Complete | 2021-07-27 | 2021-11-11 | 2021-07-27 | 2021-08-06 | 100% - Complete | 2021-08-20 | Approved | 2021-08-20 | 2021-07-27 | 2021-11-29 | 2021-07-27 | 2021-08-06 | 100% - Complete | 2021-11-30 | 2021-12-03 | 2021-08-13 | 2021-09-03 | 100% - Complete |  | RICE 2 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R027 | Report | Budget To Report | Personnel Service (PS) and Non Personnel Service (NPS) expenditure by public school | Personnel Service (PS) and Non Personnel Service (NPS) expenditure by public school | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Goel; Nidhi (OCFO-Contractor) | Narayan Ayyagari | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-01 | 2021-06-08 | 2021-06-01 | 2021-06-11 | 100% - Complete | 2021-06-09 | 2021-06-17 | 2021-06-14 | 2021-07-06 | 100% - Complete | N/A | N/A | N/A | 2021-06-18 | 2021-07-06 | 2021-06-21 | 2021-07-22 | 100% - Complete | 2021-07-07 | 2021-07-12 | 2021-07-26 | 2021-08-06 | 100% - Complete | [5 empty] | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R028 | Report | Budget To Report | Personnel Service (PS) Charges Expenditure report | Personnel Service (PS) Charges Expenditure report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R029 | Report | Budget To Report | School Advances Report | School Advances Report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R030 | Report | Budget To Report | Special Purpose Revenue Report | Special Purpose Revenue Report | Phase 2 | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R031 | Report | Budget To Report | Subledger Reconciliation Report | Subledger Reconciliation Report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Medium | Must have | Tushar Bhansali | Devananda Panchumarty | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-25 | 2021-08-25 | 2021-10-14 | 2021-10-14 | 100% - Complete | 2021-10-25 | 2021-11-22 | 2021-10-27 | 2021-10-27 | 100% - Complete | 2021-12-01 | Approved | 2021-12-01 | 2021-11-23 | 2021-12-03 | 2022-01-24 | 2022-02-11 | 100% - Complete | 2021-12-06 | 2022-02-18 | 2021-12-01 | 2022-02-18 | 100% - Complete |  | RICE 3 |  | 02/18/2022: will be reviewed on Friday and sprinted next Tuesday 02/17/2022: Testing in progress 02/10/2022: Testing in Progress. 02/07/2022 : Tushar and Tej to test the report and confirm 02/03/2022: Tushar is updating the lean spec for layout and also testing the changes 01/27/2022: Bhaskar has gotten feedback from Tushar - Tej meeting tomorrow morning 01/13/2022: Will be sending data to Tushar for review and validation 09/02/2021: This may not be needed?; Submitted to District for approval on 11/23 due by 11/30 |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R032 | Report | Budget To Report | Summer Pay Credit Report for DCPS | Summer Pay Credit Report for DCPS | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R033 | Report | Projects and Grants | Total Budget by fund for Capital Improvement Plan (CIP) (To be Descoped) | Total Budget by fund for Capital Improvement Plan (CIP) | TBD | ERP Cloud | Sprint 11 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Tej Mehta | Vijay Jampana | Deloitte Owned | Offtrack (Active) | Active | N/A | 0-Not Started | -150 | Approved | 2021-12-07 | 2021-12-14 |  |  | 0% - Not Started | 2022-01-06 | 2022-01-13 |  |  |  | N/A | N/A | N/A | 2022-01-14 | 2022-02-02 |  |  |  | 2022-03-10 | 2022-03-16 |  |  |  |  | RICE 4 |  | 02/10/2022: CR 759002 for descoping the report per the team 02/07/2022 : Tej to confirm on the descoping of the Report 01/13/2022: Followup with Tej and Jessica on Func. specs Jen follow up Rohan - Budget Report? |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R034 | Report | Budget To Report | Transaction Detail Report | Transaction Detail Report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R035 | Report | Budget To Report | Variance/Available Balance Report - Budget vs Actuals | Variance/Available Balance Report - Budget vs Actuals | Phase 1 | ERP Cloud | Sprint 11 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Goel; Nidhi (OCFO-Contractor) | Narayan Ayyagari | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-17 | 2021-06-23 | 2021-06-18 | 2021-06-30 | 100% - Complete | 2021-07-08 | 2021-07-19 | 2021-07-02 | 2021-07-22 | 100% - Complete | N/A | N/A | N/A | 2021-07-20 | 2021-08-04 | 2021-07-26 | 2021-08-18 | 100% - Complete | 2021-08-05 | 2021-08-09 | 2021-08-18 | 2021-08-27 | 100% - Complete |  |  |  | Unit Testing to be completed by 8/27/2021 |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R036 | Report | Budget To Report | Washington Teachers Union Member Accrual Report | Washington Teachers Union Member Accrual Report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R037 | Report | Interagency | Intra-district budget dashboard | Intra-district budget dashboard | TBD | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Jagannathan Viswanathan | Percy Mangwiro | Deloitte Owned | Offtrack (Active) | Active | N/A | 0-Not Started | -168 | Approved | 2021-11-17 | 2021-11-26 |  |  |  | 2022-01-31 | 2022-02-08 |  |  |  | N/A | N/A | N/A | 2022-02-09 | 2022-02-25 |  |  |  | 2022-01-03 | 2022-01-10 |  |  |  |  | TBD |  | 12/13/2021 (Tej): Met with the District and agreed that this report can be descoped since the requirements can be fulfilled by R085 report. Requested a CR to descope report. | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R038 | Report | Interagency | Intra-district dashboard | Intra-district dashboard | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R039 | Report | Interagency | Intra-district fixed costs report | Intra-district fixed costs report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R040 | Report | Order To Cash | Agency Invoice report | Agency Invoice report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Andrew Fedoris | Vijay Jampana | Deloitte Owned | Offtrack (Active) | Active | N/A | 2-Technical Spec | -144 | Approved | 2021-08-05 | 2021-08-12 | 2021-08-05 | 2021-08-26 | 100% - Complete | 2021-12-15 | 2021-12-20 |  |  |  | N/A | N/A | N/A | 2021-12-21 | 2021-12-29 |  |  |  | 2021-12-30 | 2022-01-03 | [6 empty] | CR # 739548 is approved to merge R040 and R058 | Merged | 0 | 0 | 0 | 0 | 120 | 60 | 85 | 0 | 0 | 0 | 0 | 0 | 0
R041 | Report | Order To Cash | AR Statement Report | AR Statement Report | TBD | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Andrew Fedoris | Sriniivas Kompalli | Deloitte Owned | Offtrack (Active) | Active | N/A | 1-Functional Spec | -70 | Approved | 2022-02-28 | 2022-03-04 | 2021-11-22 |  | 75% - In Review | 2022-03-07 | 2022-03-14 |  |  |  | N/A | N/A | N/A | 2022-03-15 | 2022-03-22 |  |  |  | 2022-03-23 | 2022-03-25 |  |  |  |  | TBD |  | CR being processed to descope as per Eric's email on 1/4 - CR 753833 approved and executed | No | 0 | 0 | 0 | 0 | 120 | 60 | 85 | 0 | 0 | 0 | 0 | 0 | 0
R042 | Report | Order To Cash | Bank ID Funding Report | Bank ID Funding Report | TBD | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Medium | Should Have | Chilakamarri, Srinivas | Raghav Goundaram | District Owned | Offtrack (Active) | Active | N/A | 3-Build | -44694 | Approved | 2021-06-03 | 2021-06-12 | 2021-06-03 | 2021-06-12 | 100% - Complete | 2021-06-14 | 2021-06-22 | 2021-06-14 | 2021-06-22 | 100% - Complete | N/A | Approved | N/A | [13 empty] | 08/17/2021: Removed By CR 730909 - Steam requested this be be replaced by Standar ERP Report - Account Analysis Report - Details in PMC | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R043 | Report | Order To Cash | Cash Distribution report | Cash Distribution report | TBD | ERP Cloud | Sprint 08 |  | Inbound | NA |  |  | NA | NA | Medium | Should Have | Chilakamarri, Srinivas | Raghav Goundaram | District Owned | Offtrack (Active) | Complete | N/A | 5-Complete | -277 | Approved | 2021-06-17 | 2021-06-23 | 2021-06-23 | 2021-07-08 | 100% - Complete | 2021-07-08 | 2021-07-19 | 2021-07-16 | 2021-07-30 | 100% - Complete | N/A | 2021-09-15 | N/A | 2021-07-20 | 2021-08-04 | 2021-08-02 | 2021-08-06 | 100% - Complete | 2021-08-05 | 2021-08-09 | 2021-08-09 | 2021-08-18 | 100% - Complete |  |  |  | 10/20/2021: R043 is dependent on I009 completing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R044 | Report | Order To Cash | Cash report | Cash report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R045 | Report | Order To Cash | Central Collections Unit Report | Central Collections Unit Report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R046 | Report | Order To Cash | Custom Sale of Assets - Revenue Report | Custom Sale of Assets - Revenue Report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Raj Amme | Sriniivas Kompalli | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2022-03-28 | 2022-04-01 | 2021-12-01 | 2021-12-09 | 100% - Complete | 2022-04-15 | 2022-04-26 | 2021-11-15 | 2021-12-21 | 100% - Complete | 2022-01-21 | Approved | 2022-01-21 | 2022-04-13 | 2022-04-29 | 2021-12-29 | 2022-01-03 | 100% - Complete | 2022-05-01 | 2022-05-06 | 2022-01-04 | 2022-01-21 | 100% - Complete |  | RICE 4 |  | 01/13/2022-Added requested columns and sent data to Raj for testing and validation 12/16/2021 - can this be consilidated with R054 |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 200 | 75 | 125
R048 | Report | Order To Cash | Customer Listing report | Customer Listing report | TBD | ERP Cloud | [10 empty] | Andrew Fedoris | Vijay Jampana | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | 09/20/2021: CR # 739548 approved to descope this report as out of the box meets Districts' requirement 09/09/2021: There is an out of the box report This report is descoped/not needed | Descoped | 0 | 0 | 0 | 0 | 120 | 60 | 85 | 0 | 0 | 0 | 0 | 0 | 0
R049 | Report | Order To Cash | Customized Dunning Letter Report | Customized Dunning Letter Report | Phase 1 | ERP Cloud | Sprint 08 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Chilakamarri, Srinivas | Raghav Goundaram | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-13 | 2021-08-20 | 2021-07-13 | 2021-08-20 | 100% - Complete | 2021-08-17 | 2021-08-20 | 2021-08-17 | 2021-08-20 | 100% - Complete | N/A | 2021-09-15 | N/A | 2021-08-23 | 2021-09-07 | 2021-08-26 | 2021-08-28 | 100% - Complete | 2021-09-08 | 2021-09-10 | 2021-09-08 | 2021-09-10 | 100% - Complete | [5 empty] | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R050 | Report | Order To Cash | Interest income report | Interest income report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Must Have | Chilakamarri, Srinivas | Raghav Goundaram | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-16 | 2021-08-20 | 2021-08-12 | 2021-08-20 | 100% - Complete | 2021-10-06 | 2021-10-14 | 2021-10-12 | 2021-10-15 | 100% - Complete | N/A | 2021-09-15 | N/A | 2021-10-15 | 2021-11-02 | 2021-09-30 | 2021-10-15 | 100% - Complete | 2021-11-03 | 2021-11-05 | 2021-11-08 | 2021-11-12 | 100% - Complete | [5 empty] | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R051 | Report | Budget to Report | Journal Entry Detail report | Journal Entry Detail report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Jessica Rubin | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-14 | 2021-06-18 | 2021-06-14 | 2021-06-18 | 100% - Complete | 2021-06-28 | 2021-07-22 | 2021-06-28 | 2021-07-22 | 100% - Complete | 2021-07-30 | Approved | 2021-07-30 | 2021-06-28 | 2021-07-23 | 2021-06-28 | 2021-07-23 | 100% - Complete | 2021-07-12 | 2021-07-29 | 2021-07-12 | 2021-07-29 | 100% - Complete |  | RICE 1 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R052 | Report | Order To Cash | Non Sufficient Funds Report | Non Sufficient Funds Report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Chilakamarri, Srinivas | Raghav Goundaram | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-30 | 2021-09-02 | 2021-08-26 | 2021-10-08 | 100% - Complete | 2021-10-25 | 2021-11-02 | 2021-11-22 | 2021-11-26 | 100% - Complete | N/A | N/A | N/A | 2021-11-03 | 2021-11-22 | 2021-11-22 | 2021-11-29 | 100% - Complete | 2021-11-23 | 2021-11-26 | 2021-11-30 | 2021-12-02 | 100% - Complete |  |  |  | 11/29/2021: ETA to complete development/unit testing by 12/3 11/22/2021: Demo completed for this report to P2P team, development is close to completion. ETA to complete the development/unit testing is by 12/3/2021 11/15/2021: Narayan to follow up with O2C team the week of 11/15/2021 10/04/2021: meeting scheduled for the week of 10/04; Srini has the required info/requirements for this report 9/27/2021: Received sample report from OTR; CR will be processed to realign this report to P2P. Narayan to follow up with Meg/Subrah for next steps 9/20/2021: Met with O2C team, awaiting for sample from OTR; expecting to get samples from PTR by 9/24/2021 9/13/2021: Awaiting sample report from O2C functional team; meetings scheduled for the week of 9/13/2021 Plan is to start this report the week of 8/30/2021 |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R053 | Report | Order To Cash | Offset report | Offset report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Andrew Fedoris | Vijay Jampana | Deloitte Owned | Complete | Complete | 3-Build | 5-Complete | 20 | In Review | 2022-04-25 | 2022-04-29 | 2022-01-27 | 2022-02-01 | 100% - Complete | 2022-05-01 | 2022-05-09 | 2022-02-02 | 2022-02-02 | 100% - Complete | 2022-02-15 | 1st Submission |  | 2022-05-10 | 2022-05-27 | 2022-02-03 | 2022-02-11 | 100% - Complete | 2022-05-30 | 2022-06-02 | 2022-02-08 | 2022-02-14 | 100% - Complete |  | RICE 4 |  | 02/10/2022: Matching R068? Checking to see if it's the same report - meeting on 02/11/2022 with Murali 02/07/2022: Technical build in Progress. Validating data with Andrew 02/03/2022: Will review the entire design and then schedule approval reviews |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 92.6471 | 75 | 17.6471
R054 | Report | Order To Cash | Receipt Detail report | Receipt Detail report | TBD | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Should Have | Andrew Fedoris | Vijay Jampana | Deloitte Owned | Offtrack (Active) | Active | N/A | 3-Build | -147 | Approved | 2021-11-10 | 2021-11-18 | 2021-11-15 | 2021-11-23 | 100% - Complete | 2021-11-19 | 2021-11-30 | 2021-11-23 | 2021-12-21 | 100% - Complete | N/A | N/A | N/A | 2021-12-01 | 2021-12-17 |  |  |  | 2021-12-20 | 2021-12-27 |  |  |  |  | TBD |  | CR being processed to descope as per Eric's email on 1/4 CR753833 approved and executed | No | 0 | 0 | 0 | 0 | 200 | 75 | 150 | 0 | 0 | 0 | 0 | 0 | 0
R055 | Report | Order To Cash | Reserved fund report | Reserved fund report | TBD | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Must Have | Chilakamarri, Srinivas | Raghav Goundaram | District Owned | Offtrack (Active) | Complete | N/A | 5-Complete | -217 | Approved | 2021-08-02 | 2021-08-20 | 2021-08-12 | 2021-08-20 | 100% - Complete | 2021-09-08 | 2021-09-17 | 2021-09-09 | 2021-10-06 | 100% - Complete | N/A | 2021-11-08 | N/A | 2021-09-20 | 2021-10-05 | 2021-10-05 | 2021-10-13 | 100% - Complete | 2021-10-06 | 2021-10-08 | 2021-10-12 | 2021-10-15 | 100% - Complete |  |  |  | 9/20/2021: Tech spec in process; ETA by 9/24/2021 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R056 | Report | Order To Cash | Revenue Details report | Revenue Details report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R057 | Report | Order To Cash | Revenue vs Expenditure report | Revenue vs Expenditure report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R058 | Report | Order To Cash | Transaction Details Report | Transaction Details Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Andrew Fedoris | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-13 | 2021-08-26 | 2021-08-13 | 2021-08-26 | 100% - Complete | 2021-08-27 | 2021-09-03 | 2021-09-13 | 2021-09-22 | 100% - Complete | 2021-10-26 | Approved | 2021-10-26 | 2021-09-06 | 2021-09-22 | 2021-09-16 | 2021-10-05 | 100% - Complete | 2021-09-23 | 2021-09-28 | 2021-10-07 | 2021-10-28 | 100% - Complete |  | RICE 2 |  | 10/21/21: Andrew updated the requirements in Functional testing |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R059 | Report | Order To Cash | Unclaimed Assets report | Unclaimed Assets report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Chilakamarri, Srinivas | Raghav Goundaram | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-10 | 2021-09-16 | 2021-09-15 | 2021-10-08 | 100% - Complete | 2021-11-23 | 2021-12-03 | 2021-11-29 | 2021-12-02 | 100% - Complete | N/A | N/A | N/A | 2021-12-06 | 2021-12-21 | 2022-01-12 | 2022-01-31 | 100% - Complete | 2021-12-22 | 2021-12-27 | 2022-02-01 | 2022-02-03 | 100% - Complete |  |  |  | 10/04/2021: Srini is reviewing the sample reports received from OFT and finalizing the requirements 9/27/2021: ETA for func spec is 10/1/2021. Received sample reports from OFT 9/21/2021: Func spec in process; ETA by 9/24/2021 |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R060 | Report | Procure To Pay | AP Data Extraction | AP Data Extraction | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Low | Could Have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | 9/13/2021: CR#736797 was approved to conslidate this report with R079 Consolidate with R079 - CR in process and to be discussed during PMO meeting | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R061 | Report | Procure To Pay | Check Hold report | Check Hold report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | N/A | N/A | N/A | [10 empty] | N/A | N/A | N/A | [13 empty] | 9/13/2021: CR#736797 was approved to conslidate this report with R079 Consolidate with R079 - CR in process and to be discussed during PMO meeting | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R062 | Report | Procure To Pay | Custom 1099 payment data report | Custom 1099 payment data report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Medium | Should Have | Muralidhar Pedasanaganti | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-05 | 2021-11-17 | 2021-11-08 | 2021-11-12 | 100% - Complete | 2021-11-12 | 2021-11-18 | 2022-01-19 | 2022-01-20 | 100% - Complete | 2022-01-27 | Approved | 2022-01-27 | 2022-01-21 | 2022-01-28 | 2022-01-20 | 2022-02-02 | 100% - Complete | 2022-01-31 | 2022-02-02 | 2022-02-02 | 2022-02-03 | 100% - Complete |  | RICE 4 |  | 02/03/2022: This can be sprinted on Monday 02/01/2022: we should be able to sprint this next Wednesday, Feb 9th/keep in Sprint 10 01/25/2022: Addressing comments 01/19/2022: Still discussing the layout with the District - waiting on an approval from Debra Bacon - Anju will send - development will start in parallel 12/21/2021: Moved to Sprint 10 Per the Team 12/07/2021: Walk through scheduled 12/08 |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R063 | Report | Procure To Pay | Custom current liabilities report with details | Custom current liabilities report with details | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-27 | 2021-10-04 | 2021-10-05 | 2021-10-13 | 100% - Complete | 2021-12-14 | 2021-12-22 | 2021-11-19 | 2021-12-01 | 100% - Complete | N/A | N/A | N/A | 2021-12-23 | 2022-01-12 | 2021-12-02 | 2021-12-09 | 100% - Complete | 2022-01-13 | 2022-01-18 | 2021-12-08 | 2021-12-10 | 100% - Complete | [5 empty] | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R064 | Report | Procure To Pay | Custom Interactive PO Master Report | Custom Interactive PO Master Report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Must have | Pandu Sadam | Percy Mangwiro | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-09-06 | 2021-09-15 | 2021-09-06 | 2021-12-22 | 100% - Complete | 2021-09-23 | 2021-10-01 | 2021-09-28 | 2021-12-23 | 100% - Complete | 2022-01-20 | Final Submission |  | 2021-09-29 | 2021-10-18 | 2021-09-29 | 2022-01-04 | 100% - Complete | 2021-10-20 | 2021-10-26 | 2022-01-04 | 2022-02-04 | 100% - Complete |  | RICE 3 |  | 02/08/2022: addressing last two spec comments 02/07/2022: Technical changes completed. Will be resprinted today 02/01/2022: Will be included in Sprint 10 - on 02/07/2022 01/27/2022: Will confirm if it will be Sprint 9 or Sprint 10 tomorrow 01/25/2022:This will moved to Sprint 10 - what the District is looking for Pandu does not have it 01/19/2022: working through one remaining issue - Pandu will update tomorrow 01/13/2022: Was sprinted on 01/12/2022. Changes in design requsted by the district. Pandu and Percy will meet and finalize the design. 12/23/2021: Plan to release to testing by Monday 12/27 12/07/2021: The interactive report is going to be OTBI not BI - there is a need to redesign this report - Jen to follow up with Reddy and Divya |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R065 | Report | Procure To Pay | Custom invoice hold report | Custom invoice hold report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Must have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-28 | 2021-08-03 | 2021-08-12 | 2021-08-20 | 100% - Complete | 2021-08-27 | 2021-09-07 | 2021-08-13 | 2021-09-02 | 100% - Complete | N/A | N/A | N/A | 2021-09-21 | 2021-10-07 | 2021-09-15 | 2021-10-05 | 100% - Complete | 2021-10-07 | 2021-10-09 | 2021-10-06 | 2021-10-08 | 100% - Complete | [5 empty] | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R066 | Report | Procure To Pay | Custom invoice processing time report | Custom invoice processing time report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Low | Must have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-23 | 2021-11-29 | 2021-10-05 | 2021-12-02 | 100% - Complete | 2021-12-03 | 2021-12-13 | 2021-12-14 | 2021-12-20 | 100% - Complete | N/A | N/A | N/A | 2021-12-14 | 2021-12-30 | 2022-01-06 | 2022-01-13 | 100% - Complete | 2021-12-31 | 2022-01-05 | 2022-01-12 | 2022-01-14 | 100% - Complete |  |  |  | 11/29/2021: func spec in process; ETA to complete func spec by 12/8/2021 |  | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R067 | Report | Procure To Pay | Custom one time payments report | Custom one time payments report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Should Have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-11 | 2021-08-17 | 2021-08-26 | 2021-10-13 | 100% - Complete | 2021-10-08 | 2021-10-18 | 2021-10-12 | 2021-10-20 | 100% - Complete | N/A | N/A | N/A | 2021-10-26 | 2021-11-12 | 2021-10-20 | 2021-11-07 | 100% - Complete | 2021-11-15 | 2021-11-17 | 2021-11-08 | 2021-11-12 | 100% - Complete |  |  |  | 10/04/2021: CR to be submitted today (10/04) to PMO 9/27/2021: Narayan to follow up with Subrah if CR is submitted. if not, Narayan will send out an email to PMO with CR details 9/20/2021: CR# to be processed; Meg has confirmed this report is no longer required; Narayan to send out the info to PMO to process the CR. 9/13/2021: Functional spec to be finalized the week of 9/13/2021 Started R081 ahead of schedule; Plan is to start the week of 8/23/2021 |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R068 | Report | Procure To Pay | Custom payment offset report | Custom payment offset report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Must have | Muralidhar Pedasanaganti | Devananda Panchumarty | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 2-Technical Spec | -67 | Not Submitted | 2022-02-03 | 2022-02-14 | 2022-01-27 | 2022-02-03 | 100% - Complete | 2022-02-28 | 2022-03-07 |  |  |  |  | N/A |  | 2022-03-08 | 2022-03-24 |  |  |  | 2022-03-25 | 2022-03-30 |  |  |  |  | RICE 4 |  | 02/17/2022:Keenan to confirm the scope - R053 was sprinted this week - can we descope R068 - Jen will create CR to merge 02/15/2022: We will merge with O2C R053? Work to get Agency added to R053 and descope R068. Include additional folks to Thursday meeting 02/10/2022: is this a duplicate of the O2C report R053? Andrew working with Eric will know by early next week 02/08/2022: Functional Spec completed - shared with Tech team - Bhaskar will start tech work 02/09/2022 |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 25 | 25 | 0 | 200 | 75 | 125
R069 | Report | Procure To Pay | Custom payment register report | Custom payment register report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Low | Must have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-12 | 2021-10-18 | 2021-10-05 | 2021-11-18 | 100% - Complete | 2022-01-13 | 2022-01-24 | 2021-11-18 | 2022-01-06 | 100% - Complete | N/A | N/A | N/A | 2022-01-25 | 2022-02-11 | 2021-12-28 | 2022-01-12 | 100% - Complete | 2022-02-14 | 2022-02-16 | 2022-01-13 | 2022-01-14 | 100% - Complete |  |  |  | 11/15/2021: Plan is to start this report next week, 11/22/2021 11/8/2021: Plan is to start this report next week, 11/15/2021 10/25/2021: Planning to meet A2R team this week to discuss requirements |  | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R070 | Report | Procure To Pay | Custom payments due report | Custom payments due report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | 9/13/2021: CR#736797 was approved to conslidate this report with R079 Consolidate with R079 - CR in process and to be discussed during PMO meeting | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R071 | Report | Procure To Pay | Custom PO open balances report with accounting and aging | Custom PO open balances report with accounting and aging | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must have | Pandu Sadam | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-19 | 2021-07-30 | 2021-07-19 | 2021-08-18 | 100% - Complete | 2021-07-29 | 2021-08-20 | 2021-08-02 | 2021-09-07 | 100% - Complete | 2022-01-06 | Approved | 2022-01-06 | 2021-09-07 | 2021-10-18 | 2021-09-07 | 2021-12-06 | 100% - Complete | 2021-10-19 | 2021-10-22 | 2021-12-06 | 2021-12-14 | 100% - Complete |  | RICE 3 |  | 12/07/2021: Changes in the Specs again from Zemeer - no road blocks anticipated 10/21/21: Spec changed again;Submitted to District for approval on 11/29 due by 12/2; most of the comments were from Subrah as he is OOO till Dec 3rd reached out to Narayan |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R072 | Report | Procure To Pay | Custom spend report by supplier | Custom spend report by supplier | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Muralidhar Pedasanaganti | Percy Mangwiro | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-05 | 2021-08-18 | 2021-08-19 | 2021-09-06 | 100% - Complete | 2021-09-01 | 2021-09-07 | 2021-09-07 | 2021-09-17 | 100% - Complete | 2021-10-05 | Approved | 2021-10-05 | 2021-09-08 | 2021-09-15 | 2021-09-20 | 2021-10-05 | 100% - Complete | 2021-10-07 | 2021-10-18 | 2021-10-07 | 2021-11-17 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R073 | Report | Procure To Pay | Custom time to payment report | Custom time to payment report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Medium | Must have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-09 | 2021-11-15 | 2021-10-05 | 2021-11-24 | 100% - Complete | 2021-11-03 | 2021-11-12 | 2021-11-22 | 2021-11-24 | 100% - Complete | N/A | N/A | N/A | 2021-11-15 | 2021-12-02 | 2021-11-29 | 2021-12-17 | 100% - Complete | 2021-12-03 | 2021-12-07 | 2021-12-22 | 2022-01-09 | 100% - Complete |  |  |  | 12/13/2021: Plan to finish build by 12/24 11/22/2021: Narayan to follow up with updates |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R074 | Report | Procure To Pay | Custom zero dollar invoice report | Custom zero dollar invoice report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Must have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-25 | 2021-08-31 | 2021-08-27 | 2021-09-03 | 100% - Complete | 2021-11-15 | 2021-11-23 | 2021-11-18 | 2021-11-22 | 100% - Complete | N/A | N/A | N/A | 2021-11-24 | 2021-12-13 | 2022-01-06 | 2022-01-13 | 100% - Complete | 2021-12-14 | 2021-12-16 | 2022-01-12 | 2022-01-14 | 100% - Complete | [5 empty] | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R075 - Swap | Report | Procure To Pay | Detailed Payment Register Report | Detailed Payment Register Report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must have | Muralidhar Pedasanaganti | Percy Mangwiro | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A |  | N/A | N/A |  |  |  |  | N/A | [5 empty] | N/A | N/A | N/A | [13 empty] | 09/03/2021: We had a meeting with the District team and found out that the requirements for the below listed two reports are the same. Narayan’s team has already started report development for R079 (District owned report). Subrah is checking to see if we really need to build R075. For now, R075 is on hold. 1/19/2022: Determined to be duplicate of R081, no longer needed. | Descoped | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R076 | Report | Procure To Pay | Encumbrances and Pre-Encumbrances Report | Encumbrances and Pre-Encumbrances Report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R077 | Report | Procure To Pay | Expense Report and P Card invoice details | Expense Report and P Card invoice details | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Pandu Sadam | Percy Mangwiro | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 1-Functional Spec | -81 | Not Submitted | 2022-02-14 | 2022-02-21 | 2022-02-08 | 2022-02-21 | 75% - In Review | 2022-02-22 | 2022-02-25 |  |  |  |  | N/A |  | 2022-02-28 | 2022-03-04 |  |  |  | 2022-03-07 | 2022-03-11 |  |  |  |  | RICE 4 |  | 02/17/2022:Pandu working on specs 02/14/2022: Pandu is working on the Func. Spec. Scheduled to complete by end of the week or early next week. |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 18.75 | 18.75 | 0 | 120 | 60 | 60
R078 | Report | Procure To Pay | Invoices workflow status report | Invoices workflow status report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Must Have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-16 | 2021-06-22 | 2021-06-18 | 2021-06-25 | 100% - Complete | 2021-06-23 | 2021-07-01 | 2021-06-25 | 2021-07-02 | 100% - Complete | N/A | N/A | N/A | 2021-07-02 | 2021-07-21 | 2021-07-07 | 2021-07-23 | 100% - Complete | 2021-07-22 | 2021-07-26 | 2021-08-09 | 2021-08-13 | 100% - Complete | [5 empty] | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R079 | Report | Procure To Pay | payment/cleared status report by invoice | payment/cleared status report by invoice | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Gorti; Subrah (OCFO-Contractor) | Ayyagari; Narayan (OCFO) | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-01 | 2021-06-08 | 2021-06-01 | 2021-06-11 | 100% - Complete | 2021-09-01 | 2021-09-13 | 2021-09-01 |  | 100% - Complete | N/A | N/A | N/A | 2021-09-14 | 2021-09-29 | 2021-09-08 | 2021-09-28 | 100% - Complete | 2021-09-30 | 2021-10-04 | 2021-09-30 | 2021-10-05 | 100% - Complete |  |  |  | 9/20/2021: tech spec in process; ETA by 9/23/2021 and then start development 9/13/2021: CR#736797 was approved to conslidate R060, R061, R070 with R079 |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R080 | Report | Procure To Pay | Retainage Report | Retainage Report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Low | Must have | Pandu Sadam | Percy Mangwiro | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-12-13 | 2021-12-21 | 2021-12-16 | 2021-12-23 | 100% - Complete | 2022-03-23 | 2022-03-24 | 2022-01-04 | 2022-01-11 | 100% - Complete | 2022-01-28 | 1st Submission |  | 2022-02-01 | 2022-02-18 | 2022-02-01 | 2022-02-10 | 100% - Complete | 2022-02-01 | 2022-02-18 | 2022-02-01 | 2022-02-11 | 100% - Complete |  | RICE 4 |  | 02/07/2022: Percy working on the Techincal changes required from Testing inout by Pandu. PLan to spring next week if not earlier. 02/03/2022: Percy working on this - still planning for sprint next wednesday 02/01/2022: adding more columns per the spec review feedback - aiming for Feb 9 01/27/2022: some requirement changes Pandu is working 01/25/2022: Spec review scheduled for 01/26/2022 01/19/2022: can Anju schedule walk through next week 01/13/2022:Tech specs to be reviewed and status updated 12/16/2021 - got requirements Pandu moving on spec |  | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R081 | Report | Procure To Pay | Vendor payment extract | Vendor payment extract | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Low | Must have | Gorti; Subrah (OCFO-Contractor) | Krishna Aravapalli | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-08 | 2021-10-15 | 2021-08-18 | 2021-08-31 | 100% - Complete | 2022-01-31 | 2022-02-04 | 2021-09-01 | 2021-09-28 | 100% - Complete | N/A | N/A | N/A | 2021-10-18 | 2021-11-02 | 2021-11-03 | 2021-11-08 | 100% - Complete | 2021-11-03 | 2021-11-05 | 2021-11-08 | 2021-11-12 | 100% - Complete | [5 empty] | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R082 | Report | Projects and Grants | Bond Reconciliation Report | Bond Reconciliation Report | Phase 2 | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have | Tej Mehta | Sriniivas Kompalli | Deloitte Owned | Offtrack (Active) | Active | N/A | 0-Not Started | -179 | Approved | 2021-11-11 | 2021-11-15 |  |  |  | 2021-11-16 | 2021-11-19 |  |  |  | N/A | N/A | N/A | 2021-11-22 | 2021-12-03 |  |  |  | 2021-12-04 | 2021-12-06 |  |  |  |  | RICE 3 |  | 02/14/2022: CR 759315 has been created to move to Phase 2 02/10/2022: Meeting with OBP, have layout, will start specs 02/07/2022: Tej to cofirm on the descoping of the report 01/06/2022: Taking a step back - slightly delayed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R083 | Report | Budget Formulation | Capital formulation data extract | Capital formulation data extract | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  |  | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | 2021-07-27 | 2021-08-11 |  |  |  | 2021-08-12 | 2021-08-16 | [6 empty] | Budget report this needs to be reassigned; 06/17/2021: Rebaseline will be moved to Phase 2 - will connect with Rohan to get final approval after rebaseline |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R084 | Report | Projects and Grants | Capital FTES and positions Report | Capital FTES and positions Report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R085 | Report | Projects and Grants | P&G LTD Balances Report | P&G LTD Balances Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Tej Mehta | Sriniivas Kompalli | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-17 | 2021-05-18 | 2021-05-17 | 2021-05-18 | 100% - Complete | 2021-05-19 | 2021-05-28 | 2021-06-28 | 2021-08-02 | 100% - Complete | 2021-08-14 | Approved | 2021-08-14 | 2021-06-28 | 2021-07-14 | 2021-06-28 | 2021-08-03 | 100% - Complete | 2021-07-15 | 2021-07-20 | 2021-08-12 | 2021-10-07 | 100% - Complete |  | RICE 2 | Sprinted | 06/17/2021: Reports rebaseline based on modifications to contract - new tech resource waiting on laptop |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R086 | Report | Projects and Grants | Capital Report by Project and Subproject | Capital Report by Project and Subproject | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R087 | Report | Projects and Grants | Capital Transaction Detail | Capital Transaction Detail | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Out of Scope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R089 | Report | Projects and Grants | Closed Capital Project Report | Closed Capital Project Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Krishna Thandra | Raghavendar Goundaram | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-26 | 2021-12-02 | 2021-11-29 | 2021-12-02 | 100% - Complete | 2022-01-05 | 2022-01-14 | 2022-01-06 | 2022-01-10 | 100% - Complete | N/A | N/A | N/A | 2022-01-17 | 2022-02-02 | 2022-01-11 | 2022-01-12 | 100% - Complete | 2022-02-03 | 2022-02-07 | 2022-01-13 | 2022-01-14 | 100% - Complete |  |  | Sprinted | 10/12/2021 (01/24/2022?) |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R090 | Report | Projects and Grants | Current YTD Actions on Available Allotments data extract | Current YTD Actions on Available Allotments data extract | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Must Have | Krishna Thandra | Raghavendar Goundaram | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-12-03 | 2021-12-08 | 2021-12-20 | 2021-12-30 | 100% - Complete | 2022-02-03 | 2022-02-14 | 2021-12-27 | 2021-12-30 | 100% - Complete | N/A | N/A | N/A | 2022-02-15 | 2022-03-04 | 2021-12-29 | 2022-01-13 | 100% - Complete | 2022-03-07 | 2022-03-09 | 2022-01-13 | 2022-01-14 | 100% - Complete |  |  | Sprinted | 10/26/2021 (02/24/2022?) |  | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R091 | Report | Projects and Grants | Federal Reimbursement Report (SF270) | Federal Reimbursement report (SF270) | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Low | Must Have | Krishna Thandra | Raghavendar Goundaram | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-27 | 2021-09-01 | 2021-09-06 | 2021-11-05 | 100% - Complete | 2021-11-04 | 2021-11-15 | 2021-10-20 | 2021-12-27 | 100% - Complete | N/A | N/A | N/A | 2021-11-16 | 2021-12-03 | 2021-12-20 | 2021-12-30 | 100% - Complete | 2021-12-06 | 2021-12-08 | 2021-12-22 | 2022-01-09 | 100% - Complete |  |  |  | 12/13/2021: Krishna working with Tej to complete the needed configurations 11/29/2021: func spec is complete; ETA to complete tech spec is 12/3/2021 11/22/2021: Narayan to follow up with details 10/25/2021: Krishna is creating sample data into DEV5, review standard report and identify changes required for this report; Narayan to confirm ETA 10/04/2021: Met with Krishna to finalize the requirements 9/27/2021: Awaiting for a new P&G resource to be onboarded 9/20/2021: Awaiting for a new P&G resource to be onboarded 9/13/2021: Functional Spec in progress and meetings scheduled for the week of 9/13/2021 Plan is to start this report the week of 8/30/2021 |  | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R092 | Report | Projects and Grants | Fund by Award Report | Fund by Award Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Should Have | Krishna Thandra | Raghavendar Goundaram | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-30 | 2021-08-05 | 2021-08-16 | 2021-08-26 | 100% - Complete | 2021-08-24 | 2021-09-01 | 2021-08-26 | 2021-09-15 | 100% - Complete | N/A | 2021-12-08 | N/A | 2021-09-02 | 2021-09-17 | 2021-09-08 | 2021-09-17 | 100% - Complete | 2021-09-20 | 2021-09-22 | 2021-10-05 | 2021-10-08 | 100% - Complete |  |  | Sprinted | Functional spec is close to finalization. Tech Spec and Report development - planned to start the week of 8/30/2021; behind schedule but will catch up by unit testing |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R093 | Report | Projects and Grants | General Payroll report | General Payroll report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Could Have | Krishna Thandra | Raghavendar Goundaram | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-12-09 | 2021-12-15 | 2022-01-21 | 2022-01-26 | 100% - Complete | 2022-01-26 | 2022-02-02 | 2022-01-26 | 2022-02-02 | 100% - Complete | N/A | N/A | N/A | 2022-02-07 | 2022-02-11 | 2022-02-02 | 2022-02-08 | 100% - Complete | 2022-02-14 | 2022-02-18 | 2022-02-09 | 2022-02-12 | 100% - Complete |  |  | Sprinted | 2/7/2022: The plan is to complete build and UTP this week |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R094 | Report | Projects and Grants | Lapse report data extract (To be Descoped) | Lapse report data extract | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Should Have | Krishna Thandra | Raghavendar Goundaram | District Owned | Offtrack (Active) | Complete | N/A | 5-Complete | -126 | Approved | 2021-09-27 | 2021-10-05 | 2021-10-05 | 2021-10-20 | 100% - Complete | 2021-12-06 | 2021-12-14 | 2021-12-20 | 2021-12-28 | 100% - Complete | N/A | N/A | N/A | 2021-12-15 | 2022-01-04 | 2021-12-29 | 2022-01-19 | 100% - Complete | 2022-01-05 | 2022-01-07 | 2022-01-24 | 2022-01-27 | 100% - Complete | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R095 | Report | Projects and Grants | Maintenance of Effort data extract | Maintenance of Effort data extract | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Subrah Gorti | Krishna Aravapalli | District Owned | Offtrack (Active) | Active | N/A | 1-Functional Spec | -106 | Approved | 2022-01-21 | 2022-01-27 | 2021-12-06 |  | 25% - In Progress | 2022-05-30 | 2022-06-02 |  |  |  | N/A | N/A | N/A | 2022-06-03 | 2022-06-10 |  |  |  | 2022-02-11 | 2022-02-13 |  |  |  |  | RICE 4 | Descoped | CR 755561 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R096 | Report | Projects and Grants | Master Project Report | Master Project Report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Should Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R097 | Report | Projects and Grants | P&G Billable Report | P&G Billable Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Tej Mehta | Sriniivas Kompalli | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-06 | 2021-08-12 | 2021-08-12 | 2021-08-30 | 100% - Complete | 2021-08-17 | 2021-08-20 | 2021-09-02 | 2021-09-16 | 100% - Complete | 2021-10-04 | Approved | 2021-10-04 | 2021-08-23 | 2021-08-31 | 2021-09-02 | 2021-10-04 | 100% - Complete | 2021-09-01 | 2021-09-02 | 2021-09-22 | 2021-10-22 | 100% - Complete |  | RICE 2 | Sprinted | Name updated to P&G BIllable Report (Previously P&G Status report) |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R098 | Report | Projects and Grants | P&G to GL funds reconciliation report | P&G to GL funds reconciliation report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Tej Mehta | Sriniivas Kompalli | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-16 | 2021-06-08 |  | 2021-07-21 | 100% - Complete | 2021-07-15 | 2021-07-20 | 2021-07-26 | 2021-08-09 | 100% - Complete | 2021-08-25 | Approved | 2021-08-25 | 2021-07-21 | 2021-07-28 | 2021-08-02 | 2021-08-13 | 100% - Complete | 2021-08-16 | 2021-10-25 | 2021-08-16 | 2022-02-03 | 100% - Complete |  | RICE 3 | Sprinted | 01/13/2022: Maureen is performing Func Testing 11/18/2021: Finding issues on GL side - working on the query - similar to issues on R085 - Srini checking 10/14/2021: Issues found - sent back to DEV |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R100 | Report | Projects and Grants | Total P&G Agency Funding Report | Total P&G Agency Funding Report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Low | Should Have | Krishna Thandra | Raghavendar Goundaram | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-13 | 2021-08-19 | 2021-08-18 | 2021-08-30 | 100% - Complete | 2021-09-20 | 2021-09-29 | 2021-09-15 | 2021-10-13 | 100% - Complete | N/A | 2021-12-08 | N/A | 2021-09-30 | 2021-10-15 | 2021-10-15 | 2021-10-22 | 100% - Complete | 2021-11-04 | 2021-11-08 | 2021-11-12 | 2021-11-15 | 100% - Complete |  |  |  | 11/15/2021: ETA for report completion is end of this week, by 11/19/2021 Functional spec is close to finalization. Tech Spec and Report development - planned to start the week of 8/30/2021; behind schedule but will catch up by unit testing |  | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R101 | Report | Projects and Grants | Unspent Award/Project Balance Report | Unspent Award/Project Balance Report | TBD | ERP Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Should Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | Removed from Scope per OY2 Mod | Merged | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R102 | Report | Budget Formulation | ABC Report Status | ABC Report Status | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R103 | Report | Budget Formulation | Additional Gross Pay report | Additional Gross Pay report | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R104 | Report | Budget Formulation | Additional Request report | Additional Request report | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R105 | Report | Budget Formulation | Agency Budget before and net of Vacancy Savings | Agency Budget before and net of Vacancy Savings | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Should Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R106 | Report | Budget Formulation | Agency Submission Report | Agency Submission Report | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R107 | Report | Budget Formulation | Budget Formulation and Prior Year Data extract | Budget Formulation and Prior Year Data extract | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R108 | Report | Budget Execution | Budget vs Actuals report | Budget vs Actuals report | TBD | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Should Have |  |  |  | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | EPM Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R109 | Report | Budget Formulation | Calculation of Year-2 Actual FTEs | Calculation of Year-2 Actual FTEs | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Could Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R110 | Report | Budget Formulation | Current Service Funding Level (CSFL) Report | Current Service Funding Level (CSFL) Report | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R111 | Report | Budget Formulation | Debt model report | Debt model report | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R112 | Report | Budget Formulation | District's Proposed by Scenario, ARM Reports for Council | District's Proposed by Scenario, ARM Reports for Council | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Could Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R113 | Report | Budget Formulation | Districtwide Budget before and net of Vacancy Savings | Districtwide Budget before and net of Vacancy Savings | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R114 | Report | Budget Formulation | Estimated Impact on Operating Report | Estimated Impact on Operating Report | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R115 | Report | Budget Formulation | Exception Report | Exception Report | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R116 | Report | Budget Formulation | Fin Plan Data Dump (separate column for One-Time) | Fin Plan Data Dump (separate column for One-Time) | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | Low | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R117 | Report | Budget Formulation | LTD Capital Project balances by Funds | LTD Capital Project balances by Funds | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R118 | Report | Budget Formulation | MY budget | MY budget | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R119 | Report | Budget Formulation | One Time Report With Comments | One Time Report With Comments | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R120 | Report | Budget Formulation | Position Budgeting Data Extract | Position Budgeting Data Extract | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Should Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R121 | Report | Budget Formulation | Scenario Report | Scenario Report | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R122 | Report | Budget Formulation | Special Purpose Revenue (SPR) and Dedicated Taxes Report | Special Purpose Revenue (SPR) and Dedicated Taxes Report | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R123 | Report | Budget Formulation | Stand alone expenditure/revenue data extraction | Stand alone expenditure/revenue data extraction | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | Low | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R124 | Report | Budget Formulation | Treasury Budget Report | Treasury Budget Report | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R125 | Report | Budget Formulation | Capital Budget Request by Funding Source | Capital Budget Request by Funding Source | Phase 2 | EPM Cloud | [6 empty] | NA | NA |  | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R126 | Report | Budget Formulation | What-IF Analysis Report | What-IF Analysis Report | Phase 2 | EPM Cloud | [6 empty] | NA | NA |  | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R127 | Report | Budget Formulation | Budget Enhancements Report | Budget Enhancements Report | Phase 2 | EPM Cloud | [6 empty] | NA | NA |  | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R128 | Report | Budget Formulation | Fin Plan Assumptions | Fin Plan Assumptions | Phase 2 | EPM Cloud | [6 empty] | NA | NA |  | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R129 | Report | Budget Formulation | Position Budgeting Summary Report | Position Budgeting Summary Report | Phase 2 | EPM Cloud | [6 empty] | NA | NA |  | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R130 | Report | Budget Formulation | Mayor's Proposed by Scenario (ARM Reports - Mayor's) - Budget and FTEs | Mayor's Proposed by Scenario (ARM Reports - Mayor's) - Budget and FTEs | Phase 2 | EPM Cloud | [6 empty] | NA | NA |  | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R131 | Report | Budget Execution | Contingency Fund Report | Contingency Fund Report | TBD | EPM Cloud | [6 empty] | NA | NA |  | Must Have |  |  |  | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R132 | Report | Budget Formulation | Vacancy Savings as a % of Budget | Vacancy Savings as a % of Budget | Phase 2 | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R133 | Report | Budget Execution | Adjusted FTE report | Adjusted FTE report | TBD | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | High | Must Have |  |  |  | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | The process to update FTEs is an offline process. The report will be discussed in in the Discovery phase for fit/gap analysis. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R134 | Report | Budget Execution | Approved vs Revised Budget report | Approved vs Revised Budget report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-11 | 2021-11-29 | 2021-11-29 | 2021-12-01 | 100% - Complete | 2021-11-11 | 2021-11-23 | 2021-11-29 | 2021-12-01 | 100% - Complete | 2022-01-07 | Approved | 2022-01-07 | 2021-11-24 | 2021-12-10 | 2021-12-01 | 2021-12-10 | 100% - Complete | 2021-11-30 | 2021-12-03 | 2021-12-01 | 2021-12-10 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R135 | Report | Budget Execution | DCPS Advance Report | DCPS Advance Report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2022-01-07 | Approved | 2022-01-07 | 2021-11-29 | 2021-12-17 | 2021-11-17 | 2021-12-10 | 100% - Complete | 2021-11-22 | 2021-12-10 | 2021-12-22 | 2021-12-30 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R136 | Report | Budget Execution | Expenditures by Month Report | Expenditures by Month Report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2022-01-07 | Approved | 2022-01-07 | 2021-11-29 | 2021-12-17 | 2021-11-17 | 2021-12-10 | 100% - Complete | 2021-11-29 | 2021-12-17 | 2021-12-22 | 2021-12-30 | 100% - Complete |  | RICE 3 |  |  |  | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
R137 | Report | Budget Execution | Historical Approved and Revised Budget and Expenditures report | Historical Approved and Revised Budget and Expenditures report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2022-01-07 | Approved | 2022-01-07 | 2021-11-29 | 2021-12-17 | 2021-11-17 | 2021-12-10 | 100% - Complete | 2021-11-29 | 2021-12-17 | 2021-12-22 | 2021-12-30 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R138 | Report | Budget Execution | Spending Plan Capital Report | Spending Plan Capital Report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-06 | 2021-09-17 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-09-06 | 2021-09-17 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-12-22 | Approved | 2021-12-22 | 2021-09-20 | 2021-10-08 | 2021-08-23 | 2021-09-09 | 100% - Complete | 2021-09-20 | 2021-10-08 | 2021-08-23 | 2021-09-10 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R139 | Report | Budget Execution | Spending Plan Report | Spending Plan Report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-31 | 100% - Complete | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-25 | 100% - Complete | 2021-12-22 | Approved | 2021-12-22 | 2021-08-23 | 2021-09-10 | 2021-09-06 | 2021-09-09 | 100% - Complete | 2021-09-20 | 2021-10-08 | 2021-08-23 | 2021-09-10 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R140 | Report | Budget to Report | Substitute Teachers Payroll Report | Substitute Teachers Payroll Report | TBD | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | Medium | Must Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R141 | Report | Budget to Report | Travel and Tuition Report | Travel and Tuition Report | TBD | EPM Cloud |  |  | Inbound | NA |  |  | NA | NA | Low | Could Have |  |  | Deloitte Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R142 | Report | Procure to Pay | Prior Year Cost Recovery Report | Prior Year Cost Recovery Report | Phase 1 | ERP Cloud | Sprint 11 |  | Inbound | NA |  |  | NA | NA | Medium | Could Have | Pandu Sadam | Sriniivas Kompalli | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 3-Build | -79 | In Review | 2021-12-01 | 2021-12-06 | 2021-12-20 | 2022-01-21 | 100% - Complete | 2021-12-08 | 2021-12-14 | 2022-01-24 | 2022-01-25 | 100% - Complete | 2022-01-25 | 1st Walkthrough Complete |  | 2022-02-16 | 2022-02-23 | 2022-01-25 |  | 75% - In Review | 2022-02-24 | 2022-02-28 | 2022-02-01 |  | 25% - In Progress |  | RICE 4 |  | 02/21/2022: Srini completed the build on PO side. Pandu is validating the report 02/17/2022:Srni to wrap up build for PO by end of business 02/15/2022: Work on Direct Invoice PO Match - connect with Rohan on Direct Invoices 02/10/2022: Technal build for PO portion completed. Invoice - 02/07/202: Srini working on the technical build 01/19/2022: hoping to transfer to technical this week 12/21/2021: New proposed start date 12/27/2021 - Initial requirements received 12/07/2021: Have not started - Pandu and Prasad will meet internally and we need to start moving this item | Unplanned | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 100 | 60 | 40 | 120 | 60 | 60
R143 | Report | Order to Cash | Cash Forecast Report | Cash Forecast Report | TBD | ERP Cloud | Sprint 10 | [5 empty] | NA | NA | Medium | Could Have | Chilakamarri, Srinivas | Raghav Goundaram | District Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [14 empty] | Unplanned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R144 | Report | Procure to Pay | Supplier Expiring Profile Attribute Report | Supplier Expiring Profile Attribute Report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Pandu Sadam | Devananda Panchumarty | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-29 | 2021-12-06 | 2021-12-03 | 2021-12-09 | 100% - Complete | 2021-12-20 | 2021-12-23 | 2021-12-15 | 2021-12-15 | 100% - Complete | 2022-02-07 | Approved | 2022-02-07 | 2021-12-24 | 2022-01-05 | 2021-12-24 | 2022-01-26 | 100% - Complete | 2022-01-06 | 2022-01-10 | 2022-01-21 | 2022-02-18 | 100% - Complete |  | RICE 4 |  | 02/17/2022: Pandu waiting for inputs on body of template and the email 02/15/2022: The comments from sprinting have been completed - confirm with Meg and Katrina what is getting proposed/team completed 02/10/202: Sprinted on 02/09/2022. Pnadu to update the specs based on inputs from the Sprint call 02/07/2022: Ready to be sprinted this week. 02/03/2022: Report build for email bursting - wip 02/01/2022: Report as is is ready - Confirmed BI Bursting for the email 01/25/2022: will complete R144 just as the report - maintenance admins can use to report on all suppliers and the CR for the notification has been created - can we use BI bursting or do we call it an 01/13/2022: Report build in Progress for the report part of the requirement |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R145 | Report | Procure to Pay | Supplier Invoices Report | Supplier Invoices Report | Phase 1 | ERP Cloud | Sprint 09 | [5 empty] | NA | NA | Medium | Must Have | Muralidhar Pedasanaganti | Percy Mangwiro | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-18 | 2021-10-27 | 2021-10-18 | 2021-10-22 | 100% - Complete | 2021-12-28 | 2022-01-04 | 2021-11-01 | 2021-11-12 | 100% - Complete | 2022-12-20 | approved | 2022-01-07 | 2022-01-05 | 2022-01-12 | 2021-11-22 | 2021-12-30 | 100% - Complete | 2022-01-13 | 2022-01-14 | 2022-01-03 | 2022-01-07 | 100% - Complete |  | RICE 4 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R146 | Report | Budget To Report | Employee/Position Budget vs Actuals Report |  | TBD | ERP Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R147 | Report | Budget Execution | FRP Report |  | Phase 1 | EPM Cloud | Sprint 09 | [5 empty] | NA | NA | Medium |  | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-23 | 2021-09-03 | 2021-08-23 | 2021-08-25 | 100% - Complete | 2021-08-23 | 2021-09-03 | 2021-08-23 | 2021-08-25 | 100% - Complete | 2021-12-22 | Approved | 2021-12-22 | 2021-09-06 | 2021-10-08 | 2021-09-06 | 2021-10-08 | 100% - Complete | 2021-09-06 | 2021-10-08 | 2021-10-08 | 2021-10-11 | 100% - Complete |  | RICE 3 |  | New report. To be rationalized. |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R148 | Report | Budget Formulation | PnG vs GL Budget Report |  | Phase 2 | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R149 | Report | Budget Execution | Perform Quality Control Check On Original Operating Budget |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | Process related | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R150 | Report | Budget Execution | Budget Adjustment Report | Budget Adjustment Report | Phase 1 | EPM Cloud | Sprint 09 | [5 empty] | NA | NA |  |  | Sid Gayam | Venkata NagaBhatla (Ravi) | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-12-02 | 2021-12-13 | 2021-12-06 | 2021-12-21 | 100% - Complete | 2021-12-27 | 2022-01-10 | 2021-12-27 | 2022-01-07 | 100% - Complete | N/A | N/A | N/A | 2022-01-11 | 2022-01-20 | 2022-01-06 | 2022-01-19 | 100% - Complete | 2022-01-21 | 2022-01-26 | 2022-01-20 | 2022-01-27 | 100% - Complete |  |  |  | New report. To be rationalized. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R151 | Report | Budget Execution | Process an Intra-District Budget Request |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | Process related | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R152 | Report | Budget Execution | Process an Emergency and Contingency Reserve Request |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | Process related | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R153 | Report | Budget Execution | Process a Section 103/803 Budget Request |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | Process related | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R154 | Report | Budget Execution | Process a Budget Allocation from a Central Account |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | Process related | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R155 | Report | Budget Execution | Process a Capital Budget Full Time Equivalent (FTE) Request |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | EPM Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R156 | Report | Budget Execution | Process an Education Advance/Forward Funding for Education Agencies |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | Process related | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R157 | Report | Budget Execution | Process an Initial Grant Budget Request |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | Process related | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R158 | Report | Budget Execution | Carryforward Report - LTD allotments, budgets, etc., by project, award | Carryforward Report - LTD allotments, budgets, etc., by project, award | TBD | EPM Cloud | Sprint 10 | [5 empty] | NA | NA |  |  | Sid Gayam | Venkata NagaBhatla (Ravi) | District Owned | Offtrack (Active) | Active | N/A | 3-Build | -98 | Approved | 2022-01-06 | 2022-01-14 | 2022-01-04 | 2022-01-24 | 100% - Complete | 2022-01-18 | 2022-01-26 | 2022-01-24 | 2022-01-27 | 100% - Complete | N/A | N/A | N/A | 2022-01-27 | 2022-02-04 |  |  |  | 2022-02-07 | 2022-02-11 | [6 empty] | CR 759830 has been approved by District - Descoping R158 as R085 will be used 02/14/2022: Will be descoped as per Kushan. Merged with R085. 2/7/2022: Transitioned to R085, planning to process a CR and descope it. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R159 | Report | Budget Execution | Prepare a Quarterly Grant Budget Modification and Activity Report to Congress |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | EPM Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R160 | Report | Budget Execution | Prepare a Quarterly Grant Lapse Report |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R161 | Report | Budget Execution | Review a Quarterly Financial Review Process Report |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | Process related | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R162 | Report | Budget Execution | Perform Quality Control Check on Original Capital Budget and Allotment |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R163 | Report | Budget Execution | Process a Request to Reallocate Budget between Phases of a Project or from a placeholder project |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | Process related | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R164 | Report | Budget Execution | Prepare a quartely capital FTE report to Congress |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | Process related | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R165 | Report | Budget To Report | Prepare a Quarterly Capital Financial Status Report (FSR) |  | TBD | ERP Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R166 | Report | Budget To Report | Process a Bond Requisition Report |  | TBD | ERP Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R167 | Report | Budget Execution | Prepare an Anti-Deficiency Act (ADA) Report to the Board of Review for Anti-Deficiency Violations (BRADV) for the Capital Improvements Program |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | EPM Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R168 | Report | Budget Execution | Prepare a Reprogramming Report to Council |  | Phase 1 | EPM Cloud | Sprint 09 | [5 empty] | NA | NA | High |  | Mia Kirkwood | Lui Bai | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-04 | 2021-10-15 | 2021-09-21 | 2021-10-15 | 100% - Complete | 2021-10-04 | 2021-10-15 | 2021-09-21 | 2021-10-15 | 100% - Complete | 2021-12-22 | Approved | 2021-12-22 | 2021-10-21 | 2021-11-10 | 2021-10-15 | 2021-11-10 | 100% - Complete | 2021-10-21 | 2021-11-10 | 2021-11-04 | 2021-12-03 | 100% - Complete |  | RICE 3 |  | New report. To be rationalized. |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R169 | Report | Budget Execution | Prepare a Quarterly Emergency and Contingency Cash Reserve Report |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R170 | Report | Budget Execution | Prepare a Quarterly Intra-District Report |  | Phase 1 | EPM Cloud | Sprint 09 | [5 empty] | NA | NA | High |  | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-11 | 2021-11-29 | 2021-11-29 | 2021-12-03 | 100% - Complete | 2021-11-11 | 2021-11-23 | 2021-11-29 | 2021-12-03 | 100% - Complete | 2022-02-04 | Approved | 2022-02-04 | 2021-11-24 | 2021-12-10 | 2021-12-01 | 2021-12-10 | 100% - Complete | 2021-11-30 | 2021-12-03 | 2021-12-01 | 2021-12-10 | 100% - Complete |  | RICE 3 |  | New report. To be rationalized. |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R171 | Report | Budget Formulation | Prepare the Five-Year Financial Plan |  | Phase 2 | EPM Cloud | [6 empty] | NA | NA | High |  |  |  | District Owned | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | 2021-12-14 | 2022-01-07 |  |  |  | 2021-12-14 | 2022-01-07 | [6 empty] | New report. To be rationalized. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R172 | Report | Budget Execution | Capital Reallocation Report | Capital Reallocation Report | Phase 1 | EPM Cloud | Sprint 10 | [5 empty] | NA | NA |  |  | Sid Gayam | Venkata NagaBhatla (Ravi) | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2022-01-06 | 2022-01-14 | 2022-01-04 | 2022-01-25 | 100% - Complete | 2022-01-18 | 2022-01-26 | 2022-01-24 | 2022-01-27 | 100% - Complete | N/A | N/A | N/A | 2022-01-27 | 2022-02-04 | 2022-01-27 | 2022-02-15 | 100% - Complete | 2022-02-07 | 2022-02-11 | 2022-02-15 | 2022-02-18 | 100% - Complete |  |  |  | 02/14/2022: Will be sprinted tomorrow. 2/7/2022: Planning to complete build, UTP and sprint in Sprint 10 New report. To be rationalized. | EPM Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R173 | Report | Budget Execution | Cy_Budget_Py_Budget_2021 |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | EPM Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R174 | Report | Budget Execution | Everything report used for CBT |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R175 | Report | Budget Formulation | FP Data - With Appr Title 771792fd |  | Phase 2 | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R176 | Report | Budget Execution | FY2020 app vs FY2021 Prop Budget and FTE variance report- with fund 581a8686 |  | TBD | EPM Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | EPM Unallocated | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R177 | Report | Budget To Report | LTD Budget Allotment. Expenditures.Encum and unspent balance by fund by phase ONE PROJECT ONLY |  | TBD | ERP Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R178 | Report | Budget To Report | LTD Budget Allotment. Expenditures.Encum and unspent balance by fund by phase |  | TBD | ERP Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R179 | Report | Budget To Report | LTD Budget Allotment. Expenditures.Encum and unspent balance by project Appendix D format |  | TBD | ERP Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R180 | Report | Budget To Report | LTD Expenditures - To be used for EOM Ward Reports |  | TBD | ERP Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R181 | Report | Budget To Report | Project Actuals and Encumbrance Transactions, by date of last activity per P.O. |  | TBD | ERP Cloud | [6 empty] | NA | NA | [5 empty] | N/A Not Scheduled | N/A Not Scheduled | N/A | 0-Not Started | -44694 | Approved | [10 empty] | N/A | N/A | N/A | [13 empty] | New report. To be rationalized. | New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R182 | Report | Budget To Report | Trial Balance Report | Trial Balance Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must have | Goel; Nidhi (OCFO-Contractor) | Narayan Ayyagari | District Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-03 | 2021-06-09 | 2021-06-01 | 2021-06-23 | 100% - Complete | 2021-06-10 | 2021-06-18 | 2021-06-15 | 2021-07-06 | 100% - Complete | N/A | N/A | N/A | 2021-06-21 | 2021-07-07 | 2021-06-23 | 2021-07-22 | 100% - Complete | 2021-07-08 | 2021-07-13 | 2021-07-26 | 2021-08-06 | 100% - Complete |  |  |  | Two R036 I think Trial Balance needs own number |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R183 | Report | Budget Execution | Commission Report - SPIN | sample report 15 - Commission Report | Phase 1 | EPM Cloud | Sprint 09 | [7 empty] | High | Must have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-12-22 | Approved | 2021-12-22 | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-09 | 100% - Complete | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-10 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R184 | Report | Budget Execution | Revenue Estimate comparison by revenue type and by certification period |  | Phase 1 | EPM Cloud | Sprint 09 | [7 empty] | High | Must have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-12-22 | Approved | 2021-12-22 | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-09 | 100% - Complete | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-10 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R185 | Report | Budget Execution | General purpose Non-Tax report | sample non-tax revenue report_April_2021 used as sample | Phase 1 | EPM Cloud | Sprint 09 | [7 empty] | Medium | Must have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-12-22 | Approved | 2021-12-22 | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-09 | 100% - Complete | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-10 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R186 | Report | Budget Execution | Paygo and Reverse Paygo budget changes |  | Phase 1 | EPM Cloud | Sprint 09 | [7 empty] | High | Must have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-04 | 2021-10-15 | 2021-09-21 | 2021-10-15 | 100% - Complete | 2021-10-04 | 2021-10-15 | 2021-09-21 | 2021-10-15 | 100% - Complete | 2021-12-22 | Approved | 2021-12-22 | 2021-10-21 | 2021-11-10 | 2021-10-18 | 2021-11-10 | 100% - Complete | 2021-10-21 | 2021-11-10 | 2021-11-04 | 2021-12-03 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R187 | Report | Budget Execution | Capital Projects without plan |  | Phase 1 | EPM Cloud | Sprint 10 | [7 empty] | High |  | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-12-13 | 2022-01-07 | 2021-12-15 | 2022-01-07 | 100% - Complete | 2021-12-14 | 2022-01-07 | 2021-12-15 | 2022-01-07 | 100% - Complete | 2022-02-02 | 2nd Submission | 2022-02-08 | 2021-12-14 | 2022-01-07 | 2021-12-14 | 2022-01-07 | 100% - Complete | 2021-12-14 | 2022-01-07 | 2021-12-14 | 2021-01-20 | 100% - Complete |  | RICE 4 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 125 | 200 | 75 | 125 | 200 | 75 | 125
R188 - Descope per CR 749850 | Report | Projects and Grants | P&G Billable Expenditures Report | P&G Billable Expenditures Report | TBD | ERP Cloud | [8 empty] | Medium | Must Have | Tej Mehta | Sriniivas Kompalli | Deloitte Owned | Offtrack (Active) | Active | N/A | 1-Functional Spec | -238 | Approved | 2021-09-13 | 2021-09-17 | 2021-09-22 |  | 75% - In Review | 2021-09-20 | 2021-09-24 |  |  |  | N/A | N/A | N/A | 2021-09-27 | 2021-10-06 |  |  |  | 2021-10-07 | 2021-10-08 | [6 empty] | R188 needs to be marked out of Scope (Phase TBD). 11/04/2021: Tej to get information from District Descoped per CR 749850 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R189 | Report | Budget Formulation | Spending Plans over $10M for all out years by Agency |  | Phase 2 | [9 empty] | Low | Should Have |  |  | District Owned |  | Active | N/A | 0-Not Started |  | Approved | 2021-12-13 | [9 empty] | N/A | N/A | N/A
R190 | Report | Procure To Pay | Prior year cost recovery | Prior year cost recovery | TBD | ERP Cloud | [9 empty] | Must Have | Pandu Sadam | Vijay Jampana | Deloitte Owned |  | Active | N/A | 0-Not Started |  | Approved | 2021-12-01 | 2021-12-06 |  |  |  | 2021-12-08 | 2021-12-14 |  |  |  | N/A | N/A | N/A | 2022-02-16 | 2022-02-23 |  |  |  | 2022-02-24 | 2022-02-28 | [6 empty] | Added per CR 740537 then discovered its duplicate of R142 Agree. If we already have one, we don’t need the 2nd one. Let us delete R190. | No | [10 empty] | 0 | 0 | 0
R191 | Report | Procure To Pay | Un-reconciled Pcards | Un-reconciled Pcards | Phase 1 | ERP Cloud | Sprint 11 | [8 empty] | Must Have | Subrah Gorti | Krishna Aravapalli | District Owned | Offtrack (Active) | Active | 5-Complete | 1-Functional Spec | -102 | Approved | 2022-01-19 | 2022-01-31 | 2022-01-21 |  | 50% - In Progress | 2022-02-07 | 2022-02-19 |  |  |  | N/A | N/A | N/A | 2022-02-21 | 2022-03-02 |  |  |  | 2022-03-03 | 2022-03-08 | [6 empty] | 02/14/2022: Scheduled to complete Functional and Technical spec this week. 2/7/2022: Functional will be completed this week CR 740537 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R192 | Report | Procure To Pay | Suppliers registrations pending approval | Suppliers registrations pending approval | Phase 1 | ERP Cloud | Sprint 11 | [8 empty] | Must Have | Subrah Gorti | Krishna Aravapalli | District Owned | Offtrack (Active) | Active | 5-Complete | 1-Functional Spec | -102 | Approved | 2022-01-19 | 2022-01-31 | 2022-01-21 |  | 75% - In Review | 2022-02-07 | 2022-02-19 |  |  |  | N/A | N/A | N/A | 2022-02-21 | 2022-03-02 |  |  |  | 2022-03-03 | 2022-03-08 | [6 empty] | 02/14/2022: Scheduled to complete Functional and Technical spec this week. 2/7/2022: Functional will be completed this week CR 740537 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R193 | Report | Projects and Grants | P&G Unlinked Projects Report | P&G Unlinked Projects Report | Phase 1 | ERP Cloud | Sprint 09 | [7 empty] | Medium |  | Tej Mehta | Seshadri K | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-11-29 | 2021-12-03 | 2021-11-29 | 2021-12-02 | 100% - Complete | 2021-12-06 | 2021-12-15 | 2021-12-06 | 2021-12-09 | 100% - Complete | 2022-01-11 | Approved | 2022-01-11 | 2021-12-16 | 2022-01-07 | 2021-12-16 | 2021-12-23 | 100% - Complete | 2022-01-10 | 2022-01-12 | 2021-12-23 | 2022-01-01 | 100% - Complete |  | RICE 3 | Sprinted | CR 747367 |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 120 | 60 | 60 | 120 | 60 | 60
R194 | Report | Procure to Pay | DIFS Purchase Orders and Requisitions Changed at Year End | As Procurement Officer, I want the ability to identify all purchasing transactions adjusted as part of the year-end closing process so that it can be provide to OCP/PASS in an agreed up reporting format. | Phase 1 | ERP Cloud | Sprint 11 |  | Inbound | NA |  |  |  |  | Medium | Must Have | Sravana Atmakuru | Vijay Jampana | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 1-Functional Spec | -77 | #N/A | 2022-02-21 | 2022-02-25 | 2022-02-03 |  | 50% - In Progress | 2022-02-28 | 2022-03-04 |  |  |  | #N/A | #N/A | #N/A | 2022-03-07 | 2022-03-11 |  |  |  | 2022-03-14 | 2022-03-18 |  |  |  |  | RICE 4 |  | 02/01/2022: Keenan will draft and send to Sravana |  | 25 | 35 | 50 | 10 | 120 | 60 | 60 | 12.5 | 12.5 | 0 | 120 | 60 | 60
R195 | Report | Projects and Grants | DDOT FHWA Billing Text File | Provide the text file needed to transmit the weekly bill from DDOT to FHWA. In addition, the data used to create the text file needs to be captured in a template that will populate fields needed to record cash receipts on the large weekly FHWA bill. | Phase 1 | ERP Cloud | Sprint 11 | [7 empty] | Low | Must Have | Tej Mehta | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2022-02-21 | 2022-02-25 | 2022-02-14 | 2022-02-14 | 100% - Complete | 2002-02-21 | 2002-02-25 | 2002-02-14 | 2002-02-15 | 100% - Complete |  |  |  | 2022-02-16 | 2022-02-28 | 2022-02-16 | 2022-02-17 | 100% - Complete | 2022-02-14 | 2022-02-21 | 2022-02-16 | 2022-02-18 | 100% - Complete |  |  |  | 02/18/2022: Walk through completed and spec sent for District Approval 02/17/2022: Build completed on 02/16/2022. Testing in Progress. | yes | 15 | 15 | 30 | 5 | 65 | 30 | 35 | 65 | 30 | 35 | 65 | 30 | 35
Formulas:
Last Review update Date = IF(OR('RICEW Master'!$[Deloitte/District Owned]="District Owned", 'RICEW Master'!$[Phase]<>"Phase 1"), "N/A",IF(VLOOKUP('RICEW Master'!$[RICE ID],'WP Review Status'!$A2:H2988,8,FALSE)=0,"",VLOOKUP('RICEW Master'!$[RICE ID],'WP Review Status'!$A2:H2988,8,FALSE)))
Planned Technical Build Start Date = WORKDAY('RICEW Master'!$[Planned Technical Specification End Date],1)
Planned Technical Build End Date = WORKDAY('RICEW Master'!$[Planned Technical Build Start Date],10)
Note on R5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add a column Deloitte Owned District Owned Deloitte Response: Column inserted with the above options
Note on U5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add a LAST column Sprinted Tested Deployed Deloitte Response: Added "Overall Status" column right before Comments column with noted drop-down options
Note on AS5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unit Testing Deloitte Response: Columns AJ-AN reflect Unit Testing
Note on AW5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: adding a general comments and last update column would allow functional and technical owners to provide an update on each RICEF object, providing additional visibility to the PMO and other DIFS stakeholders. Deloitte Response: ACCEPT - We have added the Comments column as suggested to capture any additional information required. The Last Updated Column can be captured through the version history of the document. With Multiple resources updating the RICE tracker at different points of time, it may become cumbersome and may not always reflect the correct last updated date. This is also caputured via "Current State" column that reflects the latest status of the object.

## Sheet3 (hidden)
RICE ID | Process Area | Type | Phase | Description | Status | Next Step With | Max Date | Number of Days | Complexity | # of Days | Tech Spec Completion | Tech Spec Status | Pre-Review | First Walkthru Meeting | Review Lean Spec(Date send to Dist) | Received F/B from District | Update Lean spec(Date send for Approval) | 2nd Round F/B from District | Second Review of Lean spec(In-person meeting) | Final Updates(Sent to District for Approval) | >3 Submission | Latest > 3rd Submission Date | Approval | Status2 | Status3 | Approval Date Differs | Comments | 3rd Submission | Revisions and Details | POC -Del Functional | POC - Del Technical | Notes | Days Review
R008 | Acquire to Retire | Report | Phase 1 | Multi Funded Assets Report | Specification Ready | Deloitte | 2021-12-13 | 3 | Medium |  | 2021-12-13 | 100% - Complete | [11 empty] | Specification Ready |  | TRUE
R004 | Acquire to Retire | Report | Phase 1 | Capital Invoice Reconciliation Report | Specification Ready | Deloitte | 2021-12-09 | 7 | Medium |  | 2021-12-09 | 100% - Complete | [11 empty] | Specification Ready |  | TRUE
R144 | Procure to Pay | Report | Phase 1 | Supplier Expiring Profile Attribute Report | Specification Ready | Deloitte | 2021-12-15 | 1 | Medium |  | 2021-12-15 | 100% - Complete | [11 empty] | Specification Ready |  | TRUE
R144 | Procure to Pay | Report | Phase 1 | Supplier Expiring Profile Attribute Report | Specification Ready | Deloitte | 2021-12-15 | 1 | Medium |  | 2021-12-15 | 100% - Complete | [11 empty] | Specification Ready |  | TRUE
I119 | Budget to Report | Interface | Phase 1 | DOES - GL Data | Specification Ready | Deloitte | 2021-12-16 | 0 | Medium |  | 2021-12-16 | 100% - Complete | [11 empty] | Specification Ready |  | TRUE
I037 | Procure to Pay | Interface | Phase 1 | CFSA Faces - Child Care Provider Payment | Specification Ready | Deloitte | 2021-12-10 | 6 | High |  | 2021-12-10 | 100% - Complete | [11 empty] | Specification Ready |  | TRUE

## WP Review Status (hidden)
|  |  |  | DO NOT UPDATE | 2022-05-13 | [7 empty] | Remove? | if date in past, Occurred, In Future , Scheduled | Submitted | Received | 2n Submission | 2nd Feedback | 2nd Meeting | 3rd Submission |  |  | Approval
RICE ID | Process Area | Type | Phase | Description | Status | Next Step With | Max Date | Number of Days | Complexity | # of Days | Tech Spec Completion | Tech Spec Status | Pre-Review | First Walkthru Meeting | Review Lean Spec(Date send to Dist) | Received F/B from District | Update Lean spec(Date send for Approval) | 2nd Round F/B from District | Second Review of Lean spec(In-person meeting) | Final Updates(Sent to District for Approval) | >3 Submission | Latest > 3rd Submission Date | Approval | Status2 | Status3 | Approval Date Differs | Comments | 3rd Submission | Revisions and Details | POC -Del Functional | POC - Del Technical | Notes | Days Review
C001 | Procure to Pay | Conversion | Phase 1 | Suppliers | Approved | N/A | 2021-04-26 | N/A | Very High |  | 2021-03-08 | 100% - Complete | 2021-03-08 | 2021-03-11 | 2021-04-23 | [7 empty] | 2021-04-26 | Approved | 2021-04-26 | TRUE |  |  | 1st approval - 12-APR 2nd Approval - 26-APR | Prasad | Divya Y
C002 | Order to Cash | Conversion | Phase 1 | Customers | Approved | N/A | 2020-10-14 | N/A | Medium |  | 2020-10-09 | 100% - Complete |  | 2020-10-13 | [8 empty] | 2020-10-14 | Approved | 2020-10-14 | TRUE
C003 | Budget to Report | Conversion | Phase 1 | General Ledger Budget Balances | Approved | N/A | 2021-12-01 | N/A | High |  | 2020-11-15 | 100% - Complete |  | 2021-11-30 | 2021-11-30 | [7 empty] | 2021-12-01 | Approved | 2021-12-01 | TRUE | Email confirmation on Dec 1st
C004 | Projects and Grants | Conversion | Phase 1 | Projects | Approved | N/A | 2021-11-10 | N/A | Medium |  | 2020-10-23 | 100% - Complete |  | 2021-11-05 | 2021-11-09 | [7 empty] | 2021-11-10 | Approved | 2021-11-10 | TRUE | email confirmation on NOV 10th
C005 | Projects and Grants | Conversion | Phase 1 | Project Tasks | Approved | N/A | 2020-10-27 | N/A | Medium |  | 2020-10-23 | 100% - Complete |  | 2020-10-26 | [8 empty] | 2020-10-27 | Approved | 2020-10-27 | TRUE
C006 | Projects and Grants | Conversion | Phase 1 | Awards | Approved | N/A | 2020-11-18 | N/A | Medium |  | 2020-10-30 | 100% - Complete | 2020-11-12 |  | 2020-11-16 | 2020-11-16 | 2020-11-17 | [5 empty] | 2020-11-18 | Approved | 2020-11-18 | TRUE | email confirmation on Nov18th
C007 | Projects and Grants | Conversion | Phase 1 | Project Budgets | Approved | N/A | 2021-03-10 | N/A | Medium |  | 2021-02-24 | 100% - Complete |  | 2021-03-04 | 2021-03-04 | [7 empty] | 2021-03-10 | Approved | 2021-03-10 | TRUE | Email confirmation on Mar 10th
C008 | Procure to Pay | Conversion | Phase 1 | Requisitions | Approved | N/A | 2021-05-24 | N/A | High |  | 2021-05-14 | 100% - Complete | 2021-04-14 | 2021-04-19 | 2021-04-22 |  | 2021-04-26 | 2021-05-12 |  | 2021-05-21 |  |  | 2021-05-24 | Approved | 2021-05-24 | TRUE |  | 2021-05-10 | 3rd Submission - 17-MAY F/B - 19-May 4th Submission - 21 - May Final Approval - 24-MAY | Prasad | Divya Y
C009 | Procure to Pay | Conversion | Phase 1 | Purchase Orders | Approved | N/A | 2021-06-28 | N/A | High |  | 2021-04-21 | 100% - Complete |  | 2021-04-22 | 2021-05-07 |  | 2021-05-07 |  | 2021-06-18 |  |  |  | 2021-06-28 | Approved | 2021-06-28 | TRUE |  |  | 2nd Walkthru - 28 APR Refunds design finalization delay occurred 4th Submission - 6 JUL Final Approval - 14 JUL
C010 | Procure to Pay | Conversion | Phase 1 | PO Receipts | Approved | N/A | 2021-07-06 | N/A | High |  | 2021-05-07 | 100% - Complete |  | 2021-05-13 | 2021-05-24 |  | 2021-06-25 |  | 2021-06-30 |  |  |  | 2021-07-06 | Approved | 2021-07-06 | TRUE |  |  | 1st submission for review - 12 May 4th Submission - 16 JUL Approval - 16th JUL
C012 | Acquire to Retire | Conversion | Phase 1 | Fixed Asset Mass Additions | Approved | N/A | 2021-10-15 | N/A | High |  | 2021-09-01 | 100% - Complete | 2021-08-31 | 2021-09-01 | 2021-09-14 | 2021-09-21 | 2021-10-11 | 2021-10-12 |  | 2021-10-15 |  |  | 2021-10-15 | Approved | 2021-10-15 | TRUE
C013 | Order to Cash | Conversion | Phase 1 | Customers' Open Invoices | Approved | N/A | 2021-08-06 | N/A | High |  | 2021-07-21 | 100% - Complete | 2021-07-21 | 2021-07-27 | 2021-07-30 | 2021-08-03 | 2021-08-04 | [5 empty] | 2021-08-06 | Approved | 2021-08-06 | TRUE |  |  | Approved - 06AUG | Andrew | Adil | Submission due from deloitte
C014 | Projects and Grants | Conversion | Phase 1 | Project Costs | Approved | N/A | 2021-03-08 | N/A | High |  | 2021-02-24 | 100% - Complete | 2021-03-04 | 2021-03-04 | 2021-03-04 | [7 empty] | 2021-03-08 | Approved | 2021-03-08 | TRUE | Email confirmation on Mar 10th
C015 | Projects and Grants | Conversion | Phase 1 | Project & Grants Billing events | Approved | N/A | 2021-06-23 | N/A | Medium |  | 2021-06-07 | 100% - Complete |  | 2021-06-07 | 2021-06-09 |  | 2021-06-22 |  | 2021-06-23 |  |  |  | 2021-06-23 | Approved | 2021-06-23 | TRUE | Email confirmation on 23rd Jun |  | Approval - 23rd JUL
C016 | Projects and Grants | Conversion | Phase 1 | Project & Grants Revenue events | Approved | N/A | 2021-07-23 | N/A | High |  | 2021-06-07 | 100% - Complete |  | 2021-06-07 | 2021-06-09 |  | 2021-06-22 |  | 2021-06-23 |  |  |  | 2021-07-23 | Approved | 2021-07-23 | TRUE |  |  | Approval - 23rd JUL
C017 | Order to Cash | Conversion | Phase 1 | AR Receipts | Approved | N/A | 2021-07-12 | N/A | Medium |  | 2021-06-11 | 100% - Complete |  | 2021-06-17 | 2021-06-17 |  | 2021-06-25 |  | 2021-06-29 |  |  |  | 2021-07-12 | Approved | 2021-07-12 | TRUE | Email confirmation on Jul 12th |  | Approval - 12th Jul
C018 | Budget to Report | Conversion | Phase 1 | GL Balances | Approved | N/A | 2021-11-20 | N/A | Medium |  | 2020-11-06 | 100% - Complete | 2021-11-17 | 2021-11-19 | 2021-11-20 |  | 2021-11-20 | [5 empty] | 2021-11-20 | Approved | 2021-11-20 | TRUE | Email confirmation on Nov 20th
C019 | Procure to Pay | Conversion | Phase 1 | Supplier Bank Account, Assignment and External Payee | Approved | N/A | 2021-04-01 | N/A | Very High |  | 2021-03-15 | 100% - Complete |  | 2021-03-23 | 2021-03-30 | [7 empty] | 2021-04-01 | Approved | 2021-04-01 | TRUE | Email confirmation on Apr 1st
C020 | Budget | Conversion | Phase 1 | General Ledger Budget Balances (BFA to EPM) | Approved | N/A | 2022-01-07 | N/A | Low |  | 2021-12-03 | 100% - Complete | 2021-12-02 | 2021-12-06 | 2021-12-07 | 2021-12-17 | 2021-12-20 | [5 empty] | 2022-01-07 | Approved | 2022-01-07 | TRUE
E001 | Procure to Pay | Extension | Phase 1 | Liability Offsets | 1st Walkthrough Complete | Deloitte | 2022-02-18 | 84 | Very High |  | 2022-01-14 | 100% - Complete |  | 2022-02-18 | [9 empty] | 1st Walkthrough Complete |  | TRUE
E002 | Projects and Grants | Extension | Phase 1 | Funding Patterns | Approved | N/A | 2021-10-07 | N/A | Very High |  | 2021-09-08 | 100% - Complete | 2021-09-14 | 2021-09-16 | 2021-09-21 | 2021-09-28 | 2021-10-05 |  | 2021-09-24 | 2021-10-07 |  |  | 2021-10-07 | Approved | 2021-10-07 | TRUE
E003 | Budget To Report | Extension | Phase 1 | Legacy Crosswalk Generation | Approved | N/A | 2021-11-09 | N/A | Very High |  | 2021-11-09 | 100% - Complete | [10 empty] | 2021-11-09 | Approved | 2021-11-09 | TRUE
E004 | Projects and Grants | Extension | Phase 1 | P&G Hold Unpaid Expenses for Billing | Approved | N/A | 2022-02-15 | N/A | Medium |  | 2022-01-26 | 100% - Complete |  | 2022-02-04 | 2022-02-04 |  |  |  |  | 2022-02-11 |  |  | 2022-02-15 | Approved | 2022-02-15 | TRUE
E005 | Order to Cash | Extension | Phase 1 | The Receivables Invoice Segregation of Duty Page Customization | Walkthrough Scheduled | Deloitte | 2022-02-24 | 78 | Medium |  | 2022-01-21 | 100% - Complete | 2022-02-18 | 2022-02-24 | [9 empty] | Walkthrough Scheduled |  | TRUE
E006 | Projects and Grants | Extension | Phase 1 | P&G Receipt Accrual Extension | Specification Ready | Deloitte | 2022-02-04 | 98 | Medium |  | 2022-02-04 | 100% - Complete | [11 empty] | Specification Ready |  | TRUE
I001 | Budget To Report | Interface | Phase 1 | PeopleSoft - Payroll Costs | Approved | N/A | 2021-07-11 | N/A | Medium |  | 2021-06-01 | 100% - Complete | 2021-06-09 | 2021-06-10 | 2021-07-11 | 2021-06-15 | 2021-06-24 | [5 empty] | 2021-06-24 | Approved | 2021-06-24 | TRUE | Email confirmation on Jun 25th
I004 | Budget To Report | Interface | Phase 1 | Peoplesoft - COA Data | Approved | N/A | 2021-05-18 | N/A | Medium |  | 2021-05-05 | 100% - Complete |  | 2021-05-04 | 2021-05-04 |  | 2021-05-17 | [5 empty] | 2021-05-18 | Approved | 2021-05-18 | TRUE |  |  | Approval - 18th May
I009 | Order To Cash | Interface | Phase 1 | iNOVAH - Cash Collection | Approved | N/A | 2021-12-02 | N/A | Medium |  | 2021-09-10 | 100% - Complete | 2021-09-22 | 2021-09-22 | 2021-10-19 | 2021-10-29 | 2021-11-18 | 2021-11-23 | 2021-11-23 | 2021-12-02 |  |  | 2021-12-02 | Approved | 2021-12-02 | TRUE
I010 | Order To Cash | Interface | Phase 1 | OFT DMS/DBC - Debt Service Payment Postings | Approved | N/A | 2021-11-23 | N/A | Medium |  | 2021-09-16 | 100% - Complete | 2021-09-26 | 2021-10-01 | 2021-10-08 | 2021-10-14 | 2021-11-10 | [5 empty] | 2021-11-23 | Approved | 2021-11-23 | TRUE
I011 | Order To Cash | Interface | Phase 1 | Banks - Bank Statements Reconciliation & ACH Return/Rejection File From Banks | Approved | N/A | 2022-01-06 | N/A | High |  | 2021-10-08 | 100% - Complete | 2021-09-22: 2021-11-22; 2021-10-19: 2021-12-08; 2021-10-29: 2021-12-14 |  |  | 2022-01-06 | Approved | 2022-01-06 | TRUE
I012 | Order To Cash | Interface | TBD | Kyriba - GL Posting Entries | N/A | Deloitte | 2022-01-06 | N/A | Medium |  | 2021-12-17 | 100% - Complete | 2021-09-22: 2022-01-06 |  |  |  | N/A | N/A | FALSE | on hold till Agency acccount process demo is complete; Andrew to update next week
I022 | Budget | Interface | Phase 1 | ERP - P&G Master & Award Data | Approved | N/A | 2021-08-17 | N/A | High |  | 2021-07-30 | 100% - Complete | 2021-07-29 | 2021-07-30 | 2021-08-11 | 2021-08-16 | 2021-08-17 | [5 empty] | 2021-08-17 | Approved | 2021-08-17 | TRUE |  |  | approved - 17-AUG
I023 | Budget | Interface | Phase 1 | ERP - Projects Actuals | Approved | N/A | 2021-08-25 | N/A | High |  | 2021-08-13 | 100% - Complete | 2021-08-09 | 2021-08-11 | 2021-08-13 | 2021-08-23 | 2021-08-23 | [5 empty] | 2021-08-25 | Approved | 2021-08-25 | TRUE |  |  | Approved - 25-AUG |  |  | due on 18-AUG
I024 | Budget | Interface | Phase 1 | ERP - Chart of Accounts | Approved | N/A | 2021-07-30 | N/A | Low |  | 2021-07-30 | 100% - Complete | [10 empty] | 2020-12-19 | Approved | 2020-12-19 | TRUE
I025 | Budget | Interface | Phase 1 | ERP - GL Actuals | Approved | N/A | 2021-07-30 | N/A | Low |  | 2021-07-30 | 100% - Complete | [10 empty] | 2021-03-26 | Approved | 2021-03-26 | TRUE
I026 | Budget | Interface | Phase 1 | Oracle Planning - Project Budget Requests | Approved | N/A | 2022-12-10 | N/A | High |  | 2021-11-26 | 100% - Complete | 2021-12-05 | 2021-12-06 | 2021-12-08 | 2022-12-10 | 2022-01-05 | 2022-01-10 | 2022-01-10 | 2022-01-11 |  |  | 2022-01-12 | Approved | 2022-01-12 | TRUE
I027 | Budget | Interface | Phase 1 | Oracle Planning - Approved GL Budget | Approved | N/A | 2021-10-21 | N/A | Low |  | 2021-10-21 | 100% - Complete | [10 empty] | 2021-10-21 | Approved | 2021-10-21 | TRUE
I030 | Projects and Grants | Interface | Phase 1 | Peoplesoft - Payroll Costs | Approved | N/A | 2021-06-24 | N/A | Medium |  | 2021-06-01 | 100% - Complete | 2021-09-22: 2021-06-10; 2021-10-19: 2021-06-15; 2021-11-18: 2021-06-24 |  |  | 2021-06-24 | Approved | 2021-06-24 | TRUE |  |  | Approval - 24th Jun
I031 | Projects and Grants | Interface | Phase 1 | PeopleSoft - Employee Data | Approved | N/A | 2021-05-18 | N/A | Medium |  | 2021-05-06 | 100% - Complete | 2021-09-22: 2021-05-06; 2021-10-19: 2021-05-06; 2021-11-18: 2021-05-17 |  |  | 2021-05-18 | Approved | 2021-05-18 | TRUE |  |  | Approval - 18th May
I033 | Acquire To Retire | Interface | Phase 1 | CARSS - Assets Extract | Approved | N/A | 2021-11-18 | N/A | Medium |  | 2021-10-01 | 100% - Complete | 2021-10-20 | 2021-10-21 | 2021-10-25 | 2021-10-27 | 2021-11-15 | [5 empty] | 2021-11-18 | Approved | 2021-11-18 | TRUE
I034 | Procure To Pay | Interface | Phase 1 | OSSE OECD - Day Care Grant Vendor Payment | Approved | N/A | 2021-10-18 | N/A | Medium |  | 2021-09-10 | 100% - Complete | 2021-09-22: 2021-09-20; 2021-09-22: 2021-09-21; 2021-10-19: 2021-10-13 |  |  | 2021-10-18 | Approved | 2021-10-18 | TRUE
I035 | Procure To Pay | Interface | Phase 1 | MMIS - Medicaid Vendor Payment | Approved | N/A | 2022-02-17 | N/A | High |  | 2022-01-14 | 100% - Complete |  | 2022-02-02 | 2022-02-07 | 2022-02-10 | 2022-02-10 | 2022-02-11 | 2022-02-14 | 2022-02-14 |  | 2022-02-14 | 2022-02-17 | Approved | 2022-02-17 | TRUE
I036 | Procure To Pay | Interface | Phase 1 | MMIS - Medicaid Vendor Payment Response | Approved | N/a | 2022-02-17 | N/A | Medium |  | 2022-01-14 | 100% - Complete |  | 2022-02-02 | 2022-02-07 | 2022-02-10 | 2022-02-10 | 2022-02-11 | 2022-02-14 | 2022-02-14 |  | 2022-02-14 | 2022-02-17 | Approved | 2022-02-17 | TRUE
I037 | Procure To Pay | Interface | Phase 1 | CFSA Faces - Child Care Provider Payment | Approved | N/A | 2022-01-28 | N/A | High |  | 2021-12-10 | 100% - Complete |  | 2021-01-14 | 2022-01-18 | 2022-01-24 | 2022-01-26 |  |  | 2022-01-28 |  |  | 2022-01-28 | Approved | 2022-01-28 | TRUE
I038 | Procure To Pay | Interface | Phase 1 | CFSA Faces - Child Care Provider Payment Response | Approved | N/A | 2022-01-28 | N/A | Medium |  | 2022-01-06 | 100% - Complete |  | 2021-01-14 | 2022-01-18 | 2022-01-24 | 2022-01-26 | 2022-01-28 | 2022-01-28 | 2022-01-28 |  |  | 2022-01-28 | Approved | 2022-01-28 | TRUE
I039 | Procure To Pay | Interface | Phase 1 | DDS RSA - Grant Vendor Payment | Approved | Deloitte | 2022-01-11 | N/A | Medium |  | 2021-09-17 | 100% - Complete | 2021-11-18 | 2021-11-19 | 2021-11-21 | 2021-11-29 | 2021-12-02 | 2021-12-06 |  |  |  |  | 2022-01-11 | Approved | 2022-01-11 | TRUE | Due by 6-DEC
I040 | Procure To Pay | Interface | Phase 1 | DDS RSA - Grant Vendor Payment Response | Approved | N/A | 2021-12-10 | N/A | Medium |  | 2021-09-27 | 100% - Complete | 2021-11-18 | 2021-11-19 | 2021-11-21 | 2021-11-29 | 2021-12-02 |  |  | 2021-12-08 |  |  | 2021-12-10 | Approved | 2021-12-10 | TRUE | Due by 6-DEC
I041 | Procure To Pay | Interface | Phase 1 | DMV Destiny- Refund of Traffic Fines | Approved | N/A | 2022-01-05 | N/A | Medium |  | 2021-09-24 | 100% - Complete | 2021-09-22: 2021-10-29; 2021-10-19: 2021-12-06; 2021-10-29: 2021-12-08; 2021-11-18: 2021-12-14 |  |  | 2022-01-05 | Approved | 2022-01-05 | TRUE | Discussion with DMV completed |  |  |  |  | Fayaz to have meeting with DMV to clarify error handling
I042 | Procure To Pay | Interface | Phase 1 | DMV Destiny- Refund of Traffic Fines Response | Approved | District | 2021-12-31 | N/A | Medium |  | 2021-09-29 | 100% - Complete |  | 2021-12-03 | 2021-12-10 | 2021-12-14 | 2021-12-22 | 2021-12-22 |  | 2021-12-23 |  |  | 2021-12-31 | Approved | 2021-12-31 | TRUE
I043 | Procure To Pay | Interface | Phase 1 | OFT - Unclaimed Property | Approved | N/A | 2021-10-29 | N/A | High |  | 2021-09-17 | 100% - Complete | 2021-10-17 | 2021-10-18 | 2021-10-25 | 2021-10-28 | 2021-10-28 | 2021-10-28 |  |  |  |  | 2021-10-29 | Approved | 2021-10-29 | TRUE
I044 | Procure To Pay | Interface | Phase 1 | OSSE ONEAPP - University Payments | Approved | N/A | 2021-08-17 | N/A | Medium |  | 2021-06-23 | 100% - Complete | 2021-06-24 | 2021-06-24 | 2021-06-25 | 2021-06-30 | 2021-08-11 |  | 2021-08-11 |  |  |  | 2021-08-17 | Approved | 2021-08-17 | TRUE |  |  | 13-Aug - Subrah wants an open item for the embedded deck - reprocess 17-AUG Approved | Prasad | Sri Hari
I045 | Procure To Pay | Interface | Phase 1 | OSSE ONEAPP - University Payments Response | Approved | N/A | 2021-09-03 | N/A | Medium |  | 2021-06-22 | 100% - Complete | 2021-06-24 | 2021-06-24 | 2021-06-25 | 2021-06-30 | 2021-06-30 |  | 2021-08-26 | 2021-09-03 |  |  | 2021-09-03 | Approved | 2021-09-03 | TRUE |  |  | Final approval with open items - 03 SEP 2021 | Sravana | Sri Hari
I046 | Procure To Pay | Interface | Phase 1 | OSSE NSCAPS - Nutrition Services Payment Request | Approved | N/A | 2021-08-19 | N/A | Medium |  | 2021-06-18 | 100% - Complete | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-25 | 2021-08-12 | 2021-08-16 | 2021-08-11 | 2021-08-18 |  |  | 2021-08-19 | Approved | 2021-08-19 | TRUE |  |  | 16-Aug - One additional comment by Subrah | Prasad | Sri Hari
I047 | Procure To Pay | Interface | Phase 1 | OSSE NSCAPS - Nutrition Services Payment Response | Approved | N/A | 2021-07-12 | N/A | Medium |  | 2021-06-24 | 100% - Complete | 2021-09-22: 2021-06-11; 2021-10-19: 2021-06-08; 2021-11-18: 2021-06-15; 2021-11-23: 2021-07-09 |  |  | 2021-07-12 | Approved | 2021-07-12 | TRUE |  |  | Approval - 12th Jul
I048 | Procure To Pay | Interface | Phase 1 | DOES - Employers Unemployment Contribution Refunds | Approved | N/A | 2021-08-30 | N/A | Medium |  | 2021-05-10 | 100% - Complete | 2021-05-11 | 2021-05-11 | 2021-06-08 | 2021-06-11 | 2021-06-22 | 2021-06-23 | 2021-08-02 | 2021-08-30 |  |  | 2021-08-30 | Approved | 2021-08-30 | TRUE | 2nd in-person meeting on Aug 13th | 2021-07-23 | Meeting with Subrah and Meg scheduled on 27-JUL since Meg was out Meeting held on 2-AUG, more comments provided Nirmala and Murali - provided all updates from comments recv'd during meeting Aug 13 - One to one meeting with Meg and Subrah - 1099 Aug 30 - Approved
I049 | Procure To Pay | Interface | Phase 1 | OSSE BITSEE- Special Education Not Encumbered Payment Requests | Approved | N/A | 2021-07-06 | N/A | Medium |  | 2021-05-14 | 100% - Complete | 2021-05-11: 2021-05-28; 2021-06-08: 2021-06-08; 2021-06-22: 2021-06-29; 2021-08-02: 2021-06-30 |  |  | 2021-07-06 | Approved | 2021-07-06 | TRUE | Email confirmation on Jul 20th |  | 4th Submission - District has open issues - conducted a meeting - 15th JUL 5th Submission - 20th JUL Approval on 20th JUL
I050 | Procure To Pay | Interface | Phase 1 | OSSE BITSEE- General and Special Education Payment Response | Approved | N/A | 2021-07-12 | N/A | Medium |  | 2021-06-04 | 100% - Complete | 2021-05-11: 2021-06-11; 2021-06-08: 2021-06-08; 2021-06-22: 2021-06-15; 2021-08-02: 2021-07-09 |  |  | 2021-07-12 | Approved | 2021-07-12 | TRUE |  |  | Approval - 12th Jul
I051 | Procure To Pay | Interface | Phase 1 | OSSE EGMS -Payment Request | Approved | N/A | 2021-09-28 | N/A | High |  | 2021-08-19 | 100% - Complete | 2021-08-19 | 2021-08-20 | 2021-08-25 | 2021-08-31 | 2021-09-02 | 2021-09-08 |  | 2021-09-16 |  |  | 2021-09-28 | Approved | 2021-09-28 | TRUE | 20-SEP sent to district 21- SEP came back with more comments
I052 | Procure To Pay | Interface | Phase 1 | MITS - State Income Liability Offset (SITLP) | Approved | N/A | 2021-07-27 | N/A | Very High |  | 2021-06-18 | 100% - Complete | 2021-05-11: 2021-06-30; 2021-06-08: 2021-07-09 |  |  | 2021-07-27 | Approved | 2021-07-27 | TRUE |  |  | Eric approved the final comment, Anu approved the Spec on 27Jul2021
I053 | Procure To Pay | Interface | Phase 1 | MITS - DC Vendor Offset | 1st Walkthrough Complete | Deloitte | 2022-02-18 | 84 | High |  | 2022-01-14 | 100% - Complete | 2021-05-11: 2022-02-18 |  |  |  | 1st Walkthrough Complete |  | TRUE
I054 | Procure To Pay | Interface | Phase 1 | MITS - DC Vendor Offset Response | 2nd Walkthrough Complete | Deloitte | 2022-02-18 | 84 | High |  | 2022-01-07 | 100% - Complete | 2021-05-11: 2022-02-18 |  |  |  | 2nd Walkthrough Complete |  | TRUE
I055 | Procure To Pay | Interface | Phase 1 | TOP - State Federal Liability Offset | 3rd Walkthrough Complete | Deloitte | 2022-02-18 | 84 | Very High |  | 2022-01-14 | 100% - Complete | 2021-05-11: 2022-02-18 |  |  |  | 3rd Walkthrough Complete |  | TRUE
I056 | Procure To Pay | Interface | Phase 1 | TOP - State Federal Liability Offset Response | 4th Walkthrough Complete | Deloitte | 2022-02-18 | 84 | High |  | 2022-01-07 | 100% - Complete | 2021-05-11: 2022-02-18 |  |  |  | 4th Walkthrough Complete |  | TRUE
I057 | Procure To Pay | Interface | Phase 1 | Banks - ACH Payments | Approved | N/A | 2022-02-07 | N/A | Medium |  | 2021-12-30 | 100% - Complete | 2022-01-20 | 2022-01-21 | 2022-01-24 | 2022-01-26 | 2022-02-04 |  |  | 2022-02-07 |  |  | 2022-02-07 | Approved | 2022-02-07 | TRUE
I058 | Procure To Pay | Interface | Phase 1 | Checkwrite - Warrant and Invoice file | 1st Walkthrough Complete | Deloitte | 2022-02-04 | 98 | High |  | 2022-01-28 | 100% - Complete | 2021-05-11: 2022-02-04 |  |  |  | 1st Walkthrough Complete |  | TRUE
I060 | Procure To Pay | Interface | Phase 1 | E-Risk - PSWCP Vendor Payments | Approved | N/A | 2021-09-29 | N/A | Medium |  | 2021-09-03 | 100% - Complete | 2021-09-02 | 2021-09-03 | 2021-09-08 | 2021-09-14 | 2021-09-27 | 2021-09-28 |  | 2021-09-29 |  |  | 2021-09-29 | Approved | 2021-09-29 | TRUE
I061 | Procure To Pay | Interface | Phase 1 | E-Risk - PSWCP Vendor Payment Response | Approved | N/A | 2021-12-10 | N/A | Medium |  | 2021-10-15 | 100% - Complete | 2021-11-12 | 2021-11-12 | 2021-11-15 | 2021-11-18 | 2021-11-22 | 2021-12-06 | 2021-12-09 | 2021-12-10 |  |  | 2021-12-10 | Approved | 2021-12-10 | TRUE | Extended dead line for review for Subrah and Meg - Dec 9th
I062 | Procure To Pay | Interface | Phase 1 | PeopleSoft - Payroll Tax Deductions | Approved | N/A | 2021-12-07 | N/A | Medium |  | 2021-06-24 | 100% - Complete | 2021-07-09 | 2021-07-09 | 2021-07-22 |  | 2021-07-23 |  | 2021-07-28 | 2021-12-02 |  |  | 2021-12-07 | Approved | 2021-12-07 | TRUE |  |  |  | Prasad |  | 752 transaction PS
I063 | Procure To Pay | Interface | Phase 1 | ERP - Supplier Master | Approved | N/A | 2021-09-28 | N/A | High |  | 2021-07-14 | 100% - Complete |  | 2021-07-16 | 2021-07-16 | 2021-07-21 | 2021-07-22 | 2021-07-28 | 2021-09-22 | 2021-09-24 |  |  | 2021-09-28 | Approved | 2021-09-28 | TRUE |  |  |  | Prasad | Lalitha
I065 | Procure To Pay | Interface | Phase 1 | Banks - PCard Allocation | Specification Ready | Deloitte | 2022-02-14 | 88 | Medium |  | 2022-02-14 | 100% - Complete | [11 empty] | Specification Ready |  | TRUE
I066 | Procure To Pay | Interface | Phase 1 | ARIBA OnPrem - ERP Create and Update (chg/cancel) Requisitions On Prem | 2nd Walkthrough Complete | Deloitte | 2022-02-17 | 85 | Very High |  | 2022-01-06 | 100% - Complete | 2021-11-12: 2022-01-25; 2021-11-15: 2022-02-04; 2021-12-09: 2022-02-17 |  |  |  | 2nd Walkthrough Complete |  | TRUE
I068 | Procure To Pay | Interface | Phase 1 | ARIBA OnPrem - ERP Create and Update Purchase Orders | 1st Walkthrough Complete | Deloitte | 2022-02-03 | 99 | Very High |  | 2022-01-28 | 100% - Complete | 2021-11-12: 2022-02-03 |  |  |  | 1st Walkthrough Complete |  | TRUE |  |  | Send to PASS team for confirmation on 23-SEP, Sreenath,Adi,Ajah,Maijo and Siva
I070 | Procure To Pay | Interface | Phase 1 | ARIBA OnPrem - ERP Create and Update Suppliers | Approved | N/A | 2021-06-30 | N/A | High |  | 2021-05-12 | 100% - Complete | 2021-11-12: 2021-05-12; 2021-11-15: 2021-05-13; 2021-11-22: 2021-05-17; 2021-12-09: 2021-06-25 |  |  | 2021-06-30 | Approved | 2021-06-30 | TRUE | Email confirmation on Jul 20th |  | 4th- Submission - 12-JUL 2nd meeting with District -16-JUL Final acceptance by Subrah - 19-JUL Approved by Anu - 19-JUL | Prasad | Phani | Functional design change delays
I073 | Procure To Pay | Interface | Phase 1 | ERP - ARIBA OnPrem Procurement Payment Status | Specification Ready | Deloitte | 2022-02-11 | 91 | High |  | 2022-02-11 | 100% - Complete | [11 empty] | Specification Ready |  | TRUE
I075 | Procure To Pay | Interface | Phase 1 | ERP- Ariba OnPrem Sync COA Master Data | N/A | N/A |  | N/A | Medium |  | 0 | 50% - In Progress | [11 empty] | N/A |  | TRUE
I080 | Budget To Report | Interface | TBD | ERP - CFO$OLVE/DW Master Data | N/A | N/A |  | N/A | Very High |  | 0 | 0 | [11 empty] | N/A | N/A | FALSE
I081 | Budget To Report | Interface | Phase 1 | ERP - CFO$OLVE/DW Transactional Data | 2nd Submission Feedback Received | Deloitte | 2022-01-11 | 122 | Very High |  | 2021-11-11 | 100% - Complete |  | 2021-12-15 | 2021-12-15 | 2022-01-04 | 2022-01-05 | 2022-01-11 | [5 empty] | 2nd Submission Feedback Received |  | TRUE
I082 | Budget To Report | Interface | Phase 1 | EPM - CFO$OLVE/DW Transactional & Master Data | Specification Ready | Deloitte | 2022-02-15 | 87 | Very High |  | 2022-02-15 | 100% - Complete | [11 empty] | Specification Ready |  | TRUE
I083 | Order To Cash | Interface | TBD | Kyriba - Transactions Cash Forecasting | N/A | N/A |  | N/A | Medium |  | 0 | 0 | [11 empty] | N/A | N/A | FALSE
I084 | Budget To Report | Interface | Phase 1 | DOES - Paid Family Leave (PFL) Benefit Program Accounting Entries | Approved | N/A | 2021-06-04 | N/A | Medium |  | 2021-05-12 | 100% - Complete | 2021-05-13 | 2021-05-17 | 2021-05-20 | 2021-05-25 | 2021-06-03 | [5 empty] | 2021-06-04 | Approved | 2021-06-04 | TRUE |  |  | Approval - 4th JUN Certain delays due to doc access issues for the DOES team
I085 | Procure To Pay | Interface | Phase 1 | DOES - Paid Family Leave (PFL) Benefit Program Employer Tax Refunds | Approved | N/A | 2021-08-30 | N/A | Medium |  | 2021-04-22 | 100% - Complete |  | 2021-04-23 | 2021-04-25 | 2021-05-06 | 2021-06-08 | 2021-06-23 | 2021-08-02 | 2021-08-30 |  |  | 2021-08-30 | Approved | 2021-08-30 | TRUE | 2nd in-person meeting on Aug 13th | 2021-07-16 | 16-JUL - one to one call with District 4th Submission - 22nd Jul Aug 5 - Murali submitted updated doc Aug 10- Back with more comments from Subrah and Meg Aug 13 - One to one meeting with Meg and Subrah - 1099 Aug 30 - Approved; Ms Bacon |  |  | On hold till Ms Bacon is back - 1099 issue
I086 | Procure To Pay | Interface | Phase 1 | PeopleSoft - Payroll Expenses (Vendor Payments) | Approved | N/A | 2021-10-27 | N/A | High |  | 2021-06-23 | 100% - Complete | 2021-07-09 | 2021-07-09 | 2021-07-22 | 2021-07-23 | 9/16/2021 - one to one discussion 20-SEP internal meeting ; updated spec send on 10/3 | 2021-10-05 | 2021-10-22 | 2021-10-27 |  |  | 2021-10-27 | Approved | 2021-10-27 | TRUE | 15-OCT -SOAR 752 trans updated 18-OCT - more comments came back 26-Oct another submission - confirmation from Meg/Subrah on 27th |  |  |  |  | Prasad and Nirmala
I087 | Procure To Pay | Interface | Phase 1 | ARIBA OnPrem - ERP Create and Update PO Receipts | Approved | N/A | 2021-12-31 | N/A | Very High |  | 2021-11-22 | 100% - Complete | 2021-09-02 | 2021-09-02 | 2021-09-08 | 2021-09-14 | 2021-11-30 | 2021-12-02 |  | 2021-12-23 |  |  | 2021-12-31 | Approved | 2021-12-31 | TRUE
I090 | Procure To Pay | Interface | Phase 1 | E-Invoice Portal - Create and Update Invoices | 1st Submission | District | 2022-02-07 | 95 | High |  | 2022-01-18 | 100% - Complete | 2021-11-12: 2022-01-26; 2021-11-12: 2022-01-27; 2021-11-15: 2022-02-07 |  |  |  | 1st Submission |  | TRUE
I091 | Projects and Grants | Interface | Phase 2 | DDOT - FMIS Budget Reallocation | N/A | N/A |  | N/A | Medium |  | 0 | 0 | [11 empty] | N/A | N/A | FALSE
I092 | Budget | Interface | Phase 1 | Oracle Planning - Approved Project Requests | Approved | N/A | 2021-08-18 | N/A | High |  | 2021-08-06 | 100% - Complete | 2021-11-12: 2021-08-09; 2021-11-12: 2021-08-11; 2021-11-15: 2021-08-13; 2021-11-18: 2021-08-18 |  |  | 2021-08-18 | Approved | 2021-08-18 | TRUE |  |  | Approved - 18-AUG
I095 | Technical | Interface | Phase 1 | Common Error Handling & Setup | Approved | N/A | 2021-06-17 | N/A | High |  | 2021-03-19 | 100% - Complete |  |  | 2021-05-03 | 2021-05-03 | 2021-05-09 | 2021-05-10 | 2021-05-10 | 2021-06-03 |  |  | 2021-06-17 | Approved | 2021-06-17 | TRUE | 17-May - another submission to District 17th May - Sean provided more comments Came back from District(Sean) with comments ; 6/3- Subrah confirmed; Vijay will confirm after the integration meeting This is APPROVED on 17-Jun-2021 with the following condition 1) Please add the following verbiage in Open Item 2) Please add the verbiage as an Action Item in PMC and let us know action item # Verbiage:- The Global Error Handling Framework Document will be designed to handle an End-to-End Error Handling Solution for the DIFS project: inclusive of Error Lifecycle for each DIFS System Component (OIC, DBCS, ERP, EPM and ODI). The error handler will address batch record processing and accommodate reprocessing of records if there failure in case of all or none scenario. It will ensure that batch processes must be restartable. Email confirmation on Jun6th
I096 | Technical | Interface | Phase 1 | DIFS Transformation Hub and Crosswalk | Approved | N/A | 2021-03-19 | N/A | High |  | 2021-03-19 | 100% - Complete | 2021-11-12: 2021-01-25 |  |  | 2021-02-01 | Approved | 2021-02-01 | TRUE
I107 | Budget To Report | Interface | Phase 1 | DOES - Payroll Data | Approved | N/A | 2021-06-04 | N/A | Medium |  | 2021-05-13 | 100% - Complete | 2021-05-13 | 2021-05-14 | 2021-05-14 | 2021-05-25 |  |  | 2021-06-03 |  |  |  | 2021-06-04 | Approved | 2021-06-04 | TRUE |  |  | Approval - 4th JUN Certain delays due to doc access issues for the DOES team
I108 | Procure To Pay | Interface | TBD | DIFS - ERP/PASS - Invoice Outbound | Approved | N/A | 2021-10-02 | N/A | Very High |  | 2021-08-13 | 100% - Complete | 2021-08-09 | 2021-08-13 | 2021-08-17 | 2021-08-20 | 2021-09-03 | 2021-09-09 | 2021-09-16 | 2021-09-30 |  |  | 2021-10-02 | Approved | N/A | FALSE |  |  |  | Zameer | Lalitha
I110 | Procure To Pay | Interface | Phase 1 | OFT - Unclaimed Property Response | Approved | N/A | 2022-01-11 | N/A | Medium |  | 2021-09-24 | 100% - Complete | 2021-08-13: 2021-12-03; 2021-08-17: 2021-12-10 |  |  | 2022-01-11 | Approved | 2022-01-11 | TRUE
I119 | Budget To Report | Interface | Phase 1 | DOES - GL Data | Approved | N/A | 2022-12-21 | N/A | Medium |  | 2021-12-16 | 100% - Complete | 12//16/2021 | 2021-12-17 | 2022-12-21 | 2022-01-04 | 2022-01-06 | 2022-01-06 | 2022-01-10 | 2022-01-12 | 2022-01-12 | 2022-01-12 | 2022-01-12 | Approved | 2022-01-12 | TRUE
I111 | Procure To Pay | Interface | Phase 1 | MMIS PDMS - Create and Update Vendors | Specification Ready | Deloitte | 2022-01-14 | 119 | High |  | 2022-01-14 | 100% - Complete | [11 empty] | Specification Ready |  | TRUE
I119 | Budget To Report | Interface | Phase 1 | DOES - GL Data | Approved | N/A | 2022-12-21 | N/A | Medium |  | 2021-12-16 | 100% - Complete | 2021-08-13: 2022-12-21 |  |  | 2022-01-12 | Approved | 2022-01-12 | TRUE
I120 | Procure To Pay | Interface | Phase 1 | DIFS - DOES Employer Unemployment Contribution Refund Payment Response | Approved | N/A | 2021-08-31 | N/A | Medium |  | 2021-08-06 | 100% - Complete | 2021-08-06 | 2021-08-10 | 2021-08-10 | 2021-08-12 | 2021-08-19 | 2021-08-23 | 2021-08-26 | 2021-08-27 |  |  | 2021-08-31 | Approved | 2021-08-31 | TRUE |  | 2021-08-27 | 2021-08-31 |  |  | 18-AUG close loop
I121 | Procure To Pay | Interface | Phase 1 | DIFS - EGMS Payment Response | Approved | N/A | 2021-12-10 | N/A | Medium |  | 2021-09-27 | 100% - Complete | 2021-11-12 | 2021-11-12 | 2021-11-15 | 2021-11-18 | 2021-11-23 | 2021-12-06 | 2021-12-09 | 2021-12-10 |  |  | 2021-12-10 | Approved | 2021-12-10 | TRUE | Extended dead line for review for Subrah and Meg - Dec 9th
I122 | Procure To Pay | Interface | Phase 1 | DIFS - DOES PFL Small Business Tax Refunds Payment Response | Approved | N/A | 2021-08-31 | N/A | Medium |  | 2021-08-06 | 100% - Complete | 2021-08-06 | 2021-08-10 | 2021-08-10 | 2021-08-12 | 2021-08-19 | 2021-08-23 | 2021-08-26 | 2021-08-27 |  |  | 2021-08-31 | Approved | 2021-08-31 | TRUE |  | 2021-08-27 | 2021-08-31
R002 | Acquire To Retire | Report | Phase 1 | Asset Register | Approved | N/A | 2021-11-12 | N/A | High |  | 2021-10-18 | 100% - Complete | 2021-08-06: 2021-10-19; 2021-08-10: 2021-10-20; 2021-08-10: 2021-10-20 |  |  | 2021-11-12 | Approved | 2021-11-12 | TRUE
R003 | Acquire To Retire | Report | Phase 1 | Asset Transaction Report | Approved | N/A | 2021-10-29 | N/A | Medium |  | 2021-10-21 | 100% - Complete | 2021-10-25 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | [5 empty] | 2021-10-29 | Approved | 2021-10-29 | TRUE | Email confirmation on Oct 29th
R004 | Acquire To Retire | Report | Phase 1 | Capital Invoice Reconciliation Report | Approved | N/A | 2022-02-04 | N/A | Medium |  | 2021-12-09 | 100% - Complete | 2021-08-10: 2021-12-17; 2021-08-10: 2021-12-17; 2021-08-27: 2022-01-19 |  |  | 2022-02-04 | Approved | 2022-02-04 | TRUE
R005 | Acquire To Retire | Report | Phase 1 | Category Reconciliation Report | Approved | N/A | 2021-11-12 | N/A | High |  | 2021-11-03 | 100% - Complete | 2021-08-06: 2021-10-26; 2021-08-10: 2021-10-28; 2021-08-10: 2021-10-28; 2021-08-12: 2021-11-01 |  |  | 2021-11-12 | Approved | 2021-11-12 | TRUE
R008 | Acquire To Retire | Report | Phase 1 | Multi Funded Assets Report | Approved | N/A | 2022-02-04 | N/A | Medium |  | 2021-12-13 | 100% - Complete | 2021-08-10: 2021-12-17; 2021-08-10: 2021-12-17; 2021-08-27: 2022-01-05 |  |  | 2022-02-04 | Approved | 2022-02-04 | TRUE
R019 | Budget To Report | Report | Phase 1 | Expenditure and revenue report | Approved | N/A | 2021-11-29 | N/A | High |  | 2021-08-16 | 100% - Complete | 2021-09-03 | 2021-09-10 | 2021-11-16 | 2021-11-19 | 2021-11-24 | [5 empty] | 2021-11-29 | Approved | 2021-11-29 | TRUE
R025 | Budget To Report | Report | Phase 1 | Budgetary Control Analysis Report | Approved | N/A | 2021-10-14 | N/A | High |  | 2021-08-19 | 100% - Complete | 2021-09-14 | 2021-09-16 | 2021-09-17 | 2021-09-22 | 2021-09-29 | 2021-10-03 |  |  |  |  | 2021-10-14 | Approved | 2021-10-14 | TRUE
R026 | Budget To Report | Report | Phase 1 | Chart of Account Profile Data Report | Approved | N/A | 2021-08-20 | N/A | High |  | 2021-08-06 | 100% - Complete | 2021-08-06: 2021-08-09; 2021-08-10: 2021-08-13; 2021-08-10: 2021-08-17; 2021-08-12: 2021-08-19 |  |  | 2021-08-20 | Approved | 2021-08-20 | TRUE |  |  | Approval - 20-Aug
R031 | Budget To Report | Report | Phase 1 | Subledger Reconciliation Report | Approved | N/A | 2021-12-01 | N/A | Medium |  | 2021-10-27 | 100% - Complete | 2021-11-03 | 2021-11-04 | 2021-11-11 | 2021-11-15 | 2021-11-23 | [5 empty] | 2021-12-01 | Approved | 2021-12-01
R033 | Projects and Grants | Report | TBD | Total Budget by fund for Capital Improvement Plan (CIP) (To be Descoped) | N/A | N/A |  | N/A | High |  | 0 | 0 | [11 empty] | N/A | N/A | FALSE
R037 | Interagency | Report | TBD | Intra-district budget dashboard | N/A | N/A |  | N/A | High |  | 0 | 0 | [11 empty] | N/A | N/A | FALSE
R041 | Order To Cash | Report | TBD | AR Statement Report | N/A | N/A |  | N/A | Medium |  | 0 | 0 | [11 empty] | N/A | N/A | FALSE
R046 | Order To Cash | Report | Phase 1 | Custom Sale of Assets - Revenue Report | Approved | N/A | 2022-01-21 | N/A | High |  | 2021-12-21 | 100% - Complete | 2021-08-10: 2022-01-05; 2021-08-10: 2022-01-07; 2021-08-19: 2022-01-20; 2021-08-27: 2022-01-20 |  |  | 2022-01-21 | Approved | 2022-01-21 | TRUE
R051 | Budget to Report | Report | Phase 1 | Journal Entry Detail report | Approved | N/A | 2021-07-30 | N/A | High |  | 2021-07-22 | 100% - Complete | 2021-08-10: 2021-07-16; 2021-08-10: 2021-07-19; 2021-08-19: 2021-07-27 |  |  | 2021-07-30 | Approved | 2021-07-30 | TRUE |  |  | 30-JUL approved |  |  | Due on 29-JUL
R053 | Order To Cash | Report | Phase 1 | Offset report | 1st Submission | District | 2022-02-15 | 87 | High |  | 2022-02-02 | 100% - Complete | 2021-08-06: 2022-02-09; 2021-08-10: 2022-02-11; 2021-08-10: 2022-02-15 |  |  |  | 1st Submission |  | TRUE
R054 | Order To Cash | Report | TBD | Receipt Detail report | Specification Ready | Deloitte | 2021-12-21 | 143 | High |  | 2021-12-21 | 100% - Complete | [11 empty] | Specification Ready | N/A | FALSE
R058 | Order To Cash | Report | Phase 1 | Transaction Details Report | Approved | N/A | 2021-10-26 | N/A | High |  | 2021-09-22 | 100% - Complete | 2021-09-23 | 2021-09-27 | 2021-09-28 | 2021-10-12 | 2021-10-13 | 2021-10-25 |  |  |  |  | 2021-10-26 | Approved | 2021-10-26 | TRUE
R062 | Procure To Pay | Report | Phase 1 | Custom 1099 payment data report | Approved | n/A | 2022-01-27 | N/A | Medium |  | 2022-01-20 | 100% - Complete | 2021-12-06 | 2021-12-08 |  | 2022-01-07 | 2022-01-12 | 2022-01-12 | 2022-01-19 | 2022-01-20 | 2022-01-25 | 2022-01-26 | 2022-01-27 | Approved | 2022-01-27 | TRUE
R064 | Procure To Pay | Report | Phase 1 | Custom Interactive PO Master Report | Final Submission | District | 2022-01-20 | 113 | High |  | 2021-12-23 | 100% - Complete | 2022-01-07 | 2022-01-07 | 2022-01-14 |  |  |  | 2022-01-20 | 2022-01-20 |  |  |  | Final Submission |  | TRUE
R068 | Procure To Pay | Report | Phase 1 | Custom payment offset report | N/A | N/A |  | N/A | High |  | 0 | 0 | [11 empty] | N/A |  | TRUE
R071 | Procure To Pay | Report | Phase 1 | Custom PO open balances report with accounting and aging | Approved | N/A | 2022-01-06 | N/A | High |  | 2021-09-07 | 100% - Complete | 2021-09-22 | 2021-09-24 | 2021-11-16 | 2021-11-19 |  |  |  | 2022-01-05 |  |  | 2022-01-06 | Approved | 2022-01-06 | TRUE
R072 | Procure To Pay | Report | Phase 1 | Custom spend report by supplier | Approved | N/A | 2021-10-05 | N/A | Medium |  | 2021-09-17 | 100% - Complete | 2021-09-22 | 2021-09-24 | 2021-09-24 | 2021-09-28 | 2021-09-30 | 2021-10-01 | 2021-10-01 |  |  |  | 2021-10-05 | Approved | 2021-10-05 | TRUE
R077 | Procure To Pay | Report | Phase 1 | Expense Report and P Card invoice details | N/A | N/A |  | N/A | Medium |  | 0 | 0 | [11 empty] | N/A |  | TRUE
R080 | Procure To Pay | Report | Phase 1 | Retainage Report | 1st Submission | District | 2022-01-28 | 105 | Low |  | 2022-01-11 | 100% - Complete | 2021-08-06: 2022-01-20; 2021-08-10: 2022-01-26; 2021-08-10: 2022-01-28 |  |  |  | 1st Submission |  | TRUE
R082 | Projects and Grants | Report | Phase 2 | Bond Reconciliation Report | Walkthrough Scheduled | Deloitte | 2021-12-13 | 151 | High |  | 0 | 0 | 2021-08-06: 2021-12-09; 2021-08-10: 2021-12-13 |  |  |  | Walkthrough Scheduled | N/A | FALSE | On hold for now -Tej
R085 | Projects and Grants | Report | Phase 1 | P&G LTD Balances Report | Approved | N/A | 2021-08-14 | N/A | High |  | 2021-08-02 | 100% - Complete | 2021-08-05 | 2021-08-06 | 2021-08-09 | 2021-08-13 | 2021-08-13 | [5 empty] | 2021-08-14 | Approved | 2021-08-14 | TRUE | Email confirmation on Aug 16th |  | approved- 16-Aug |  |  | Lean spec back by Aug 12
R095 | Projects and Grants | Report | TBD | Maintenance of Effort data extract | N/A | N/A |  | N/A | Medium |  | 0 | 0 | [11 empty] | N/A | N/A | FALSE
R097 | Projects and Grants | Report | Phase 1 | P&G Billable Report | Approved | N/A | 2021-10-04 | N/A | Medium |  | 2021-09-16 | 100% - Complete | 2021-09-17 | 2021-09-22 | 2021-09-23 | 2021-09-29 | 2021-09-29 | [5 empty] | 2021-10-04 | Approved | 2021-10-04 | TRUE
R098 | Projects and Grants | Report | Phase 1 | P&G to GL funds reconciliation report | Approved | N/A | 2021-08-25 | N/A | Medium |  | 2021-08-09 | 100% - Complete | 2021-08-10 | 2021-08-19 | 2021-08-19 | 2021-08-24 | 2021-08-24 | [5 empty] | 2021-08-25 | Approved | 2021-08-25 | TRUE |  |  | Approved - 25-AUG
R134 | Budget Execution | Report | Phase 1 | Approved vs Revised Budget report | Approved | District | 2022-01-07 | N/A | Medium |  | 2021-12-01 | 100% - Complete |  | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-22 | 2021-12-22 | 2021-12-22 |  |  |  | 2022-01-07 | Approved | 2022-01-07 | TRUE
R135 | Budget Execution | Report | Phase 1 | DCPS Advance Report | Approved | District | 2022-01-07 | N/A | High |  | 2021-11-16 | 100% - Complete | 2021-11-24 | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-22 | 2021-12-22 | 2021-12-22 |  |  |  | 2022-01-07 | Approved | 2022-01-07 | TRUE
R136 | Budget Execution | Report | Phase 1 | Expenditures by Month Report | Approved | District | 2022-01-07 | N/A | Low |  | 2021-11-16 | 100% - Complete | 2021-11-24 | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-22 | 2021-12-22 | 2021-12-22 |  |  |  | 2022-01-07 | Approved | 2022-01-07 | TRUE
R137 | Budget Execution | Report | Phase 1 | Historical Approved and Revised Budget and Expenditures report | Approved | District | 2022-01-07 | N/A | High |  | 2021-11-16 | 100% - Complete | 2021-11-24 | 2021-12-02 | 2021-12-03 | 2021-12-06 | 2021-12-22 | 2021-12-22 | 2021-12-22 |  |  |  | 2022-01-07 | Approved | 2022-01-07 | TRUE
R138 | Budget Execution | Report | Phase 1 | Spending Plan Capital Report | Approved | N/A | 2021-12-22 | N/A | Medium |  | 2021-08-20 | 100% - Complete | 2021-11-19 | 2021-11-21 | 2021-11-21 | 2021-11-23 | 2021-11-23 |  |  | 2021-12-20 |  |  | 2021-12-22 | Approved | 2021-12-22 | TRUE | Checked with Randall - they are checking each one.
R139 | Budget Execution | Report | Phase 1 | Spending Plan Report | Approved | N/A | 2021-12-22 | N/A | High |  | 2021-08-25 | 100% - Complete | 2021-11-19 | 2021-11-21 | 2021-11-21 | 2021-11-23 | 2021-11-23 |  |  | 2021-12-20 |  |  | 2021-12-22 | Approved | 2021-12-22 | TRUE | Checked with Randall - they are checking each one.
R142 | Procure to Pay | Report | Phase 1 | Prior Year Cost Recovery Report | 1st Walkthrough Complete | n/a | 2022-01-25 | 108 | Medium |  | 2022-01-25 | 100% - Complete | [11 empty] | 1st Walkthrough Complete |  | TRUE | Checked with Randall - they are checking each one.
R144 | Procure to Pay | Report | Phase 1 | Supplier Expiring Profile Attribute Report | Approved | N/A | 2022-02-07 | N/A | Medium |  | 2021-12-15 | 100% - Complete |  | 2022-01-05 | 2022-01-18 | 2022-01-21 | 2022-02-01 |  |  | 2022-02-04 |  |  | 2022-02-07 | Approved | 2022-02-07 | TRUE
R145 | Procure to Pay | Report | Phase 1 | Supplier Invoices Report | approved | N/A | 2022-12-20 | N/A | Medium |  | 2021-11-12 | 100% - Complete | 2021-11-19 | 2021-12-03 | 2021-12-07 | 2021-12-10 | 2022-12-16 | 2022-12-20 |  | 2022-01-05 |  |  | 2022-01-07 | approved | 2022-01-07 | TRUE
R147 | Budget Execution | Report | Phase 1 | FRP Report | Approved | N/A | 2021-12-22 | N/A | Medium |  | 2021-08-25 | 100% - Complete | 2021-11-19 | 2021-11-21 | 2021-11-21 | 2021-11-23 | 2021-11-23 |  |  | 2021-12-20 |  |  | 2021-12-22 | Approved | 2021-12-22 | TRUE | Checked with Randall - they are checking each one.
R168 | Budget Execution | Report | Phase 1 | Prepare a Reprogramming Report to Council | Approved | N/A | 2021-12-22 | N/A | High |  | 2021-10-15 | 100% - Complete | 2021-11-19 | 2021-11-21 | 2021-11-21 | 2021-11-23 | 2021-11-23 |  |  | 2021-12-20 |  |  | 2021-12-22 | Approved | 2021-12-22 | TRUE | Checked with Randall - they are checking each one.
R170 | Budget Execution | Report | Phase 1 | Prepare a Quarterly Intra-District Report | Approved | District | 2022-02-04 | N/A | High |  | 2021-12-03 | 100% - Complete | 2021-12-05 | 2021-12-06 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2021-12-22 | 2022-01-19 |  |  | 2022-02-04 | Approved | 2022-02-04 | TRUE
R183 | Budget Execution | Report | Phase 1 | Commission Report - SPIN | Approved | N/A | 2021-12-22 | N/A | High |  | 2021-08-20 | 100% - Complete | 2021-11-19 | 2021-11-21 | 2021-11-21 | 2021-11-23 | 2021-11-23 |  |  | 2021-12-20 |  |  | 2021-12-22 | Approved | 2021-12-22 | TRUE | Checked with Randall - they are checking each one.
R184 | Budget Execution | Report | Phase 1 | Revenue Estimate comparison by revenue type and by certification period | Approved | N/A | 2021-12-22 | N/A | High |  | 2021-08-20 | 100% - Complete | 2021-11-19 | 2021-11-21 | 2021-11-21 | 2021-11-23 | 2021-11-23 |  |  | 2021-12-20 |  |  | 2021-12-22 | Approved | 2021-12-22 | TRUE | Checked with Randall - they are checking each one.
R185 | Budget Execution | Report | Phase 1 | General purpose Non-Tax report | Approved | N/A | 2021-12-22 | N/A | Medium |  | 2021-08-20 | 100% - Complete | 2021-11-19 | 2021-11-21 | 2021-11-21 | 2021-11-23 | 2021-11-23 |  |  | 2021-12-20 |  |  | 2021-12-22 | Approved | 2021-12-22 | TRUE | Checked with Randall - they are checking each one.
R186 | Budget Execution | Report | Phase 1 | Paygo and Reverse Paygo budget changes | Approved | N/A | 2021-12-22 | N/A | High |  | 2021-10-15 | 100% - Complete | 2021-11-19 | 2021-11-21 | 2021-11-21 | 2021-11-23 | 2021-11-23 |  |  | 2021-12-20 |  |  | 2021-12-22 | Approved | 2021-12-22 | TRUE | Checked with Randall - they are checking each one.
R187 | Budget Execution | Report | Phase 1 | Capital Projects without plan | 2nd Submission | District | 2022-02-02 | 100 | High |  | 2022-01-07 | 100% - Complete | 2021-12-06: 2022-01-26; 2021-12-22: 2022-01-31; 2021-12-22: 2022-02-02; 2021-12-22: 2022-02-02 |  |  |  | 2nd Submission | 2022-02-08 | FALSE
R193 | Projects and Grants | Report | Phase 1 | P&G Unlinked Projects Report | Approved | N/A | 2022-01-11 | N/A | Medium |  | 2021-12-09 | 100% - Complete | 2021-12-09 | 2021-12-16 | 2021-12-16 | 2021-12-22 | 2021-12-22 | [5 empty] | 2022-01-11 | Approved | 2022-01-11 | TRUE
R195 | Projects and Grants | Report | #N/A | #N/A | 1st Submission | District | #N/A | #N/A | #N/A |  | #N/A | #N/A | 2021-12-05: 2022-01-15; 2021-12-06: 2022-02-18; 2021-12-22: 2022-02-18 |  |  |  | 1st Submission | #N/A | #N/A
Formulas:
Tech Spec Completion = VLOOKUP(Table224[[#This Row],[RICE ID]],'RICEW Master'!$A5:AJ339,35,FALSE)
Status3 = VLOOKUP(Table224[[#This Row],[RICE ID]],'RICEW Master'!$A5:AM339,39,FALSE)
Note on AB89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We request that the design be updated to include end-to-end error collection (as defined as from the beginning of interface processing through import into Oracle ERP). For completeness- here is our expectation for each interface method: • For Batch transactions, the errors should be consolidated back in the email attachment. • For sync, we request that you send the interface table error as applicable (i.e. not only if the custom code encounters an error we send but also if the ERP import transaction fails) back to the user. • For async, we request that you send the interface table error as applicable (i.e. not only if the custom code encounters an error we send but also if the ERP import transaction fails) back in the email. We believe that this design augmentation is critical because the current design places undo burden on the Tier3 support team to resolve any interface issues that have the potential to be resolved at the application functional level. Tier3 Application support errors typically have a longer time to resolution resulting in a degradation of customer service.
Note on R105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There could be a delay till Dec 1st since Meg and Subrah are out
Note on R120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delay since Meg and Subrah are out till Dec 1st

## WP PIVOT (hidden)
Status2 | (Multiple Items)
Type | (All)
Row Labels | Count of RICE ID
Deloitte | 15
1st Submission | 1
1st Walkthrough Complete | 4
2nd Walkthrough Complete | 1
Specification Ready | 6
2nd Submission Feedback Received | 1
Walkthrough Scheduled | 2
District | 5
1st Submission | 4
2nd Submission | 1
N/A | 1
1st Walkthrough Complete | 1
Grand Total | 21

## WP TO ADDRESS (hidden)
RICE ID | Object Type | Process Area | DIFS Object Name | Description | Phase | System | Sprint/Mock Cycle | Report/Interface Type | Report/Interface Direction | Update COA | ERP/EPM Object Type | System Owner | Source System | Target System | Complexity Level | Priority (MoSCoW) | Functional Owner | Technical Owner | Deloitte/District Owned | Current State (Not Started, Functional Specification, Technical Specification, District Review, Technical Build, Functional Testing, Complete) | Active? | Expected Phase | Current Phase | # Of Days Behind | Spec Status | Planned Functional Specification Start Date | Planned Functional Specification End Date | Actual Functional Specification Start Date | Actual Functional Specification End Date | Functional Specification Status | Planned Technical Specification Start Date | Planned Technical Specification End Date | Actual Technical Specification Start Date | Actual Technical Specification End Date | Technical Specification Status | District Work Product Review, Date Provided to District | WP Status | District Work Product Review, Date Approval Provided From District | Planned Technical Build Start Date | Planned Technical Build End Date | Actual Technical Build Start Date | Actual Technical Build End Date | Build Status | Planned Unit Test Start Date | Planned Unit Test End Date | Actual Unit Test Start Date | Actual Unit Test End Date | Unit Test Status | Received Actual Source File | Included in Phase/Milestone | Overall Status | Comments | In Scope | Func | Tech | Build | Unit | Estimated Total | Estimated Spec | Estimated Build/Unit | Actual Total | Actual Spec | Actual Build/Unit | Expected Total | Expected Spec | Expected Buil/Unit
R170 | Report | Budget Execution | Prepare a Quarterly Intra-District Report |  | Phase 1 | EPM Cloud | Sprint 09 | [5 empty] | NA | NA | High |  | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | Not Submitted | 2021-11-11 | 2021-11-29 | 2021-11-29 | 2021-12-03 | 100% - Complete | 2021-11-11 | 2021-11-23 | 2021-11-29 | 2021-12-03 | 100% - Complete |  | Specification Ready |  | 2021-11-24 | 2021-12-10 | 2021-12-01 |  | 25% - In Progress | 2021-11-30 | 2021-12-03 |  |  |  |  | RICE 3 |  | New report. To be rationalized. |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 100 | 75 | 25 | 156.25 | 75 | 81.25
R136 | Report | Budget Execution | Expenditures by Month Report | Expenditures by Month Report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | In Review | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-12-02 | 1st Walkthrough Complete |  | 2021-11-29 | 2021-12-17 | 2021-11-17 |  | 75% - In Review | 2021-11-29 | 2021-12-17 |  |  |  |  | RICE 3 |  |  |  | 15 | 15 | 30 | 5 | 65 | 30 | 45 | 52.5 | 30 | 22.5 | 37.7778 | 30 | 7.7778
R134 | Report | Budget Execution | Approved vs Revised Budget report | Approved vs Revised Budget report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | Not Submitted | 2021-11-11 | 2021-11-29 | 2021-11-29 | 2021-12-01 | 100% - Complete | 2021-11-11 | 2021-11-23 | 2021-11-29 | 2021-12-01 | 100% - Complete | 2021-12-02 | 1st Walkthrough Complete |  | 2021-11-24 | 2021-12-10 | 2021-12-01 |  | 25% - In Progress | 2021-11-30 | 2021-12-03 |  |  |  |  | RICE 3 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 72.5 | 60 | 12.5 | 98.125 | 60 | 38.125
R071 | Report | Procure to Pay | Custom PO open balances report with accounting and aging | Custom PO open balances report with accounting and aging | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Zemeer Padikkal | Vijay Jampana | Deloitte Owned | Offtrack (Active) | Active | 4-Unit Test | 3-Build | -46 | In Review | 2021-07-19 | 2021-07-30 | 2021-07-19 | 2021-08-18 | 100% - Complete | 2021-07-29 | 2021-08-20 | 2021-08-02 | 2021-09-07 | 100% - Complete | 2021-11-29 | 1st Submission Feedback Received |  | 2021-09-07 | 2021-10-18 | 2021-09-07 |  | 75% - In Review | 2021-10-19 | 2021-10-22 |  |  |  |  | RICE 3 |  | 10/21/21: Spec changed again;Submitted to District for approval on 11/29 due by 12/2; most of the comments were from Subrah as he is OOO till Dec 3rd reached out to Narayan |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 150 | 75 | 75 | 200 | 75 | 125
R064 | Report | Procure to Pay | Custom Interactive PO Master Report | Custom Interactive PO Master Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Pandu | Percy Mangwiro | Deloitte Owned | Offtrack (Active) | Active | 4-Unit Test | 3-Build | -46 | Not Submitted | 2021-09-06 | 2021-09-15 | 2021-09-06 | 2021-10-04 | 100% - Complete | 2021-09-23 | 2021-10-01 | 2021-09-28 | 2021-10-01 | 100% - Complete |  | Specification Ready |  | 2021-09-29 | 2021-10-18 | 2021-09-29 |  | 50% - In Progress | 2021-10-20 | 2021-10-26 |  |  |  |  | RICE 3 |  | 09/30/2021: Still in discussion |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 125 | 75 | 50 | 200 | 75 | 125
I087 | Interface | Procure to Pay | ARIBA OnPrem - ERP Create and Update PO Receipts | Create and Update PO Receipts in ERP from Ariba OnPrem. On-Prem ARIBA to ERP will be only inbound as per current ARIBA-SOAR implementation. | Phase 1 | ERP Cloud | Sprint 10 | Online | Inbound | Y | Create and Update PO Receipts | OCP | ARIBA-OnPrem | ERP | Very High |  | Sravana Atmakuru | Phani Vajjhala | Deloitte Owned | Ontrack (Active) | Active | 4-Unit Test | 4-Unit Test | N/A | In Review | 2021-06-18 | 2021-06-24 | 2021-07-15 | 2021-08-02 | 100% - Complete | 2021-08-12 | 2021-10-27 | 2021-08-12 | Date | 100% - Complete | 2021-11-30 | 1st Submission Feedback Received |  | 2021-10-28 | 2021-11-18 | 2021-09-01 | 2021-09-24 | 100% - Complete | 2021-09-29 | 2021-12-22 | 2021-09-29 |  | 25% - In Progress |  | RICE 4 |  | 11/11/2021: Not in Scope? On Hold | Yes | 50 | 120 | 160 | 50 | 380 | 170 | 280 | 342.5 | 170 | 172.5 | 368.6905 | 170 | 198.6905
I041 | Interface | Procure to Pay | DMV Destiny- Refund of Traffic Fines | Receive traffic fines refund data and issue payments to DC residents | Phase 1 | ERP Cloud | Sprint 08 | Batch | Inbound | Y | Create Invoice | DMV | Destiny | ERP | Medium |  | Sravana Atmakuru | Himabindu Veganur | Deloitte Owned | Ontrack (Active) | Active | 4-Unit Test | 4-Unit Test | N/A | Not Submitted | 2021-11-15 | 2021-11-22 | 2021-09-09 | 2021-09-22 | 100% - Complete | 2021-12-14 | 2021-12-22 | 2021-09-22 | 2021-09-24 | 100% - Complete |  | 1st Walkthrough Complete |  | 2021-09-27 | 2021-10-18 | 2021-09-27 | 2021-11-29 | 100% - Complete | 2021-10-28 | 2021-10-29 | 2021-10-12 |  | 75% - In Review |  | RICE 3 |  |  | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 100 | 145 | 70 | 75 | 110 | 30 | 80
I011 | Interface | Order to Cash | Banks - Bank Statements Reconciliation & ACH Return/Rejection File From Banks | Receive daily bai2 files for bank account reconciliation. It comes from banks. It will be multiple banks. This has been updated from Kyriba to Banks as process has changed. The files from banks will be consumed by both Kyriba and ERP. | Phase 1 | ERP Cloud | Sprint 10 | Batch | Inbound | N | Create Bank Statement Lines | OCFO | BANKS | ERP | High |  | Rajshekar Amme | Phani Vajjhala | Deloitte Owned | Offtrack (Active) | Active | 4-Unit Test | 3-Build | -17 | Not Submitted | 2021-09-02 | 2021-09-09 | 2021-09-16 | 2021-09-23 | 100% - Complete | 2022-09-23 | 2021-10-06 | 2021-09-30 | 2021-10-08 | 100% - Complete |  | 1st Walkthrough Complete |  | 2021-10-25 | 2021-11-16 | 2021-11-15 |  | 50% - In Progress | 2021-12-24 | 2021-12-29 |  |  |  |  | RICE 3 |  | 11/04/2021: Functional folks doing the configuration - scheduling the job to run to pick up the file - will test | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 200 | 180 | 120 | 60 | 160 | 40 | 120
R137 | Report | Budget Execution | Historical Approved and Revised Budget and Expenditures report | Historical Approved and Revised Budget and Expenditures report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | In Review | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-12-02 | 1st Walkthrough Complete |  | 2021-11-29 | 2021-12-17 | 2021-11-17 |  | 75% - In Review | 2021-11-29 | 2021-12-17 |  |  |  |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 150 | 75 | 75 | 102.7778 | 75 | 27.7778
R135 | Report | Budget Execution | DCPS Advance Report | DCPS Advance Report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | In Review | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-12-02 | 1st Walkthrough Complete |  | 2021-11-29 | 2021-12-17 | 2021-11-17 |  | 75% - In Review | 2021-11-22 | 2021-12-10 |  |  |  |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 150 | 75 | 75 | 112.5 | 75 | 37.5
I081 | Interface | Budget to Report | ERP - CFO$OLVE/DW Transactional Data | Updating this as per new direction for reporting. Transactional data from ERP to CFO$OLVE/DW for reporting purpose Decision needs to be made if this is still needed based on reports strategy. Will involve crosswalk as well before loading the data. Below is not applicable anymore, Extract daily all incremental transactional data from ERP to CFO$OLVE for reporting. All transactions which have been posted, deleted and pending (suspense) in the ERL GL subledger. This is the incremental dump as per current functionality. This involves all crosswalk, transformation and lookup into the SOAR format which CFO$OLVE is expecting. Updated the process area column as per Scott's request. Moved to Phase1 and in-scope as this data is needed CFO$OLVE | Phase 1 | ERP Cloud | Sprint 11 | Batch | Outbound | Y | Send ERP Transactional Data | OCFO | ERP | DW | Very High |  | Rohan Patel | Divya Teja | Deloitte Owned | Ontrack (Active) | Active | 2-Technical Spec | 3-Build | 49 | Not Submitted | 2021-10-14 | 2021-11-26 | 2021-10-18 | 2021-11-05 | 100% - Complete | 2021-11-29 | 2021-12-20 | 2021-10-18 | 2021-11-11 | 100% - Complete |  | Specification Ready |  | 2021-12-21 | 2022-01-21 |  |  | 50% - In Progress | 2022-01-24 | 2022-02-01 |  |  |  |  | RICE 4 |  | 11/04/2021: Reddy sending to Rohan | Yes | 50 | 120 | 160 | 50 | 380 | 170 | 280 | 250 | 170 | 80 | 72.8571 | 72.8571 | 0
I062 | Interface | Procure to Pay | PeopleSoft - Payroll Tax Deductions | Payroll tax deduction payment request data from PeopleSoft. These are payments to IRS, States etc. | Phase 1 | ERP Cloud | Sprint 09 | Batch | Inbound | New | Create Invoice | OCTO | PeopleSoft | ERP | Medium |  | Prasad Potturi | Nirmala | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-05-20 | 2021-06-02 | 2021-05-20 | 2021-06-01 | 100% - Complete | 2021-06-29 | 2021-07-06 | 2021-06-17 | 2021-06-24 | 100% - Complete | 2021-07-22 | 2nd Walkthrough Complete |  | 2021-08-18 | 2021-08-27 | 2021-06-28 | 2021-07-12 | 100% - Complete | 2021-08-27 | 2021-08-31 | 2021-07-12 | 2021-07-16 | 100% - Complete |  | RICE 3 | Tested | Design discussions not happened. Co-ordinating with Fayaz to schedule. The delay is due to the prior items still in discussion. 05/26/2021 Jags will have completed by end of week | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 100 | 150 | 70 | 80 | 150 | 70 | 80
I057 | Interface | Procure to Pay | Banks - ACH Payments | Send ACH payment data to Wells Fargo and Citibank | Phase 1 | ERP Cloud | Sprint 10 | Batch | Outbound | N | Create ACH Payment File | OCFO | ERP | KYRIBA | Medium |  | Muralidhar Pedasanaganti | Divya Teja | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | Not Submitted | 2021-10-11 | 2021-10-19 | 2021-10-18 | 2021-10-22 | 100% - Complete | 2021-10-27 | 2021-11-10 | 2021-10-22 | 2021-11-05 | 100% - Complete |  | Specification Ready |  | 2021-11-15 | 2021-12-06 | 11/06/202 |  | 50% - In Progress | 2022-01-05 | 2022-01-07 |  |  |  |  | RICE 4 |  |  | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 100 | 100 | 70 | 30 | 121.4286 | 70 | 51.4286
I038 | Interface | Procure to Pay | CFSA Faces - Child Care Provider Payment Response | Payment status response back to CFSA | Phase 1 | ERP Cloud | Sprint 09 | Batch | Outbound | Y | Send Payment Status | CFSA | ERP | Faces | Medium |  | Sravana Atmakuru | Sri Hari | Deloitte Owned | Offtrack (Active) | Active | 4-Unit Test | 3-Build | -37 | Not Submitted | 2021-09-16 | 2021-09-22 | 2021-10-05 | 2021-10-08 | 100% - Complete | 2021-11-26 | 2021-12-02 | 2021-10-13 | 2021-10-15 | 100% - Complete |  | Specification Ready |  | 2021-10-18 | 2021-10-27 | 2021-10-28 |  | 25% - In Progress | 2021-10-27 | 2021-10-29 |  |  |  |  | RICE 3 |  | 11/04/2021: working with agency to clarify | Yes | 30 | 40 | 60 | 20 | 150 | 70 | 100 | 85 | 70 | 15 | 150 | 70 | 80
I026 | Interface | Budget | Oracle Planning - Project Budget | Project Budget data from Oracle Planning to Oracle ERP PPM. This needs to go-live after budget is formulated in Oracle Planning. This interface will also be used for reprogramming and modifications. Oracle released recently a built-in adapter for this. Need to check if adapter or custom. | Phase 1 | EPM Cloud | Sprint 10 | Batch | Outbound | New | Create Project Budget | OCFO | EPM | ERP | High |  | Ahamed Rauf | Chitra S | Deloitte Owned | Ontrack (Active) | Active | 4-Unit Test | 4-Unit Test | N/A | Not Submitted | 2021-08-02 | 2021-08-06 | 2021-08-02 | 2021-08-06 | 100% - Complete | 2021-09-01 | 2021-09-17 | 2021-09-01 | 2021-11-26 | 100% - Complete |  | Specification Ready |  | 2021-09-14 | 2021-10-04 | 2021-09-17 | 2021-10-15 | 100% - Complete | 2021-10-05 | 2021-10-08 | 2021-10-21 |  | 75% - In Review | No | RICE 3 |  | 11/12/2021 - Ahmed will provide sample file on 11/12 on Dev7. Testing is still 75% as the new file format need to be validated and tested | Yes | 40 | 80 | 120 | 30 | 270 | 120 | 200 | 262.5 | 120 | 142.5 | 270 | 120 | 150

## Sheet1 (hidden)
RICE ID | Object Type | Process Area | DIFS Object Name | Description | Phase | System | Sprint/Mock Cycle | Report/Interface Type | Report/Interface Direction | Update COA | ERP/EPM Object Type | System Owner | Source System | Target System | Complexity Level | Priority (MoSCoW) | Functional Owner | Technical Owner | Deloitte/District Owned | Current State (Not Started, Functional Specification, Technical Specification, District Review, Technical Build, Functional Testing, Complete) | Active? | Expected Phase | Current Phase | # Of Days Behind | Spec Status | Planned Functional Specification Start Date | Planned Functional Specification End Date | Actual Functional Specification Start Date | Actual Functional Specification End Date | Functional Specification Status | Planned Technical Specification Start Date | Planned Technical Specification End Date | Actual Technical Specification Start Date | Actual Technical Specification End Date | Technical Specification Status | District Work Product Review, Date Provided to District | WP Status | District Work Product Review, Date Approval Provided From District | Planned Technical Build Start Date | Planned Technical Build End Date | Actual Technical Build Start Date | Actual Technical Build End Date | Build Status | Planned Unit Test Start Date | Planned Unit Test End Date | Actual Unit Test Start Date | Actual Unit Test End Date | Unit Test Status | Received Actual Source File | Included in Phase/Milestone | Overall Status | Comments | In Scope | Func | Tech | Build | Unit | Estimated Total | Estimated Spec | Estimated Build/Unit | Actual Total | Actual Spec | Actual Build/Unit | Expected Total | Expected Spec | Expected Buil/Unit
R193 | Report | Projects and Grants | P&G Unlinked Projects Report | P&G Unlinked Projects Report | Phase 1 | ERP Cloud | [8 empty] | Medium |  | Tej Mehta | TBD | Deloitte Owned | Ontrack (Active) | Active | 2-Technical Spec | 2-Technical Spec | N/A | Not Submitted | 2021-11-29 | 2021-12-03 | 2021-11-29 | 2021-12-02 | 100% - Complete | 2021-12-06 | 2021-12-15 |  |  |  |  | N/A |  | 2021-12-16 | 2022-01-07 |  |  |  | 2022-01-10 | 2022-01-12 |  |  |  |  | RICE 4 |  | CR 747367 |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 25 | 25 | 0 | 28.8889 | 28.8889 | 0
R187 | Report | Budget Execution | Capital Projects without plan |  | Phase 1 | EPM Cloud | Sprint 09 | [7 empty] | High |  | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Upcoming (2 Weeks) | Upcoming (2 Weeks) | N/A | 0-Not Started | 31 | Not Submitted | 2021-12-13 | 2022-01-07 |  |  |  | 2021-12-14 | 2022-01-07 |  |  |  |  | N/A |  | 2021-12-14 | 2022-01-07 |  |  |  | 2021-12-14 | 2022-01-07 |  |  |  |  | RICE 4 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 0 | 0 | 0 | 0 | 0 | 0
R186 | Report | Budget Execution | Paygo and Reverse Paygo budget changes |  | Phase 1 | EPM Cloud | Sprint 09 | [7 empty] | High | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Ontrack (Active) | Active | 4-Unit Test | 4-Unit Test | N/A | In Review | 2021-10-04 | 2021-10-15 | 2021-09-21 | 2021-10-15 | 100% - Complete | 2021-10-04 | 2021-10-15 | 2021-09-21 | 2021-10-15 | 100% - Complete | 2021-10-01 | 2nd Submission |  | 2021-10-21 | 2021-11-10 | 2021-10-18 | 2021-11-10 | 100% - Complete | 2021-10-21 | 2021-11-10 | 2021-11-04 |  | 50% - In Progress |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 187.5 | 75 | 112.5 | 200 | 75 | 125
R185 | Report | Budget Execution | General purpose Non-Tax report | sample non-tax revenue report_April_2021 used as sample | Phase 1 | EPM Cloud | Sprint 09 | [7 empty] | Medium | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-08-27 | 2nd Submission |  | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-09 | 100% - Complete | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-10 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 120 | 60 | 60 | 120 | 60 | 60
R184 | Report | Budget Execution | Revenue Estimate comparison by revenue type and by certification period |  | Phase 1 | EPM Cloud | Sprint 09 | [7 empty] | High | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-08-27 | 2nd Submission |  | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-09 | 100% - Complete | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-10 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 200 | 75 | 125
R183 | Report | Budget Execution | Commission Report - SPIN | sample report 15 - Commission Report | Phase 1 | EPM Cloud | Sprint 09 | [7 empty] | High | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-08-27 | 2nd Submission |  | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-09 | 100% - Complete | 2021-08-23 | 2021-09-10 | 2021-08-23 | 2021-09-10 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 200 | 75 | 125
R170 | Report | Budget Execution | Prepare a Quarterly Intra-District Report |  | Phase 1 | EPM Cloud | Sprint 09 | [5 empty] | NA | NA | High |  | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | Not Submitted | 2021-11-11 | 2021-11-29 | 2021-11-29 | 2021-12-03 | 100% - Complete | 2021-11-11 | 2021-11-23 | 2021-11-29 | 2021-12-03 | 100% - Complete |  | Specification Ready |  | 2021-11-24 | 2021-12-10 | 2021-12-01 |  | 25% - In Progress | 2021-11-30 | 2021-12-03 |  |  |  |  | RICE 3 |  | New report. To be rationalized. |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 100 | 75 | 25 | 181.25 | 75 | 106.25
R168 | Report | Budget Execution | Prepare a Reprogramming Report to Council |  | Phase 1 | EPM Cloud | Sprint 09 | [5 empty] | NA | NA | High |  | Mia Kirkwood | Lui Bai | Deloitte Owned | Ontrack (Active) | Active | 4-Unit Test | 4-Unit Test | N/A | In Review | 2021-10-04 | 2021-10-15 | 2021-09-21 | 2021-10-15 | 100% - Complete | 2021-10-04 | 2021-10-15 | 2021-09-21 | 2021-10-15 | 100% - Complete | 2021-10-01 | 2nd Submission |  | 2021-10-21 | 2021-11-10 | 2021-10-15 | 2021-11-10 | 100% - Complete | 2021-10-21 | 2021-11-10 | 2021-11-04 |  | 50% - In Progress |  | RICE 3 |  | New report. To be rationalized. |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 187.5 | 75 | 112.5 | 200 | 75 | 125
R147 | Report | Budget Execution | FRP Report |  | Phase 1 | EPM Cloud | Sprint 09 | [5 empty] | NA | NA | High |  | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-08-23 | 2021-09-03 | 2021-08-23 | 2021-08-25 | 100% - Complete | 2021-08-23 | 2021-09-03 | 2021-08-23 | 2021-08-25 | 100% - Complete | 2021-10-01 | 2nd Submission |  | 2021-09-06 | 2021-10-08 | 2021-09-06 | 2021-10-08 | 100% - Complete | 2021-09-06 | 2021-10-08 | 2021-10-08 | 2021-10-11 | 100% - Complete |  | RICE 3 |  | New report. To be rationalized. |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 200 | 75 | 125
R145 | Report | Procure to Pay | federal Reimbursement report | Supplier Submitted Invoices through Portal Report | Phase 1 | ERP Cloud | Sprint 09 | [5 empty] | NA | NA | Medium | Must Have | Muralidhar Pedasanaganti | Percy Mangwiro | Deloitte Owned | Ontrack (Active) | Active | 2-Technical Spec | 3-Build | 36 | Not Submitted | 2021-10-18 | 2021-10-27 | 2021-10-18 | 2021-10-22 | 100% - Complete | 2021-12-28 | 2022-01-04 | 2021-11-01 | 2021-11-04 | 100% - Complete |  | 1st Walkthrough Complete |  | 2022-01-05 | 2022-01-12 | 2021-11-22 |  | 75% - In Review | 2022-01-13 | 2022-01-14 |  |  |  |  | RICE 4 |  | 11/18/2021: Schedule the review 10/19/2021: Report Name Change: Current Name: DIFS Supplier Submitted Invoices through Portal Report New Name: DIFS Supplier Invoices Report |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 97.5 | 60 | 37.5 | 25 | 25 | 0
R144 | Report | Procure to Pay | Supplier Expiring Profile Attribute Report | Supplier Expiring Profile Attribute Report | Phase 1 | ERP Cloud | Sprint 10 | [5 empty] | NA | NA | Medium | Must Have | Zemeer Padikkal | Vijay Jampana | Deloitte Owned | Offtrack (Active) | Active | 2-Technical Spec | 0-Not Started | -1 | Not Submitted | 2021-11-29 | 2021-12-06 |  |  |  | 2021-12-20 | 2021-12-23 |  |  |  |  | N/A |  | 2021-12-24 | 2022-01-05 |  |  |  | 2022-01-06 | 2022-01-10 |  |  |  |  | RICE 4 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 0 | 0 | 0 | 25 | 25 | 0
R142 | Report | Procure to Pay | Prior Year Cost Recovery Report | Prior Year Cost Recovery Report | Phase 1 | ERP Cloud | [6 empty] | NA | NA | Medium | Could Have | Pandu Sadam | Vijay Jampana | Deloitte Owned | Offtrack (Active) | Active | 2-Technical Spec | 0-Not Started | -1 | Not Submitted | 2021-12-01 | 2021-12-06 |  |  |  | 2021-12-08 | 2021-12-14 |  |  |  |  | N/A |  | 2022-02-16 | 2022-02-23 |  |  |  | 2022-02-24 | 2022-02-28 |  |  |  |  | RICE 4 |  |  | Unplanned | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 0 | 0 | 0 | 25 | 25 | 0
R139 | Report | Budget Execution | Spending Plan Report | Spending Plan Report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-31 | 100% - Complete | 2021-08-09 | 2021-08-20 | 2021-08-09 | 2021-08-25 | 100% - Complete | 2021-08-27 | 2nd Submission |  | 2021-08-23 | 2021-09-10 | 2021-09-06 | 2021-09-09 | 100% - Complete | 2021-09-20 | 2021-10-08 | 2021-08-23 | 2021-09-10 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 200 | 75 | 125
R138 | Report | Budget Execution | Spending Plan Capital Report | Spending Plan Capital Report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | In Review | 2021-09-06 | 2021-09-17 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-09-06 | 2021-09-17 | 2021-08-09 | 2021-08-20 | 100% - Complete | 2021-08-27 | 2nd Submission |  | 2021-09-20 | 2021-10-08 | 2021-08-23 | 2021-09-09 | 100% - Complete | 2021-09-20 | 2021-10-08 | 2021-08-23 | 2021-09-10 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 120 | 60 | 60 | 120 | 60 | 60
R137 | Report | Budget Execution | Historical Approved and Revised Budget and Expenditures report | Historical Approved and Revised Budget and Expenditures report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | In Review | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-12-02 | Ist Submission |  | 2021-11-29 | 2021-12-17 | 2021-11-17 |  | 75% - In Review | 2021-11-29 | 2021-12-17 |  |  |  |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 150 | 75 | 75 | 130.5556 | 75 | 55.5556
R136 | Report | Budget Execution | Expenditures by Month Report | Expenditures by Month Report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | In Review | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-12-02 | Ist Submission |  | 2021-11-29 | 2021-12-17 | 2021-11-17 |  | 75% - In Review | 2021-11-29 | 2021-12-17 |  |  |  |  | RICE 3 |  |  |  | 15 | 15 | 30 | 5 | 65 | 30 | 45 | 52.5 | 30 | 22.5 | 45.5556 | 30 | 15.5556
R135 | Report | Budget Execution | DCPS Advance Report | DCPS Advance Report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | In Review | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-11-11 | 2021-11-26 | 2021-11-11 | 2021-11-16 | 100% - Complete | 2021-12-02 | Ist Submission |  | 2021-11-29 | 2021-12-17 | 2021-11-17 |  | 75% - In Review | 2021-11-22 | 2021-12-10 |  |  |  |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 150 | 75 | 75 | 140.2778 | 75 | 65.2778
R134 | Report | Budget Execution | Approved vs Revised Budget report | Approved vs Revised Budget report | Phase 1 | EPM Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Mia Kirkwood | Mark Vignovich | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | In Review | 2021-11-11 | 2021-11-29 | 2021-11-29 | 2021-12-01 | 100% - Complete | 2021-11-11 | 2021-11-23 | 2021-11-29 | 2021-12-01 | 100% - Complete | 2021-12-02 | Ist Submission |  | 2021-11-24 | 2021-12-10 | 2021-12-01 |  | 25% - In Progress | 2021-11-30 | 2021-12-03 |  |  |  |  | RICE 3 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 72.5 | 60 | 12.5 | 110.625 | 60 | 50.625
R098 | Report | Projects and Grants | P&G to GL funds reconciliation report | P&G to GL funds reconciliation report | Phase 1 | ERP Cloud | Sprint 11 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Tej Mehta | Sriniivas Kompalli | Deloitte Owned | Ontrack (Active) | Active | 4-Unit Test | 4-Unit Test | N/A | Approved | 2021-08-16 | 2021-06-08 |  | 2021-07-21 | 100% - Complete | 2021-07-15 | 2021-07-20 | 2021-07-26 | 2021-08-09 | 100% - Complete | 2021-08-19 | Approved | 2021-08-25 | 2021-07-21 | 2021-07-28 | 2021-08-02 | 2021-08-13 | 100% - Complete | 2021-08-16 | 2021-10-25 | 2021-08-16 |  | 75% - In Review |  | RICE 3 |  | 11/18/2021: Finding issues on GL side - working on the query - similar to issues on R085 - Srini checking 10/14/2021: Issues found - sent back to DEV |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 117.5 | 60 | 57.5 | 120 | 60 | 60
R097 | Report | Projects and Grants | P&G Billable Report | P&G Billable Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Tej Mehta | Sriniivas Kompalli | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-06 | 2021-08-12 | 2021-08-12 | 2021-08-30 | 100% - Complete | 2021-08-17 | 2021-08-20 | 2021-09-02 | 2021-09-16 | 100% - Complete | 2021-09-23 | Approved | 2021-10-04 | 2021-08-23 | 2021-08-31 | 2021-09-02 | 2021-10-04 | 100% - Complete | 2021-09-01 | 2021-09-02 | 2021-09-22 | 2021-10-22 | 100% - Complete |  | RICE 2 |  | Name updated to P&G BIllable Report (Previously P&G Status report) |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 120 | 60 | 60 | 120 | 60 | 60
R095 | Report | Projects and Grants | Maintenance of Effort data extract | Maintenance of Effort data extract | Phase 1 | ERP Cloud | Sprint 11 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Tej Mehta | Sriniivas Kompalli | Deloitte Owned | Not Planned to Start Yet | Not Planned to Start Yet | N/A | 0-Not Started | 51 | Not Submitted | 2022-01-21 | 2022-01-27 |  |  |  | 2022-05-30 | 2022-06-02 |  |  |  |  | N/A |  | 2022-06-03 | 2022-06-10 |  |  |  | 2022-02-11 | 2022-02-13 |  |  |  |  | RICE 4 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 0 | 0 | 0 | 0 | 0 | 0
R085 | Report | Projects and Grants | P&G LTD Balances Report | P&G LTD Balances Report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Tej Mehta | Sriniivas Kompalli | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-05-17 | 2021-05-18 | 2021-05-17 | 2021-05-18 | 100% - Complete | 2021-05-19 | 2021-05-28 | 2021-06-28 | 2021-08-02 | 100% - Complete | 2021-08-09 | Approved | 2021-08-16 | 2021-06-28 | 2021-07-14 | 2021-06-28 | 2021-08-03 | 100% - Complete | 2021-07-15 | 2021-07-20 | 2021-08-12 | 2021-10-07 | 100% - Complete |  | RICE 2 |  | 06/17/2021: Reports rebaseline based on modifications to contract - new tech resource waiting on laptop |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 200 | 75 | 125
R082 | Report | Projects and Grants | Bond Reconciliation Report | Bond Reconciliation Report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Tej Mehta | Sriniivas Kompalli | Deloitte Owned | Offtrack (Active) | Active | 4-Unit Test | 2-Technical Spec | -18 | Not Submitted | 2021-11-11 | 2021-11-15 | 2021-11-18 | 2021-12-02 | 100% - Complete | 2021-11-16 | 2021-11-19 |  |  |  |  | N/A |  | 2021-11-22 | 2021-12-03 |  |  |  | 2021-12-04 | 2021-12-06 |  |  |  |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 25 | 25 | 0 | 200 | 75 | 125
R080 | Report | Procure to Pay | Retainage Report | Retainage Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Low | Must Have | Pandu Sadam | Sriniivas Kompalli | Deloitte Owned | Offtrack (Active) | Active | 2-Technical Spec | 0-Not Started | -7 | Not Submitted | 2021-11-23 | 2021-11-30 |  |  |  | 2022-03-23 | 2022-03-24 |  |  |  |  | N/A |  | 2022-03-25 | 2022-04-01 |  |  |  | 2022-04-04 | 2022-04-05 |  |  |  |  | RICE 4 |  | Report Resolves a Gap Process |  | 15 | 15 | 30 | 5 | 65 | 30 | 45 | 0 | 0 | 0 | 15 | 15 | 0
R077 | Report | Procure to Pay | Expense Report and P Card invoice details | Expense Report and P Card invoice details | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Zemeer Padikkal | Percy Mangwiro | Deloitte Owned | Not Planned to Start Yet | Not Planned to Start Yet | N/A | 0-Not Started | 100 | Not Submitted | 2022-03-08 | 2022-03-17 |  |  |  | 2022-03-25 | 2022-03-31 |  |  |  |  | N/A |  | 2022-04-01 | 2022-04-08 |  |  |  | 2022-04-11 | 2022-04-13 |  |  |  |  | RICE 4 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 0 | 0 | 0 | 0 | 0 | 0
R072 | Report | Procure to Pay | Custom spend report by supplier | Custom spend report by supplier | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Muralidhar Pedasanaganti | Percy Mangwiro | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-05 | 2021-08-18 | 2021-08-19 | 2021-09-06 | 100% - Complete | 2021-09-01 | 2021-09-07 | 2021-09-07 | 2021-09-17 | 100% - Complete | 2021-09-24 | Approved | 2021-10-05 | 2021-09-08 | 2021-09-15 | 2021-09-20 | 2021-10-05 | 100% - Complete | 2021-10-07 | 2021-10-18 | 2021-10-07 | 2021-11-17 | 100% - Complete |  | RICE 3 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 120 | 60 | 60 | 120 | 60 | 60
R071 | Report | Procure to Pay | Custom PO open balances report with accounting and aging | Custom PO open balances report with accounting and aging | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Pandu Sadam | Vijay Jampana | Deloitte Owned | Offtrack (Active) | Active | 4-Unit Test | 3-Build | -50 | In Review | 2021-07-19 | 2021-07-30 | 2021-07-19 | 2021-08-18 | 100% - Complete | 2021-07-29 | 2021-08-20 | 2021-08-02 | 2021-09-07 | 100% - Complete | 2021-11-29 | 1st Submission Feedback Received |  | 2021-09-07 | 2021-10-18 | 2021-09-07 |  | 75% - In Review | 2021-10-19 | 2021-10-22 |  |  |  |  | RICE 3 |  | 10/21/21: Spec changed again;Submitted to District for approval on 11/29 due by 12/2; most of the comments were from Subrah as he is OOO till Dec 3rd reached out to Narayan |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 150 | 75 | 75 | 200 | 75 | 125
R068 | Report | Procure to Pay | Custom payment offset report | Custom payment offset report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Muralidhar Pedasanaganti | Percy Mangwiro | Deloitte Owned | Not Planned to Start Yet | Not Planned to Start Yet | N/A | 0-Not Started | 69 | Not Submitted | 2022-02-03 | 2022-02-14 |  |  |  | 2022-02-28 | 2022-03-07 |  |  |  |  | N/A |  | 2022-03-08 | 2022-03-24 |  |  |  | 2022-03-25 | 2022-03-30 |  |  |  |  | RICE 4 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 0 | 0 | 0 | 0 | 0 | 0
R064 | Report | Procure to Pay | Custom Interactive PO Master Report | Custom Interactive PO Master Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Pandu Sadam | Percy Mangwiro | Deloitte Owned | Offtrack (Active) | Active | 4-Unit Test | 3-Build | -50 | Not Submitted | 2021-09-06 | 2021-09-15 | 2021-09-06 | 2021-10-04 | 100% - Complete | 2021-09-23 | 2021-10-01 | 2021-09-28 | 2021-10-01 | 100% - Complete |  | Specification Ready |  | 2021-09-29 | 2021-10-18 | 2021-09-29 |  | 50% - In Progress | 2021-10-20 | 2021-10-26 |  |  |  |  | RICE 3 |  | 09/30/2021: Still in discussion |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 125 | 75 | 50 | 200 | 75 | 125
R062 | Report | Procure to Pay | Custom 1099 payment data report | Custom 1099 payment data report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Should Have | Muralidhar Pedasanaganti | Vijay Jampana | Deloitte Owned | Ontrack (Active) | Active | 3-Build | 3-Build | N/A | Not Submitted | 2021-11-05 | 2021-11-17 | 2021-11-08 | 2021-11-12 | 100% - Complete | 2021-11-12 | 2021-11-18 | 2021-11-12 | 2021-11-29 | 100% - Complete |  | Specification Ready |  | 2022-01-21 | 2022-01-28 |  |  |  | 2022-01-31 | 2022-02-02 |  |  |  |  | RICE 4 |  | Report Resolves a Gap Process |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 60 | 60 | 0 | 60 | 60 | 0
R058 | Report | Order to Cash | Transaction Details Report | Transaction Details Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Andrew Fedoris | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-08-13 | 2021-08-26 | 2021-08-13 | 2021-08-26 | 100% - Complete | 2021-08-27 | 2021-09-03 | 2021-09-13 | 2021-09-22 | 100% - Complete | 2021-09-28 | Approved | 2021-10-26 | 2021-09-06 | 2021-09-22 | 2021-09-16 | 2021-10-05 | 100% - Complete | 2021-09-23 | 2021-09-28 | 2021-10-07 | 2021-10-28 | 100% - Complete |  | RICE 2 |  | 10/21/21: Andrew updated the requirements in Functional testing |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 200 | 75 | 125
R054 | Report | Order to Cash | Receipt Detail report | Receipt Detail report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Should Have | Andrew Fedoris | Vijay Jampana | Deloitte Owned | Offtrack (Active) | Active | 3-Build | 2-Technical Spec | -7 | Not Submitted | 2021-11-10 | 2021-11-18 | 2021-11-15 | 2021-11-23 | 100% - Complete | 2021-11-19 | 2021-11-30 | 2021-11-23 |  | 50% - In Progress |  | N/A |  | 2021-12-01 | 2021-12-17 |  |  |  | 2021-12-20 | 2021-12-27 |  |  |  |  | RICE 3 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 50 | 50 | 0 | 112.5 | 75 | 37.5
R053 | Report | Order to Cash | Offset report | Offset report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Andrew Fedoris | Sriniivas Kompalli | Deloitte Owned | Not Planned to Start Yet | Not Planned to Start Yet | N/A | 0-Not Started | 143 | Not Submitted | 2022-04-25 | 2022-04-29 |  |  |  | 2022-05-01 | 2022-05-09 |  |  |  |  | N/A |  | 2022-05-10 | 2022-05-27 |  |  |  | 2022-05-30 | 2022-06-02 |  |  |  |  | RICE 4 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 0 | 0 | 0 | 0 | 0 | 0
R051 | Report | Budget to Report | Journal Entry Detail report | Journal Entry Detail report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Jessica Rubin | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-14 | 2021-06-18 | 2021-06-14 | 2021-06-18 | 100% - Complete | 2021-06-28 | 2021-07-22 | 2021-06-28 | 2021-07-22 | 100% - Complete | 2021-07-19 | Approved | 2021-07-30 | 2021-06-28 | 2021-07-23 | 2021-06-28 | 2021-07-23 | 100% - Complete | 2021-07-12 | 2021-07-29 | 2021-07-12 | 2021-07-29 | 100% - Complete |  | RICE 1 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 200 | 75 | 125
R046 | Report | Order to Cash | Custom Sale of Assets - Revenue Report | Custom Sale of Assets - Revenue Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Simon Lu | Sriniivas Kompalli | Deloitte Owned | Ontrack (Active) | Active | N/A | 1-Functional Spec | 115 | Not Submitted | 2022-03-28 | 2022-04-01 | 2021-12-01 |  | 50% - In Progress | 2022-04-04 | 2022-04-12 |  |  |  |  | N/A |  | 2022-04-13 | 2022-04-29 |  |  |  | 2022-05-01 | 2022-05-06 |  |  |  |  | RICE 4 |  | Report Resolves a Gap Process |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 12.5 | 12.5 | 0 | 0 | 0 | 0
R041 | Report | Order to Cash | AR Statement Report | AR Statement Report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Andrew Fedoris | Sriniivas Kompalli | Deloitte Owned | Ontrack (Active) | Active | N/A | 2-Technical Spec | 97 | Not Submitted | 2022-02-28 | 2022-03-04 | 2021-11-22 | 2021-11-30 | 100% - Complete | 2022-03-07 | 2022-03-14 |  |  |  |  | N/A |  | 2022-03-15 | 2022-03-22 |  |  |  | 2022-03-23 | 2022-03-25 |  |  |  |  | RICE 4 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 25 | 25 | 0 | 0 | 0 | 0
R037 | Report | Intra-District | Intra-district budget dashboard | Intra-district budget dashboard | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Tej Mehta | Percy Mangwiro | Deloitte Owned | Offtrack (Active) | Active | 2-Technical Spec | 0-Not Started | -11 | Not Submitted | 2021-11-17 | 2021-11-26 |  |  |  | 2022-01-31 | 2022-02-08 |  |  |  |  | N/A |  | 2022-02-09 | 2022-02-25 |  |  |  | 2022-01-03 | 2022-01-10 |  |  |  |  | RICE 4 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 0 | 0 | 0 | 25 | 25 | 0
R033 | Report | Budget to Report | Total Budget by fund for Capital Improvement Plan (CIP) | Total Budget by fund for Capital Improvement Plan (CIP) | Phase 1 | ERP Cloud | Sprint 11 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Jessica Rubin | Vijay Jampana | Deloitte Owned | Not Started (Active) | Active | 1-Functional Spec | 0-Not Started | 7 | Not Submitted | 2021-12-07 | 2021-12-14 |  |  | 0% - Not Started | 2022-01-06 | 2022-01-13 |  |  |  |  | N/A |  | 2022-01-14 | 2022-02-02 |  |  |  | 2022-03-10 | 2022-03-16 |  |  |  |  | RICE 4 |  | Jessica Rubin began writing functional spec for custom report with RICE ID 33 |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 0 | 0 | 0 | 0 | 0 | 0
R031 | Report | Budget to Report | Subledger Reconciliation Report | Subledger Reconciliation Report | Phase 1 | ERP Cloud | Sprint 11 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Tushar Bhansali | Sriniivas Kompalli | Deloitte Owned | Offtrack (Active) | Active | 4-Unit Test | 3-Build | -4 | In Review | 2021-08-25 | 2021-08-25 | 2021-10-14 | 2021-10-14 | 100% - Complete | 2021-10-25 | 2021-11-22 | 2021-10-27 | 2021-10-27 | 100% - Complete | 2021-11-23 | Approved |  | 2021-11-23 | 2021-12-03 | 2021-11-02 |  | 75% - In Review | 2021-12-06 | 2021-12-09 | 2021-12-01 |  | 75% - In Review |  | RICE 3 |  | 09/02/2021: This may not be needed?; Submitted to District for approval on 11/23 due by 11/30 |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 105 | 60 | 45 | 113.3333 | 60 | 53.3333
R026 | Report | Budget to Report | Chart of Account Profile Data Report | Org/Program report | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Jessica Rubin | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-19 | 2021-07-27 | 2021-07-19 | 2021-07-27 | 100% - Complete | 2021-07-27 | 2021-11-11 | 2021-07-27 | 2021-08-06 | 100% - Complete | 2021-08-17 | Approved | 2021-08-20 | 2021-07-27 | 2021-11-29 | 2021-07-27 | 2021-08-06 | 100% - Complete | 2021-11-30 | 2021-12-03 | 2021-08-13 | 2021-09-03 | 100% - Complete |  | RICE 2 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 200 | 75 | 125
R025 | Report | Budget to Report | Budgetary Control Analysis Report | Non Personnel Service (NPS) Budget Reports | Phase 1 | ERP Cloud | Sprint 09 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Trinh Trinh | Percy Mangwiro | Deloitte Owned | Ontrack (Active) | Active | 4-Unit Test | 4-Unit Test | N/A | Approved | 2022-07-15 | 2021-07-22 | 2021-08-16 | 2021-07-22 | 100% - Complete | 2021-07-23 | 2021-07-30 | 2021-07-26 | 2021-08-19 | 100% - Complete | 2021-09-17 | Approved | 2021-10-14 | 2021-08-02 | 2021-08-18 | 2021-08-19 | 2021-09-27 | 100% - Complete | 2021-09-27 | 2021-10-25 | 2021-09-27 |  | 75% - In Review |  | RICE 3 |  | 10/21/2021: issue identified will work with Percy on the issue |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 193.75 | 75 | 118.75 | 175 | 50 | 125
R019 | Report | Budget to Report | Expenditure and revenue report | Expenditure and revenue report | Phase 1 | ERP Cloud | Sprint 10 |  | Inbound | NA |  |  | NA | NA | High | Must Have | Trinh Trinh | Percy Mangwiro | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-06-09 | 2021-07-20 | 2021-05-17 | 2021-08-02 | 100% - Complete | 2021-07-21 | 2021-07-28 | 2021-06-28 | 2021-08-16 | 100% - Complete | 2021-09-10 | Approved | 2021-11-29 | 2021-07-29 | 2021-08-16 | 2021-08-17 | 2021-09-01 | 100% - Complete | 2021-09-27 | 2021-10-18 | 2021-09-27 | 2021-12-02 | 100% - Complete |  | RICE 3 |  | 10/21/2021 - check with Trinh - scope is changing? Call 10/22/2021 |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 200 | 75 | 125
R005 | Report | Acquire to Retire | Category Reconciliation Report | Category Reconciliation Report | Phase 1 | ERP Cloud | Sprint 8.5 |  | Inbound | NA |  |  | NA | NA | High | Should Have | Simon Lu | Sriniivas Kompalli | Deloitte Owned | Ontrack (Active) | Active | N/A | 4-Unit Test | 87 | Approved | 2022-01-03 | 2022-01-10 | 2021-09-01 | 2021-09-20 | 100% - Complete | 2022-02-03 | 2022-02-10 |  |  | 100% - Complete | 2021-10-28 | Approved | 2021-11-12 | 2022-02-11 | 2022-02-28 | 2021-10-27 |  | 100% - Complete | 2022-03-01 | 2022-03-04 |  |  |  |  | RICE 4 |  |  |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 175 | 75 | 100 | 0 | 0 | 0
R003 | Report | Acquire to Retire | Asset Transaction Report | Asset Transaction Report | Phase 1 | ERP Cloud | Sprint 8.5 |  | Inbound | NA |  |  | NA | NA | Medium | Must Have | Simon Lu | Vijay Jampana | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-10-18 | 2021-10-22 | 2021-09-01 | 2021-10-08 | 100% - Complete | 2021-10-25 | 2021-10-28 | 2021-10-11 | 2021-10-21 | 100% - Complete | 2021-10-26 | Approved | 2021-10-29 | 2021-10-26 | 2021-11-02 | 2021-10-26 | 2021-11-11 | 100% - Complete | 2021-11-03 | 2021-11-05 | 2021-11-02 | 2021-11-11 | 100% - Complete |  | RICE 2 |  |  |  | 25 | 35 | 50 | 10 | 120 | 60 | 85 | 120 | 60 | 60 | 120 | 60 | 60
R002 | Report | Acquire to Retire | Asset Register | Asset Register | Phase 1 | ERP Cloud | Sprint 8.5 | OTBI | Inbound | NA |  |  | NA | NA | High | Must Have | Simon Lu | Sriniivas Kompalli | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-09-21 | 2021-09-27 | 2021-09-01 | 2021-09-20 | 100% - Complete | 2021-09-28 | 2021-10-05 | 2021-10-12 | 2021-10-18 | 100% - Complete | 2021-10-20 | Approved | 2021-11-12 | 2021-10-26 | 2021-11-12 | 2021-10-19 |  | 100% - Complete | 2021-11-15 | 2021-11-19 | 2021-10-28 |  | 100% - Complete |  | RICE 3 |  | Report Resolves a Gap Process |  | 25 | 50 | 100 | 25 | 200 | 75 | 150 | 200 | 75 | 125 | 200 | 75 | 125

## Sheet4 (hidden)
RICE ID | Object Type | Process Area | DIFS Object Name | Description | Phase | System | Sprint/Mock Cycle | Report/Interface Type | Report/Interface Direction | Update COA | ERP/EPM Object Type | System Owner | Source System | Target System | Complexity Level | Priority (MoSCoW) | Functional Owner | Technical Owner | Deloitte/District Owned | Current State (Not Started, Functional Specification, Technical Specification, District Review, Technical Build, Functional Testing, Complete) | Active? | Expected Phase | Current Phase | # Of Days Behind | Spec Status | Planned Functional Specification Start Date | Planned Functional Specification End Date | Actual Functional Specification Start Date | Actual Functional Specification End Date | Functional Specification Status | Planned Technical Specification Start Date | Planned Technical Specification End Date | Actual Technical Specification Start Date | Actual Technical Specification End Date | Technical Specification Status | Last Review update Date | WP Status | District Work Product Review, Date Approval Provided From District | Planned Technical Build Start Date | Planned Technical Build End Date | Actual Technical Build Start Date | Actual Technical Build End Date | Build Status | Planned Unit Test Start Date | Planned Unit Test End Date | Actual Unit Test Start Date | Actual Unit Test End Date | Unit Test Status | Received Actual Source File | Included in Phase/Milestone | Overall Status | Comments | In Scope | Func | Tech | Build | Unit | Estimated Total | Estimated Spec | Estimated Build/Unit | Actual Total | Actual Spec | Actual Build/Unit | Expected Total | Expected Spec | Expected Buil/Unit
E006 | Extension | Projects and Grants | P&G Receipt Accrual Extension | Create receipt accrual for Projects and awards, to reflect the Projects accruals correctly. | Phase 1 | ERP Cloud |  |  |  |  | ERP | OCFO | ERP |  | Medium |  | Tej Mehta | Reddy | Deloitte Owned | Not Started (Active) | Active | 1-Functional Spec | 0-Not Started | 0 | #N/A | 2022-01-17 | 2022-01-24 |  |  |  | 2022-01-24 | 2022-01-28 |  |  |  | #N/A | #N/A | #N/A | 2022-01-31 | 2022-02-11 |  |  |  | 2022-02-12 | 2022-02-15 | [8 empty] | 25 | 40 | 80 | 15 | 160 | 65 | 120 | 0 | 0 | 0 | #REF! | 25 | #REF!
E005 | Extension | O2C | The Receivables Invoice Segregation of Duty Page Customization | • Need a page customization for AR invoice creation process. This will ensure Segregation of Duty. • The role, DIFS Customer Maintenance JR, will have the Complete function greyed out or taken away on the invoice page. | Phase 1 | ERP Cloud |  | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Medium |  | Andrew Fedoris | Hima | Deloitte Owned | Ontrack (Active) | Active | 2-Technical Spec | 4-Unit Test | 9 | #N/A | 2022-01-12 | 2022-01-20 | 2022-01-11 | 2022-01-20 | 100% - Complete | 2022-01-20 | 2022-01-25 | 2022-01-20 | 2022-01-21 | 100% - Complete | #N/A | #N/A | #N/A | 2022-01-25 | 2022-01-28 | 2022-01-20 | 2022-01-21 | 100% - Complete | 2022-01-28 | 2022-02-02 | 2022-01-21 |  | 50% - In Progress | [5 empty] | 25 | 40 | 80 | 15 | 160 | 65 | 120 | 152.5 | 65 | 87.5 | 57 | 57 | 0
E004 | Extension | Projects and Grants | P&G Hold Unpaid Expenses for Billing | P&G Hold Unpaid Expenses for Billing | Phase 1 | ERP Cloud | Sprint 10 | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Medium |  | Tej Mehta | Hima | Deloitte Owned | Ontrack (Active) | Active | 2-Technical Spec | 2-Technical Spec | N/A | Not Submitted | 2021-11-29 | 2021-12-03 | 2021-11-29 | 2021-12-07 | 100% - Complete | 2021-12-16 | 2022-01-30 | 2021-12-16 |  | 50% - In Progress |  | N/A |  | 2022-01-31 | 2022-02-14 |  |  |  | 2022-02-15 | 2022-02-18 |  |  |  |  | RICE 4 |  | 1/17/2022 - Opened an SR with Oracle; Solution not achievable via API; May have to revisit the approach |  | 25 | 40 | 80 | 15 | 160 | 65 | 120 | 45 | 45 | 0 | 59.6667 | 59.6667 | 0
E003 | Extension | Budget to Report | Legacy Crosswalk Generation | Extension for reverse crosswalk from DIFS COA/PATEO to SOAR COA and Index/PCA. This is needed when new DIFS values are added so that existing agency systems such as PASS, PeopleSoft, MMIS etc. can consume these values in SOAR structure. | Phase 1 | ERP Cloud | Sprint 09 | Online | Bidirectional | Y | ERP | OCFO | ERP | TBD | Very High |  | Rohan Patel | Hima | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 4-Unit Test | -27 | Approved | 2021-09-15 | 2021-10-29 | 2021-09-15 | 2021-11-04 | 100% - Complete | 2021-11-01 | 2021-11-17 | 2021-10-25 | 2021-11-09 | 100% - Complete | 2021-11-09 | Approved | 2021-11-09 | 2021-11-18 | 2021-12-31 | 2021-11-01 | 2021-12-01 | 100% - Complete | 2021-12-14 | 2021-12-28 | 2021-11-22 |  | 75% - In Review |  | RICE 3 |  | this was approved(1/22/2021) and tested during the pre-construction and the RICE ID was I005. |  | 50 | 140 | 220 | 50 | 460 | 190 | 360 | 447.5 | 190 | 257.5 | 460 | 190 | 270
E002 | Extension | Projects and Grants | Funding Patterns | Funding Patterns | Phase 1 | ERP Cloud | Sprint 09 | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Very High |  | Rohan Patel | Lalitha Gollapudi | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-05 | 2021-07-26 | 2021-08-05 | 2021-08-20 | 100% - Complete | 2021-08-10 | 2021-08-30 | 2021-08-27 | 2021-09-08 | 100% - Complete | 2021-10-07 | Approved | 2021-10-07 | 2021-08-31 | 2021-10-08 | 2021-09-10 | 2021-09-24 | 100% - Complete | 2021-10-12 | 2021-10-25 | 2021-09-27 | 2021-10-04 | 100% - Complete |  | RICE 2 |  | 09/16/2021: Review call scheduled | Yes | 50 | 140 | 220 | 50 | 460 | 190 | 360 | 460 | 190 | 270 | 460 | 190 | 270
E001 | Extension | Procure to Pay | Liability Offsets | Liability Offsets - Federal Liability Offset | Phase 1 | ERP Cloud | Sprint 11 | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Very High |  | Andrew Fedoris | Hima | Deloitte Owned | Offtrack (Active) | Active | 4-Unit Test | 3-Build | -11 | In Review | 2021-10-18 | 2021-11-01 | 2021-10-26 | 2021-12-20 | 100% - Complete | 2021-11-09 | 2022-01-14 | 2022-01-04 | 2022-01-14 | 100% - Complete | 2022-01-14 | Specification Ready |  | 2021-12-02 | 2022-01-13 | 2022-01-13 |  | 50% - In Progress | 2022-01-14 | 2022-01-28 |  |  |  |  | RICE 4 |  | 07/08/2021: Shifting Offset Liability dates - CR 728636 | Yes | 50 | 140 | 220 | 50 | 460 | 190 | 360 | 300 | 190 | 110 | 445.7143 | 190 | 255.7143

## Sheet5 (hidden)
RICE ID | Object Type | Process Area | DIFS Object Name | Description | Phase | System | Sprint/Mock Cycle | Report/Interface Type | Report/Interface Direction | Update COA | ERP/EPM Object Type | System Owner | Source System | Target System | Complexity Level | Priority (MoSCoW) | Functional Owner | Technical Owner | Deloitte/District Owned | Current State (Not Started, Functional Specification, Technical Specification, District Review, Technical Build, Functional Testing, Complete) | Active? | Expected Phase | Current Phase | # Of Days Behind | Spec Status | Planned Functional Specification Start Date | Planned Functional Specification End Date | Actual Functional Specification Start Date | Actual Functional Specification End Date | Functional Specification Status | Planned Technical Specification Start Date | Planned Technical Specification End Date | Actual Technical Specification Start Date | Actual Technical Specification End Date | Technical Specification Status | Last Review update Date | WP Status | District Work Product Review, Date Approval Provided From District | Planned Technical Build Start Date | Planned Technical Build End Date | Actual Technical Build Start Date | Actual Technical Build End Date | Build Status | Planned Unit Test Start Date | Planned Unit Test End Date | Actual Unit Test Start Date | Actual Unit Test End Date | Unit Test Status | Received Actual Source File | Included in Phase/Milestone | Overall Status | Comments | In Scope | Func | Tech | Build | Unit | Estimated Total | Estimated Spec | Estimated Build/Unit | Actual Total | Actual Spec | Actual Build/Unit | Expected Total | Expected Spec | Expected Buil/Unit
E006 | Extension | Projects and Grants | P&G Receipt Accrual Extension | Create receipt accrual for Projects and awards, to reflect the Projects accruals correctly. | Phase 1 | ERP Cloud |  |  |  |  | ERP | OCFO | ERP |  | Medium |  | Tej Mehta | Reddy | Deloitte Owned | Not Started (Active) | Active | 1-Functional Spec | 0-Not Started | 0 | #N/A | 2022-01-17 | 2022-01-24 |  |  |  | 2022-01-24 | 2022-01-28 |  |  |  | #N/A | #N/A | #N/A | 2022-01-31 | 2022-02-11 |  |  |  | 2022-02-12 | 2022-02-15 | [8 empty] | 25 | 40 | 80 | 15 | 160 | 65 | 120 | 0 | 0 | 0 | #REF! | 25 | #REF!
E005 | Extension | O2C | The Receivables Invoice Segregation of Duty Page Customization | • Need a page customization for AR invoice creation process. This will ensure Segregation of Duty. • The role, DIFS Customer Maintenance JR, will have the Complete function greyed out or taken away on the invoice page. | Phase 1 | ERP Cloud |  | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Medium |  | Andrew Fedoris | Hima | Deloitte Owned | Ontrack (Active) | Active | 2-Technical Spec | 4-Unit Test | 9 | #N/A | 2022-01-12 | 2022-01-20 | 2022-01-11 | 2022-01-20 | 100% - Complete | 2022-01-20 | 2022-01-25 | 2022-01-20 | 2022-01-21 | 100% - Complete | #N/A | #N/A | #N/A | 2022-01-25 | 2022-01-28 | 2022-01-20 | 2022-01-21 | 100% - Complete | 2022-01-28 | 2022-02-02 | 2022-01-21 |  | 50% - In Progress | [5 empty] | 25 | 40 | 80 | 15 | 160 | 65 | 120 | 152.5 | 65 | 87.5 | 57 | 57 | 0
E004 | Extension | Projects and Grants | P&G Hold Unpaid Expenses for Billing | P&G Hold Unpaid Expenses for Billing | Phase 1 | ERP Cloud | Sprint 10 | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Medium |  | Tej Mehta | Hima | Deloitte Owned | Ontrack (Active) | Active | 2-Technical Spec | 2-Technical Spec | N/A | Not Submitted | 2021-11-29 | 2021-12-03 | 2021-11-29 | 2021-12-07 | 100% - Complete | 2021-12-16 | 2022-01-30 | 2021-12-16 |  | 50% - In Progress |  | N/A |  | 2022-01-31 | 2022-02-14 |  |  |  | 2022-02-15 | 2022-02-18 |  |  |  |  | RICE 4 |  | 1/17/2022 - Opened an SR with Oracle; Solution not achievable via API; May have to revisit the approach |  | 25 | 40 | 80 | 15 | 160 | 65 | 120 | 45 | 45 | 0 | 59.6667 | 59.6667 | 0
E003 | Extension | Budget to Report | Legacy Crosswalk Generation | Extension for reverse crosswalk from DIFS COA/PATEO to SOAR COA and Index/PCA. This is needed when new DIFS values are added so that existing agency systems such as PASS, PeopleSoft, MMIS etc. can consume these values in SOAR structure. | Phase 1 | ERP Cloud | Sprint 09 | Online | Bidirectional | Y | ERP | OCFO | ERP | TBD | Very High |  | Rohan Patel | Hima | Deloitte Owned | Offtrack (Active) | Active | 5-Complete | 4-Unit Test | -27 | Approved | 2021-09-15 | 2021-10-29 | 2021-09-15 | 2021-11-04 | 100% - Complete | 2021-11-01 | 2021-11-17 | 2021-10-25 | 2021-11-09 | 100% - Complete | 2021-11-09 | Approved | 2021-11-09 | 2021-11-18 | 2021-12-31 | 2021-11-01 | 2021-12-01 | 100% - Complete | 2021-12-14 | 2021-12-28 | 2021-11-22 |  | 75% - In Review |  | RICE 3 |  | this was approved(1/22/2021) and tested during the pre-construction and the RICE ID was I005. |  | 50 | 140 | 220 | 50 | 460 | 190 | 360 | 447.5 | 190 | 257.5 | 460 | 190 | 270
E002 | Extension | Projects and Grants | Funding Patterns | Funding Patterns | Phase 1 | ERP Cloud | Sprint 09 | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Very High |  | Rohan Patel | Lalitha Gollapudi | Deloitte Owned | Complete | Complete | 5-Complete | 5-Complete | N/A | Approved | 2021-07-05 | 2021-07-26 | 2021-08-05 | 2021-08-20 | 100% - Complete | 2021-08-10 | 2021-08-30 | 2021-08-27 | 2021-09-08 | 100% - Complete | 2021-10-07 | Approved | 2021-10-07 | 2021-08-31 | 2021-10-08 | 2021-09-10 | 2021-09-24 | 100% - Complete | 2021-10-12 | 2021-10-25 | 2021-09-27 | 2021-10-04 | 100% - Complete |  | RICE 2 |  | 09/16/2021: Review call scheduled | Yes | 50 | 140 | 220 | 50 | 460 | 190 | 360 | 460 | 190 | 270 | 460 | 190 | 270
E001 | Extension | Procure to Pay | Liability Offsets | Liability Offsets - Federal Liability Offset | Phase 1 | ERP Cloud | Sprint 11 | Online | Bidirectional | New | ERP | OCFO | ERP | ERP | Very High |  | Andrew Fedoris | Hima | Deloitte Owned | Offtrack (Active) | Active | 4-Unit Test | 3-Build | -11 | In Review | 2021-10-18 | 2021-11-01 | 2021-10-26 | 2021-12-20 | 100% - Complete | 2021-11-09 | 2022-01-14 | 2022-01-04 | 2022-01-14 | 100% - Complete | 2022-01-14 | Specification Ready |  | 2021-12-02 | 2022-01-13 | 2022-01-13 |  | 50% - In Progress | 2022-01-14 | 2022-01-28 |  |  |  |  | RICE 4 |  | 07/08/2021: Shifting Offset Liability dates - CR 728636 | Yes | 50 | 140 | 220 | 50 | 460 | 190 | 360 | 300 | 190 | 110 | 445.7143 | 190 | 255.7143

## Burndown_Reports_District (hidden)
RICE Objects | Sept 2020 |  | Oct 2020 |  | Nov 2020 |  | Dec 2020 |  | Jan 2021 |  | Feb 2021 |  | March 2021 |  | April 2021 |  | May 2021 |  | June 2021 |  | July 2021 |  | August 2021 |  | Sept 2021 |  | Oct 2021 |  | Nov 2021 |  | Dec 2021 |  | Jan 2022 |  | Feb 2022 |  | March 2022 |  | April 2022 |  | May 2022 |  | Total by RICE |  | Progress |  | For Reference Only
| Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Complete | Remaining |  | Target | Planned | Actual | Complete | Remaining | How to update Burndown charts
Conversions | [46 empty] | Functional Spec | 34 | 0 | 0 | 0% | 100% | 1. Copy AH and Paste Formula into AI to update Burndown charts
Functional Spec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 5 | 1 | 2 | 7 | 6 | 3 | 1 | 5 | 4 | 3 | 5 | 6 | 4 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 32 | 94.12% | 5.882% | Technical Spec | 34 | 0 | 0 | 0% | 100%
Technical Spec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 3 | 4 | 2 | 3 | 4 | 3 | 2 | 3 | 4 | 5 | 4 | 5 | 6 | 7 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 34 | 31 | 91.18% | 8.824% |  | 68 | 0 | 0 | 0% | 100% | How to Update the Circle Progress charts
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 4 | 6 | 9 | 9 | 7 | 4 | 7 | 7 | 7 | 10 | 10 | 9 | 9 | 12 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 68 | 63 | 92.65% | 7.353% | Build | 34 | 0 | 0 | 0% | 100% | 1. Copy Column AB(Target) as Formula to Column AC(Actual) every month
Build | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 4 | 3 | 2 | 2 | 3 | 4 | 5 | 5 | 3 | 5 | 9 | 5 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 34 | 31 | 91.18% | 8.824% | Test | 34 | 0 | 0 | 0% | 100% | 2. Column AK (As of Date), edit the date for the Phase 1 Burndown every week
Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 2 | 4 | 3 | 3 | 2 | 3 | 5 | 4 | 4 | 4 | 6 | 10 | 5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 34 | 32 | 94.12% | 5.882% |  | 68 | 0 | 0 | 0% | 100%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 | 5 | 8 | 6 | 5 | 4 | 6 | 9 | 9 | 9 | 7 | 11 | 19 | 10 | 6 | 8 | 0 | 0 | 0 | 0 | 0 | 68 | 63 | 92.65% | 7.353% | Total: | 136 | 0 | 0 | 0% | 100%
Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 10 | 9 | 14 | 17 | 13 | 9 | 11 | 13 | 16 | 19 | 19 | 16 | 20 | 31 | 16 | 7 | 9 | 0 | 0 | 0 | 0 | 0 | 136 | 126 | 92.65% | 7.353%
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 136 | 136
[26 empty] | March 2021 | 136 | 136
[26 empty] | April 2021 | 136 | 136 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 136 | 136 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 128 | 131 | <- Fill this every month with the formula from Column AB | [7 empty] | 95.64% | 4.362% | 99.59% | 0.4065%
[26 empty] | July 2021 | 118 | 122
[26 empty] | Aug 2021 | 104 | 105
[26 empty] | Sept 2021 | 91 | 96
[26 empty] | Oct 2021 | 80 | 83
[26 empty] | Nov 2021 | 64 | 64
[26 empty] | Dec 2021 | 45 | 48
[26 empty] | Jan 2022 | 25 | 17
[26 empty] | Feb 2022 | 9 | 10
[26 empty] | Mar 2022 | 0
[26 empty] | Apr 2022 | 0
[26 empty] | May 2022 | 0
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 68 | 68
[26 empty] | March 2021 | 68 | 68
[26 empty] | April 2021 | 68 | 68 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 68 | 68 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 60 | 63 | <- Fill this every month with the formula from Column AB | [7 empty] | 97.64% | 2.357% | 100% | 0%
[26 empty] | July 2021 | 56 | 57
[26 empty] | Aug 2021 | 47 | 48
[26 empty] | Sept 2021 | 40 | 44
[26 empty] | Oct 2021 | 33 | 37
[26 empty] | Nov 2021 | 26 | 27
[26 empty] | Dec 2021 | 16 | 18
[26 empty] | Jan 2022 | 7 | 6
[26 empty] | Feb 2022 | 1 | 5
[26 empty] | Mar 2022 | 0
[26 empty] | Apr 2022 | 0
[26 empty] | May 2022 | 0
-
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 68 | 68
[26 empty] | March 2021 | 68 | 68
[26 empty] | April 2021 | 68 | 68 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 68 | 68 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 68 | 68 | <- Fill this every month with the formula from Column AB | [7 empty] | 93.77% | 6.234% | 99.21% | 0.7862%
[26 empty] | July 2021 | 62 | 65
[26 empty] | Aug 2021 | 57 | 57
[26 empty] | Sept 2021 | 51 | 52
[26 empty] | Oct 2021 | 47 | 46
[26 empty] | Nov 2021 | 38 | 37
[26 empty] | Dec 2021 | 29 | 30
[26 empty] | Jan 2022 | 18 | 11
[26 empty] | Feb 2022 | 8 | 5
[26 empty] | Mar 2022 | 0
[26 empty] | Apr 2022 | 0
[26 empty] | May 2022 | 0
100%
Reports
Planned Progress
Actual Progress
100%
Reports - Lean Spec
Planned Progress
Actual Progress
99%
Reports - Build/Test
Planned Progress
Actual Progress
Please do not edit this page.

## New Calculation (hidden)
Phase | Phase 1 |  |  | Please Update Very Carefully or contact PMO for latest
|  | Actual | Planned
Row Labels | Sum of Estimated Total | Sum of Actual Total | Sum of Expected Total | Sum of Estimated Spec | Sum of Actual Spec | Sum of Expected Spec | Sum of Estimated Build/Unit | Sum of Actual Build/Unit | Sum of Expected Buil/Unit
Deloitte Owned | 28230 | 27035 | 26593.1222 | 12086 | 11927.25 | 11501 | 16194 | 15107.75 | 15092.1222
Conversion | 5788 | 5788 | 5788 | 2209 | 2209 | 2209 | 3579 | 3579 | 3579
Extension | 1860 | 1823.75 | 1856.25 | 765 | 765 | 765 | 1095 | 1058.75 | 1091.25
Interface | 13892 | 13157 | 13179.3344 | 6322 | 6302 | 6072 | 7570 | 6855 | 7107.3344
Report | 6690 | 6266.25 | 5769.5378 | 2790 | 2651.25 | 2455 | 3950 | 3615 | 3314.5378
District Owned | 3075 | 3062.5 | 2945.5882 | 1485 | 1485 | 1450 | 1590 | 1577.5 | 1495.5882
Report | 3075 | 3062.5 | 2945.5882 | 1485 | 1485 | 1450 | 1590 | 1577.5 | 1495.5882
Grand Total | 31305 | 30097.5 | 29538.7105 | 13571 | 13412.25 | 12951 | 17784 | 16685.25 | 16587.7105
Conversion | 5788 | 5788 | 5788 | 2209 | 2209 | 2209 | 3579 | 3579 | 3579
Extension | 1860 | 1823.75 | 1856.25 | 765 | 765 | 765 | 1095 | 1058.75 | 1091.25
Interface | 13892 | 13157 | 13179.3344 | 6322 | 6302 | 6072 | 7570 | 6855 | 7107.3344
Report | 6690 | 6266.25 | 5769.5378 | 2790 | 2651.25 | 2455 | 3950 | 3615 | 3314.5378
District Owned | 3075 | 3062.5 | 2940.8824 | 1485 | 1485 | 1450 | 1590 | 1577.5 | 1490.8824
Report | 3075 | 3062.5 | 2940.8824 | 1485 | 1485 | 1450 | 1590 | 1577.5 | 1490.8824
Grand Total | 31305 | 30011.25 | 29557.4115 | 13571 | 13399.75 | 12986 | 17784 | 16611.5 | 16571.4115
| RICE Object | Actual Overall | Planned Overall | Difference | Actual Lean Specs | Planned Lean Specs | Difference | Actual Build/Test | Planned Build/Test | Difference
| Conversion | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0%
| Conversion | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0%
| Extension | 98.05% | 99.8% | -1.747% | 100% | 100% | 0% | 96.69% | 99.66% | -2.968%
| Interface | 94.71% | 94.87% | -0.1608% | 99% | 96.05% | 2.954% | 90.55% | 93.89% | -3.333%
Deloitte | Report(Deloitte) | 93.67% | 86.24% | 7.425% | 95.03% | 87.99% | 7.034% | 91.52% | 83.91% | 7.607%
|  |  |  | ^Overall % Behind |  |  | ^Overall Spec Behind |  |  | ^Overall Build/Test Behind
District | Report(District) | 99.59% | 95.64% | 3.955% | 100% | 97.64% | 2.357% | 99.21% | 93.77% | 5.448%
*ANJU please change the formula back to =F14/E14 for F23

## Burndown_Reports_Deloitte (hidden)
RICE Objects | Sept 2020 |  | Oct 2020 |  | Nov 2020 |  | Dec 2020 |  | Jan 2021 |  | Feb 2021 |  | March 2021 |  | April 2021 |  | May 2021 |  | June 2021 |  | July 2021 |  | August 2021 |  | Sept 2021 |  | Oct 2021 |  | Nov 2021 |  | Dec 2021 |  | Jan 2022 |  | Feb 2022 |  | March 2022 |  | April 2022 |  | May 2022 |  | Total by RICE |  | Progress |  | For Reference Only
| Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Complete | Remaining |  | Target | Planned | Actual | Complete | Remaining | How to update Burndown charts
Conversions | [46 empty] | Functional Spec | 43 | 1 | 1 | 2.326% | 97.67% | 1. Copy AH and Paste Formula into AI to update Burndown charts
Functional Spec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 4 | 3 | 8 | 10 | 5 | 3 | 4 | 5 | 7 | 4 | 4 | 9 | 2 | 2 | 4 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 43 | 42 | 97.67% | 2.326% | Technical Spec | 42 | 1 | 0 | 2.381% | 97.62%
Technical Spec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 1 | 6 | 11 | 4 | 4 | 5 | 5 | 8 | 5 | 4 | 8 | 3 | 4 | 2 | 1 | 3 | 0 | 1 | 0 | 1 | 0 | 42 | 39 | 92.86% | 7.143% |  | 85 | 2 | 1 | 2.353% | 97.65% | How to Update the Circle Progress charts
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 8 | 4 | 14 | 21 | 9 | 7 | 9 | 10 | 15 | 9 | 8 | 17 | 5 | 6 | 6 | 5 | 3 | 0 | 3 | 0 | 1 | 0 | 85 | 81 | 95.29% | 4.706% | Build | 43 | 0 | 0 | 0% | 100% | 1. Copy Column AB(Target) as Formula to Column AC(Actual) every month
Build | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 3 | 3 | 6 | 7 | 4 | 4 | 5 | 5 | 7 | 10 | 6 | 4 | 4 | 5 | 3 | 0 | 1 | 0 | 1 | 0 | 43 | 39 | 90.7% | 9.302% | Test | 42 | 0 | 2 | 0% | 100% | 2. Column AK (As of Date), edit the date for the Phase 1 Burndown every week
Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 5 | 6 | 8 | 4 | 4 | 3 | 7 | 11 | 5 | 3 | 6 | 8 | 4 | 0 | 0 | 0 | 1 | 0 | 42 | 38 | 90.48% | 9.524% |  | 85 | 0 | 2 | 0% | 100%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 3 | 3 | 11 | 13 | 12 | 8 | 9 | 8 | 14 | 21 | 11 | 7 | 10 | 13 | 7 | 0 | 1 | 0 | 2 | 0 | 85 | 77 | 90.59% | 9.412% | Total: | 170 | 2 | 3 | 1.176% | 98.82%
Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 13 | 6 | 17 | 24 | 20 | 20 | 21 | 18 | 24 | 17 | 22 | 38 | 16 | 13 | 16 | 18 | 10 | 0 | 4 | 0 | 3 | 0 | 170 | 158 | 92.94% | 7.059%
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 170 | 170
[26 empty] | March 2021 | 170 | 170
[26 empty] | April 2021 | 170 | 170 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 168 | 169 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 166 | 168 | <- Fill this every month with the formula from Column AB | [7 empty] | 86.24% | 13.76% | 93.67% | 6.334%
[26 empty] | July 2021 | 153 | 162
[26 empty] | Aug 2021 | 136 | 138
[26 empty] | Sept 2021 | 116 | 118
[26 empty] | Oct 2021 | 95 | 100
[26 empty] | Nov 2021 | 71 | 83
[26 empty] | Dec 2021 | 49 | 45
[26 empty] | Jan 2022 | 33 | 32
[26 empty] | Feb 2022 | 17 | 14
[26 empty] | Mar 2022 | 7
[26 empty] | Apr 2022 | 3
[26 empty] | May 2022 | 0
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 85 | 85
[26 empty] | March 2021 | 85 | 85
[26 empty] | April 2021 | 85 | 85 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 83 | 84 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 81 | 83 | <- Fill this every month with the formula from Column AB | [7 empty] | 87.99% | 12.01% | 95.03% | 4.973%
[26 empty] | July 2021 | 73 | 79
[26 empty] | Aug 2021 | 59 | 58
[26 empty] | Sept 2021 | 50 | 51
[26 empty] | Oct 2021 | 41 | 41
[26 empty] | Nov 2021 | 26 | 32
[26 empty] | Dec 2021 | 18 | 15
[26 empty] | Jan 2022 | 13 | 9
[26 empty] | Feb 2022 | 7 | 4
[26 empty] | Mar 2022 | 4
[26 empty] | Apr 2022 | 1
[26 empty] | May 2022 | 0
-
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 85 | 85
[26 empty] | March 2021 | 85 | 85
[26 empty] | April 2021 | 85 | 85 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 85 | 85 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 85 | 85 | <- Fill this every month with the formula from Column AB | [7 empty] | 83.91% | 16.09% | 91.52% | 8.481%
[26 empty] | July 2021 | 80 | 83
[26 empty] | Aug 2021 | 77 | 80
[26 empty] | Sept 2021 | 66 | 67
[26 empty] | Oct 2021 | 54 | 59
[26 empty] | Nov 2021 | 45 | 51
[26 empty] | Dec 2021 | 31 | 30
[26 empty] | Jan 2022 | 20 | 23
[26 empty] | Feb 2022 | 10 | 10
[26 empty] | Mar 2022 | 3
[26 empty] | Apr 2022 | 2
[26 empty] | May 2022 | 0
94%
Reports
Planned Progress
Actual Progress
95%
Reports - Lean Spec
Planned Progress
Actual Progress
92%
Reports - Build/Test
Planned Progress
Actual Progress
Please do not edit this page.

## Burndown_Conversions (hidden)
RICE Objects | Sept 2020 |  | Oct 2020 |  | Nov 2020 |  | Dec 2020 |  | Jan 2021 |  | Feb 2021 |  | March 2021 |  | April 2021 |  | May 2021 |  | June 2021 |  | July 2021 |  | August 2021 |  | Sept 2021 |  | Oct 2021 |  | Nov 2021 |  | Dec 2021 |  | Jan 2022 |  | Total by RICE |  | Progress |  | For Reference Only
| Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Complete | Remaining |  | Target | Planned | Actual | Complete | Remaining | How to update Burndown charts
Conversions | [38 empty] | Functional Spec | 19 | 15 | 15 | 78.95% | 21.05% | 1. Copy AH and Paste Formula into AI to update Burndown charts
Functional Spec | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 19 | 100% | 0% | Technical Spec | 19 | 13 | 13 | 68.42% | 31.58%
Technical Spec | 0 | 0 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 2 | 2 | 3 | 4 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 19 | 19 | 100% | 0% |  | 38 | 28 | 28 | 73.68% | 26.32% | How to Update the Circle Progress charts
| 0 | 0 | 10 | 10 | 2 | 2 | 0 | 0 | 0 | 0 | 5 | 6 | 4 | 3 | 4 | 2 | 3 | 5 | 5 | 5 | 4 | 1 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 38 | 38 | 100% | 0% | Build | 19 | 12 | 11 | 63.16% | 36.84% | 1. Copy Column AH(Target) as Formula to Column AI(Actual) every month
Build | 0 | 0 | 0 | 0 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 5 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 19 | 19 | 100% | 0% | Test | 19 | 13 | 11 | 68.42% | 31.58% | 2. Column AO (As of Date), edit the date for the Phase 1 Burndown every week
Test | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 1 | 4 | 0 | 2 | 0 | 0 | 3 | 1 | 3 | 4 | 1 | 0 | 1 | 2 | 4 | 4 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 19 | 19 | 100% | 0% |  | 38 | 25 | 22 | 65.79% | 34.21%
| 0 | 0 | 0 | 0 | 5 | 3 | 6 | 1 | 1 | 4 | 0 | 4 | 1 | 2 | 6 | 3 | 5 | 5 | 2 | 3 | 2 | 3 | 9 | 6 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 38 | 38 | 100% | 0% | Total: | 76 | 53 | 50 | 69.74% | 30.26%
Total: | 0 | 0 | 10 | 10 | 7 | 5 | 6 | 1 | 1 | 4 | 5 | 10 | 5 | 5 | 10 | 5 | 8 | 10 | 7 | 8 | 6 | 4 | 9 | 6 | 1 | 3 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 2 | 76 | 76 | 100% | 0%
Remaining Conversion Activities
[39 empty] | Month | Target | Actual
[39 empty] | Initial Count | 76 | 76
[39 empty] | Sept 2020 | 76 | 76
[39 empty] | Oct 2020 | 66 | 66 |  |  |  |  | Planned Progress |  | Actual Progress
[39 empty] | Nov 2020 | 59 | 61 |  |  |  |  | Complete | Remaining | Complete | Remaining
[39 empty] | Dec 2020 | 53 | 60 |  |  |  |  | 100% | 0% | 100% | 0%
[39 empty] | Jan 2021 | 52 | 56
[39 empty] | Feb 2021 | 47 | 46
[39 empty] | March 2021 | 42 | 41
[39 empty] | April 2021 | 32 | 36
[39 empty] | May 2021 | 24 | 26 | <- Fill this every month with the formula from Column AH
[39 empty] | June 2021 | 17 | 18
[39 empty] | July 2021 | 11 | 14
[39 empty] | Aug 2021 | 2 | 8
[39 empty] | Sept 2021 | 1 | 5
[39 empty] | Oct 2021 | 0 | 4
[39 empty] | Nov 2021 | 0 | 3
[39 empty] | Dec 2021 | 0 | 2
[39 empty] | Jan 2022 | 0 | 0
Remaining Lean Spec Activities
[39 empty] | Month | Target | Actual
[39 empty] | Initial Count | 38 | 38
[39 empty] | Sept 2020 | 38 | 38
[39 empty] | Oct 2020 | 28 | 28 |  |  |  |  | Planned Progress |  | Actual Progress
[39 empty] | Nov 2020 | 26 | 26 |  |  |  |  | Complete | Remaining | Complete | Remaining
[39 empty] | Dec 2020 | 26 | 26 |  |  |  |  | 100% | 0% | 100% | 0%
[39 empty] | Jan 2021 | 26 | 26
[39 empty] | Feb 2021 | 21 | 20
[39 empty] | Mar 2021 | 17 | 17
[39 empty] | April 2021 | 13 | 15
[39 empty] | May 2021 | 10 | 10
[39 empty] | June 2021 | 5 | 5
[39 empty] | July 2021 | 1 | 4
[39 empty] | Aug 2021 | 1 | 4
[39 empty] | Sept 2021 | 1 | 2
[39 empty] | Oct 2021 | 0 | 2
[39 empty] | Nov 2021 | 0 | 1
[39 empty] | Dec 2021 | 0 | 0
[39 empty] | Jan 2022 | 0 | 0
Remaining Build/Test Activities
[39 empty] | Month | Target | Actual
[39 empty] | Initial Count | 38 | 38
[39 empty] | Sept 2020 | 38 | 38
[39 empty] | Oct 2020 | 38 | 38 |  |  |  |  | Planned Progress |  | Actual Progress
[39 empty] | Nov 2020 | 33 | 35 |  |  |  |  | Complete | Remaining | Complete | Remaining
[39 empty] | Dec 2020 | 27 | 34 |  |  |  |  | 100% | 0% | 100% | 0%
[39 empty] | Jan 2021 | 26 | 30
[39 empty] | Feb 2021 | 26 | 26
[39 empty] | Mar 2021 | 25 | 24
[39 empty] | April 2021 | 19 | 21
[39 empty] | May 2021 | 14 | 16
[39 empty] | June 2021 | 12 | 13
[39 empty] | July 2021 | 10 | 10
[39 empty] | Aug 2021 | 1 | 4
[39 empty] | Sept 2021 | 0 | 3
[39 empty] | Oct 2021 | 0 | 2
[39 empty] | Nov 2021 | 0 | 2
[39 empty] | Dec 2021 | 0 | 2
[39 empty] | Jan 2022 | 0 | 0
100%
Conversion - Lean Specs
Planned Progress
Actual Progress
100%
Conversion - Build/Unit Test
Planned Progress
Actual Progress
100%
Conversions
Planned Progress
Actual Progress
Please do not edit this page.

## Burndown_Integrations (hidden)
RICE Objects | Sept 2020 |  | Oct 2020 |  | Nov 2020 |  | Dec 2020 |  | Jan 2021 |  | Feb 2021 |  | March 2021 |  | April 2021 |  | May 2021 |  | June 2021 |  | July 2021 |  | August 2021 |  | Sept 2021 |  | Oct 2021 |  | Nov 2021 |  | Dec 2021 |  | Jan 2022 |  | Feb 2022 |  | March 2022 |  | April 2022 |  | May 2022 |  | Total by RICE |  | Progress |  | For Reference Only
| Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Complete | Remaining |  | Target | Planned | Actual | Complete | Remaining | How to update Burndown charts
Conversions | [46 empty] | Functional Spec | 66 | 16 | 15 | 24.24% | 75.76% | 1. Copy AH and Paste Formula into AI to update Burndown charts
Functional Spec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 9 | 3 | 5 | 9 | 6 | 7 | 7 | 5 | 7 | 6 | 6 | 14 | 10 | 5 | 6 | 2 | 5 | 9 | 2 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 66 | 66 | 100% | 0% | Technical Spec | 66 | 11 | 10 | 16.67% | 83.33%
Technical Spec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 1 | 6 | 7 | 7 | 10 | 5 | 4 | 6 | 5 | 5 | 11 | 9 | 4 | 5 | 3 | 10 | 3 | 6 | 12 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 66 | 65 | 98.48% | 1.515% |  | 132 | 27 | 25 | 20.45% | 79.55% | How to Update the Circle Progress charts
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 4 | 12 | 4 | 11 | 16 | 13 | 17 | 12 | 9 | 13 | 11 | 11 | 25 | 19 | 9 | 11 | 5 | 15 | 12 | 8 | 14 | 1 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 132 | 131 | 99.24% | 0.7576% | Build | 66 | 8 | 9 | 12.12% | 87.88% | 1. Copy Column AB(Target) as Formula to Column AC(Actual) every month
Build | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 6 | 6 | 4 | 4 | 6 | 10 | 8 | 4 | 3 | 1 | 11 | 12 | 6 | 3 | 8 | 3 | 7 | 6 | 3 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 66 | 58 | 87.88% | 12.12% | Test | 66 | 6 | 8 | 9.091% | 90.91% | 2. Column AK (As of Date), edit the date for the Phase 1 Burndown every week
Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 5 | 6 | 3 | 5 | 10 | 9 | 1 | 4 | 5 | 10 | 6 | 5 | 5 | 3 | 2 | 3 | 7 | 12 | 5 | 2 | 0 | 0 | 0 | 1 | 0 | 66 | 52 | 78.79% | 21.21% |  | 132 | 14 | 17 | 10.61% | 89.39%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 4 | 10 | 11 | 10 | 7 | 11 | 20 | 17 | 5 | 7 | 6 | 21 | 18 | 11 | 8 | 11 | 5 | 10 | 13 | 15 | 11 | 2 | 0 | 0 | 0 | 2 | 0 | 132 | 110 | 83.33% | 16.67% | Total: | 264 | 41 | 42 | 15.53% | 84.47%
Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 4 | 4 | 17 | 8 | 21 | 27 | 23 | 24 | 23 | 29 | 30 | 16 | 18 | 31 | 40 | 27 | 22 | 13 | 26 | 17 | 18 | 27 | 16 | 15 | 3 | 0 | 1 | 0 | 2 | 0 | 264 | 241 | 91.29% | 8.712%
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 264 | 264
[26 empty] | March 2021 | 260 | 260
[26 empty] | April 2021 | 243 | 252 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 222 | 225 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 199 | 201 | <- Fill this every month with the formula from Column AB | [7 empty] | 94.87% | 5.13% | 94.71% | 5.291%
[26 empty] | July 2021 | 176 | 172
[26 empty] | Aug 2021 | 146 | 156
[26 empty] | Sept 2021 | 128 | 125
[26 empty] | Oct 2021 | 88 | 98
[26 empty] | Nov 2021 | 66 | 85
[26 empty] | Dec 2021 | 40 | 68
[26 empty] | Jan 2022 | 22 | 41
[26 empty] | Feb 2022 | 6 | 26
[26 empty] | Mar 2022 | 3
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 132 | 132
[26 empty] | March 2021 | 128 | 128
[26 empty] | April 2021 | 116 | 124 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 105 | 108 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 92 | 91 | <- Fill this every month with the formula from Column AB | [7 empty] | 96.05% | 3.954% | 99% | 1%
[26 empty] | July 2021 | 80 | 82
[26 empty] | Aug 2021 | 67 | 71
[26 empty] | Sept 2021 | 56 | 46
[26 empty] | Oct 2021 | 37 | 37
[26 empty] | Nov 2021 | 26 | 32
[26 empty] | Dec 2021 | 11 | 20
[26 empty] | Jan 2022 | 3 | 6
[26 empty] | Feb 2022 | 2 | 2
[26 empty] | Mar 2022 | 1
-
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 132 | 132
[26 empty] | March 2021 | 132 | 132
[26 empty] | April 2021 | 127 | 128 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 117 | 117 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 107 | 110 | <- Fill this every month with the formula from Column AB | [7 empty] | 93.89% | 6.112% | 90.55% | 9.445%
[26 empty] | July 2021 | 96 | 90
[26 empty] | Aug 2021 | 79 | 85
[26 empty] | Sept 2021 | 72 | 79
[26 empty] | Oct 2021 | 51 | 61
[26 empty] | Nov 2021 | 40 | 53
[26 empty] | Dec 2021 | 29 | 48
[26 empty] | Jan 2022 | 19 | 35
[26 empty] | Feb 2022 | 4 | 24
[26 empty] | Mar 2022 | 2
95%
Integrations
Planned Progress
Actual Progress
99%
Integrations - Lean Spec
Planned Progress
Actual Progress
91%
Integrations - Build/Test
Planned Progress
Actual Progress
Please do not edit this page.

## Burndown_Extension (hidden)
RICE Objects | Sept 2020 |  | Oct 2020 |  | Nov 2020 |  | Dec 2020 |  | Jan 2021 |  | Feb 2021 |  | March 2021 |  | April 2021 |  | May 2021 |  | June 2021 |  | July 2021 |  | August 2021 |  | Sept 2021 |  | Oct 2021 |  | Nov 2021 |  | Dec 2021 |  | Jan 2022 |  | Feb 2022 |  | March 2022 |  | April 2022 |  | May 2022 |  | Total by RICE |  | Progress |  | For Reference Only
| Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Target | Actual | Complete | Remaining |  | Target | Planned | Actual | Complete | Remaining | How to update Burndown charts
Conversions | [46 empty] | Functional Spec | 7 | 0 | 0 | 0% | 100% | 1. Copy AH and Paste Formula into AI to update Burndown charts
Functional Spec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 85.71% | 14.29% | Technical Spec | 7 | 0 | 0 | 0% | 100%
Technical Spec | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 4 | 3 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 85.71% | 14.29% |  | 14 | 0 | 0 | 0% | 100% | How to Update the Circle Progress charts
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 2 | 2 | 1 | 2 | 6 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 14 | 12 | 85.71% | 14.29% | Build | 7 | 0 | 0 | 0% | 100% | 1. Copy Column AB(Target) as Formula to Column AC(Actual) every month
Build | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 6 | 85.71% | 14.29% | Test | 7 | 0 | 0 | 0% | 100% | 2. Column AK (As of Date), edit the date for the Phase 1 Burndown every week
Test | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 3 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 7 | 4 | 57.14% | 42.86% |  | 14 | 0 | 0 | 0% | 100%
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 2 | 1 | 3 | 2 | 5 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 14 | 10 | 71.43% | 28.57% | Total: | 28 | 0 | 0 | 0% | 100%
Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 2 | 3 | 1 | 2 | 2 | 3 | 3 | 9 | 6 | 5 | 7 | 3 | 0 | 1 | 0 | 0 | 0 | 28 | 22 | 78.57% | 21.43%
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 28 | 28
[26 empty] | March 2021 | 28 | 28
[26 empty] | April 2021 | 28 | 28 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 28 | 28 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 28 | 28 | <- Fill this every month with the formula from Column AB | [7 empty] | 99.8% | 0.2016% | 98.05% | 1.949%
[26 empty] | July 2021 | 27 | 28
[26 empty] | Aug 2021 | 26 | 27
[26 empty] | Sept 2021 | 26 | 27
[26 empty] | Oct 2021 | 23 | 26
[26 empty] | Nov 2021 | 21 | 24
[26 empty] | Dec 2021 | 18 | 21
[26 empty] | Jan 2022 | 9 | 15
[26 empty] | Feb 2022 | 4 | 8
[26 empty] | Mar 2022 | 1
[26 empty] | Apr 2022 | 0
[26 empty] | May 2022 | 0
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 14 | 14
[26 empty] | March 2021 | 14 | 14
[26 empty] | April 2021 | 14 | 14 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 14 | 14 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 14 | 14 | <- Fill this every month with the formula from Column AB | [7 empty] | 100% | 0% | 100% | 0%
[26 empty] | July 2021 | 13 | 14
[26 empty] | Aug 2021 | 12 | 13
[26 empty] | Sept 2021 | 12 | 12
[26 empty] | Oct 2021 | 11 | 12
[26 empty] | Nov 2021 | 9 | 10
[26 empty] | Dec 2021 | 8 | 8
[26 empty] | Jan 2022 | 2 | 4
[26 empty] | Feb 2022 | 2 | 2
[26 empty] | Mar 2022 | 0
[26 empty] | Apr 2022 | 0
[26 empty] | May 2022 | 0
-
For Burndown Charts
[26 empty] | Month | Target | Actual
[26 empty] | Initial Count | 14 | 14
[26 empty] | March 2021 | 14 | 14
[26 empty] | April 2021 | 14 | 14 | [8 empty] | Planned Progress |  | Actual Progress
[26 empty] | May 2021 | 14 | 14 | [8 empty] | Complete | Remaining | Complete | Remaining
[26 empty] | June 2021 | 14 | 14 | <- Fill this every month with the formula from Column AB | [7 empty] | 99.66% | 0.3425% | 96.69% | 3.311%
[26 empty] | July 2021 | 14 | 14
[26 empty] | Aug 2021 | 14 | 14
[26 empty] | Sept 2021 | 14 | 14
[26 empty] | Oct 2021 | 12 | 13
[26 empty] | Nov 2021 | 12 | 13
[26 empty] | Dec 2021 | 10 | 12
[26 empty] | Jan 2022 | 7 | 10
[26 empty] | Feb 2022 | 2 | 5
[26 empty] | Mar 2022 | 1
[26 empty] | Apr 2022 | 0
[26 empty] | May 2022 | 0
98%
Extensions
Planned Progress
Actual Progress
100%
Extensions - Lean Spec
Planned Progress
Actual Progress
97%
Extensions - Build/Test
Planned Progress
Actual Progress
Please do not edit this page.

## ERP Report Analysis (hidden)
Process Area | Order | RICE ID | DIFS Object Name | Functional Status | Status | Comments | Sample Received, No Sample Provided, No Sample Expected (Future State) | Owner | Future Report ID | Count | Current Status2
Projects and Grants | 1 | R086 | Capital Report by Project and Subproject |  | Merge | Added additional fields to R085. Combined to R085, renamed to P&G LTD Balances Report | Sample Received | Tej | R085 - P&G LTD Balances Report | 0
Projects and Grants | 1 | R101 | Unspent Award/Project Balance Report |  | Merge | Added additional fields to R085. Combined to R085, renamed to P&G LTD Balances Report | No Sample Provided | Tej | R085 - P&G LTD Balances Report | 0
Projects and Grants | 1 | R096 | Master Project Report |  | Merge | Added additional fields to R085. Combined to R085, renamed to P&G LTD Balances Report | No Sample Provided | Tej | R085 - P&G LTD Balances Report | 0
Projects and Grants | 1 | R085 | Capital LTD Balances Report | Completed | Keep | Added additional fields to R085. Combined to R085, renamed to P&G LTD Balances Report | Sample Received | Tej | R085 - P&G LTD Balances Report | 1 | Func 100 tech 75%
Budget To Report | 2 | R017 | Due to, Due From report |  | Merge | Combined into R051 - Journal Entry Detail Report | Sample Received | Jessica | R051 - Journal Entry Detial Report | 0
Budget To Report | 2 | R020 | Financial Audit report |  | Merge | Combined into R051 - Journal Entry Detail Report | Sample Received | Jessica | R051 - Journal Entry Detial Report | 0
Budget To Report | 2 | R028 | Personnel Service (PS) Charges Expenditure report |  | Merge | Combined into R051 - Journal Entry Detail Report | Sample Received | Jessica | R051 - Journal Entry Detial Report | 0
Budget To Report | 2 | R029 | School Advances Report |  | Merge | Combined into R051 - Journal Entry Detail Report | Sample Received | Jessica | R051 - Journal Entry Detial Report | 0
Order To Cash | 2 | R045 | Central Collections Unit Report |  | Merge | Combined into R051 - Journal Entry Detail Report | Sample Received | Jessica | R051 - Journal Entry Detial Report | 0
Budget To Report | 2 | R014 | Bank reconciliation report |  | Merge | Combined into R051 - Journal Entry Detail Report | Sample Received | Jessica | R051 - Journal Entry Detial Report | 0
Budget To Report | 2 | R032 | Summer Pay Credit Report for DCPS |  | Merge | Combined into R051 - Journal Entry Detail Report | Sample Received | Jessica | R051 - Journal Entry Detial Report | 0
Order To Cash | 2 | R051 | Journal Entry Detail report | Completed | Keep | Combined into R051 - Journal Entry Detail Report | No Sample Provided | Jessica | R051 - Journal Entry Detial Report | 1 | Func 100 tech 75%
Order To Cash | 3 | R057 | Revenue vs Expenditure report |  | Merge | Combined with R019 Expenditure and Revenue Report | No Sample Provided | Trinh | R019 - Expenditure vs. Revenue Report | 0
Budget To Report | 3 | R019 | Expenditure and revenue report | In Progress | Keep | Combined with R019 Expenditure and Revenue Report | Sample Received | Trinh | R019 - Expenditure vs. Revenue Report | 1 | Func 100 current tech
Procure To Pay | 4 | R076 | Encumbrances and Pre-Encumbrances Report |  | Merge | Combined with R025 Budgetary Control Analysis Report | Sample Received | Trinh | R025 - Budgetary Control Analysis Report | 0
Budget To Report | 4 | R025 | Non Personnel Service (NPS) Budget Reports | In Progress | Keep | Combined with R025 Budgetary Control Analysis Report | No Sample Provided | Trinh | R025 - Budgetary Control Analysis Report | 1 | Func 100 current tech
Projects and Grants | 5 | R098 | P&G to GL funds reconciliation report | Completed | Keep | Future-state report | No Sample Expected | Tej | R098 - P&G to GL funds reconciliation report | 1 | Func 75%
Projects and Grants | 6 | R097 | P&G Status Report | Not Started | Keep | Turn to a P&G billable report | No Sample Provided | Tej | R097 - P&G Status Report | 1
Projects and Grants | 7 | R082 | Bond Reconciliation Report | Push | Keep |  | Sample Received | Tej | R082 - Bond Reconciliation Report | 1
Budget To Report | 8 | R031 | Subledger Reconciliation Report | Not Started | Keep | Future-state report | No Sample Expected | Trinh | R031 - Subledger Reconciliation Report | 1
Budget To Report | 9 | R026 | Org/Program report | Completed | Keep | Future-state report | No Sample Expected | Jessica | R026 - Org/Program report | 1 | Func 100% current tech
Procure To Pay | 10 | R071 | Custom PO open balances report with accounting and aging | In Progress | Keep |  | Sample Received | Prasad | R071 - Custom PO open balances report with accounting and aging | 1
Procure To Pay | 11 | R072 | Custom spend report by supplier | In Progress | Keep |  | Sample Received | Anil | R072 - Custom spend report by supplier | 1
Acquire To Retire | 12 | R002 | Asset Register | Not Started | Keep | Resolves an Identified GAP | No Sample Expected | Simon | R002 - Asset Register | 1
Acquire To Retire | 13 | R003 | Asset Transaction Report | Not Started | Keep | Provided | Sample Received | Simon | R003 - Asset Transaction Report | 1
Order To Cash | 14 | R040 | Agency Invoice report | In Progress | Keep | Provided | Sample Received | Andrew | R040 - Agency Invoice report | 1
Order To Cash | 15 | R048 | Customer Listing report | In Progress | Keep | Provided | Sample Received | Andrew | R048 - Customer Listing report | 1
Procure To Pay | 16 | R064 | Custom Interactive PO Master Report | Not Started | Keep | Provided | Sample Received | Prasad | R064 - Custom Interactive PO Master Report | 1
Procure To Pay | 17 | R075 | Detailed Payment Register Report | Not Started | Keep | Provided | Sample Received | Anil | R075 - Detailed Payment Register Report | 1
Order To Cash | 18 | R054 | Receipt Detail report | Not Started | Keep | Provided | Sample Received | Andrew | R054 - Receipt Detail report | 1
Order To Cash | 19 | R058 | Transaction Details Report | Not Started | Keep | Provided | Sample Received | Andrew | R058 - Transaction Details Report | 1
Procure To Pay | 20 | R144 | Supplier Expiring Profile Attribute Report | Not Started | Keep | Resolves an Identified GAP | No Sample Expected | P2P Resource | R144 - Supplier Expiring Profile Attribute Report | 1
Procure To Pay | 21 | R145 | Supplier Submitted Invoices through Portal Report | Not Started | Keep | Resolves an Identified GAP | No Sample Expected | P2P Resource | R145 - Supplier Submitted Invoices through Portal Report | 1
Budget To Report | 22 | R033 | Total Budget by fund for Capital Improvement Plan (CIP) | Not Started | Keep | Should be a PnG/FA report | Sample Received | Tej | R033 - Total Budget by fund for Capital Improvement Plan (CIP) | 1
Acquire To Retire | 23 | R005 | Category Reconciliation Report | Not Started | Keep |  | Sample Received | Simon | R005 - Category Reconciliation Report | 1
Order To Cash | 24 | R046 | Custom Sale of Assets - Revenue Report | Not Started | Keep | Resolves an Identified GAP | No Sample Expected | Simon | R046 - Custom Sale of Assets - Revenue Report | 1
Procure To Pay | 25 | R062 | Custom 1099 payment data report | Not Started | Keep | Resolves an Identified GAP | No Sample Expected | Anil | R062 - Custom 1099 payment data report | 1
Procure To Pay | 26 | R080 | Retainage Report | Not Started | Keep | Resolves an Identified GAP | No Sample Expected | Prasad | R080 - Retainage Report | 1
Intra-District | 27 | R037 | Intra-district budget dashboard | Not Started | Keep | Data dumps with pivot tables in excel, could be conslidated into one report | Sample Received | Tej | R037 - Intra-district budget dashboard | 1
Intra-District | 27 | R039 | Intra-district fixed costs report |  | Merge |  | Sample Received | Tej | R039 - Intra-district fixed costs report | 0
Order To Cash | 28 | R041 | AR Statement Report | Not Started | Keep | Provided | Sample Received | Andrew | R041 - AR Statement Report | 1
Order To Cash | 29 | R053 | Offset report | Not Started | Keep | Not provided, but related to offset | No Sample Provided | Andrew | R053 - Offset report | 1
Procure To Pay | 30 | R068 | Custom payment offset report | Not Started | Keep | Not provided, but related to offset | No Sample Provided | Anil | R068 - Custom payment offset report | 1
Procure To Pay | 31 | R077 | Expense Report and P Card invoice details | Not Started | Keep | Future-state report | No Sample Expected | Prasad | R077 - Expense Report and P Card invoice details | 1
Projects and Grants | 32 | R095 | Maintenance of Effort data extract | Not Started | Keep |  | No Sample Provided | Tej | R095 - Maintenance of Effort data extract | 1
TBD |  |  | Report TBD 1 |  | Placeholder | Adding in Placeholder Reports to be determined at a date no later than the development start date to hit threshold of 37 ERP Reports. District could also choose 5 reports to shift to Deloitte at this Time. | No Sample Expected |  | - Report TBD 1 | 1
TBD |  |  | Report TBD 2 |  | Placeholder | Adding in Placeholder Reports to be determined at a date no later than the development start date to hit threshold of 37 ERP Reports. District could also choose 5 reports to shift to Deloitte at this Time. | No Sample Expected |  | - Report TBD 2 | 1
TBD |  |  | Report TBD 3 |  | Placeholder | Adding in Placeholder Reports to be determined at a date no later than the development start date to hit threshold of 37 ERP Reports. District could also choose 5 reports to shift to Deloitte at this Time. | No Sample Expected |  | - Report TBD 3 | 1
TBD |  |  | Report TBD 4 |  | Placeholder | Adding in Placeholder Reports to be determined at a date no later than the development start date to hit threshold of 37 ERP Reports. District could also choose 5 reports to shift to Deloitte at this Time. | No Sample Expected |  | - Report TBD 4 | 1
TBD |  |  | Report TBD 5 |  | Placeholder |  | No Sample Expected |  | - Report TBD 5 | 1
Acquire To Retire |  | R011 | Summarized Asset Closing report |  | Discuss with Product Owners | Not a formal report. Sample consists of screenshots of SOAR screens and excel templates. | Sample Received
Budget To Report |  | R030 | Special Purpose Revenue Report |  | Shift to EPM Phase 2 Budget Formulation | Not an ERP report | Sample Received
Budget To Report |  | R015 | Bank Statement Reconciliation report |  | Discuss with Product Owners | B2R Comment: "There is no formal report in the legacy system. It is just a template that can be developed to reconcile bank to book" | No Sample Provided
Projects and Grants |  | R087 | Capital Transaction Detail |  | Duplicate to EPM Report | Aligns with I162 in EPM Scope | Sample Received
Budget To Report |  | R034 | Transaction Detail Report |  | Discuss with Product Owners | B2R Comment: "Ad-hoc report today, no formal report from legacy. It is an adhoc report an accountant runs based on his/her need." | No Sample Provided
Budget To Report |  | R036 | Washington Teachers Union Member Accrual Report |  | Discuss with Product Owners | B2R Comment: "No information about this report. Not sure who provided it" | No Sample Provided
Intra-District |  | R038 | Intra-district dashboard |  | Discuss with Product Owners | Not a formal report, but a dashboard in a specific reporting tool today | Sample Received
Order To Cash |  | R044 | Cash report |  | Discuss with Product Owners | Not a formal report. Dashboard in from an external reporting tool. | Sample Received
Order To Cash |  | R056 | Revenue Details report |  | Discuss with Product Owners | Not a report from the system. Template that is filled out with data from SOAR. | Sample Received
Budget To Report |  | R013 | "Everything" report |  | Shift to EPM Phase 2 Budget Formulation | Leverage CFO$olve during Phase 1 due to requirement on Formulated Budget and Actual Data | Sample Received
Projects and Grants |  | R084 | Capital FTES and positions Report |  | Discuss with Product Owners | Not an ERP report, contains employee and position data | Sample Received
Projects and Grants |  | R083 | Capital formulation data extract |  | Shift to EPM Phase 2 Budget Formulation | EPM Phase 2 (Budget Formulation) | No Sample Provided

## Appendix InterfaceDataSources (hidden)
[20 empty] | Producer |  | Consumer
RICEW ID | Functional Process Area | DataSource Name | Direction | Automated / Manual | Manual Intervention Required | Process | Complexity | Frequency | DAFRIN | New/Existing | Integration Style | ERP/Oracle Planning Interface Type | Interface Counter | Interface Agency Type | Permanent /Temporary | Phase | Sprint | User Story | Comments | Agency | System | Agency | System | In Scope | Verified (Yes/No) - Final As of Now | Product/Tools | Comments | Mode of Connection in SOAR | Mode of Connection in DIFS
I001 | Budget To Report | PeopleSoft - Payroll Costs | Inbound | Automated | No | Receive Payroll Data of employees and retirees (pensioners) and record them as journal entries in DIFS. Files are sent by payroll group. Multiple files with same file format. This is needed for DIFS for inbound accounting data into Oracle GL. | High | Bi-Weekly-By Payroll Group | Yes | Existing | Batch | Create Journal Entries | 6 | Global | Permanent | Phase1 | Sprint4 | B2R-042 | Need to document business rules to transform and interface payroll cost data from PeopleSoft into Oracle. This includes compliance with chart of mapping rules and desired accounting entries for various data elements of payroll costs file. FBDI needs to be created and transformed from PS format before uploading it. Fed Pensioners payroll was merged with this as no payments are issued | OCTO | PeopleSoft | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | This interface will be updated to new file format and COA. Based on OIC capability (file & ftp adapters, REST service invocation for COA, mapping etc.) and file size limitations OIC is best suited. | FTP psoft-sftp.dc.gov 10.86.36.102 port: 21 | TBD
I002 | Budget To Report | Peoplesoft - Monthly Payroll Cost Accrual/Reversal | Inbound | Semi-Automated | Yes | Receive Monthly Payroll cost accrual and reversal data from PeopleSoft. This is needed for DIFS for inbound accounting data into Oracle GL. Client wants to keep it manual and this will be revisited during implementation phase. PS will keep it manual. more details later. | High | Monthly | Yes | Existing | Batch | Create Journal Entries | 6 | Global | Permanent | Phase1 | Sprint4 | B2R-091 | For monthly they take the last files from a pay group and load it manually via DAFRIN. Currently there are manual tasks including number of days, applying percentage and uploading the data thru DAFRIN into SOAR. B2R core team agreed to continue manual payroll costs accrual process in future state as well accepting FBDI worksheet will replace DAFRIN. In future this will be semi-automated. All these files need to go through a cross-walk and converted into FBDI before automatically getting uploaded into ERP. The Yearly Payroll Cost Accrual file/s will need to go through a COA cross-walk and converted into FBDI before automatically getting uploaded into ERP." | OCTO | PeopleSoft | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | This is a semi automated interface. Based on OIC capability (file & ftp adapters, mapping etc.) and file size limitations OIC is best suited. | Manual upload Process | TBD
I003 | Budget To Report | PeopleSoft - Yearly Payroll Cost Accrual/Reversal | Inbound | Semi-Automated | Yes | Receive Yearly Payroll cost accrual and reversal data from PeopleSoft. This is needed for DIFS for inbound accounting data into Oracle GL. Client wants to keep it manual and this will be revisited during implementation phase | Medium | Yearly | Yes | Existing | Batch | Create Journal Entries | 6 | Global | Permanent | Phase1 | Sprint4 | B2R-092 | This is currently send as zip file manually and DAFRIN is created for loading. Currently there are manual tasks including number of days, applying percentage, updating account attributes and uploading the data thru DAFRIN into SOAR. B2R core team agreed to continue manual payroll costs accrual process in future state as well accepting FBDI worksheet will replace DAFRIN. The Yearly Payroll Cost Accrual file/s will need to go through a COA cross-walk and converted into FBDI before automatically getting uploaded into ERP." | OCTO | PeopleSoft | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | This is a semi automated interface.Based on OIC capability (file & ftp adapters, mapping etc.) and file size limitations OIC is best suited. | Manual upload Process | TBD
I004 | Budget To Report | Peoplesoft - COA Data | Outbound | Automated | No | Send chart of accounts data from Oracle ERP to PeopleSoft. Peoplesoft will change possibly after phase 2 (Not only segments but also all relational master data) | High | Daily | No | New | Batch | Sync COA | 31 | Global | Permanent | Phase1 | Sprint4 | B2R-010 | This will need mapping of future state DIFS COA structure to COA of acceptable to PeopleSoft. File needs to be created and sent on a regular basis from oracle ERP format to PeopleSoft format. | OCFO | ERP | OCTO | PeopleSoft | Yes | Yes - We need it | OIC & SFTP | First time load and then incremental. As incremantal load won't be much OIC will be used. Based on OIC capability (file & ftp adapters, mapping etc.) and file size limitations OIC is best suited. | Granted acces to SOAR profiles | TBD
I005 | Budget To Report | WMATA - Benefits Interface | Inbound | Semi-Automated | No | Record the expenditures related to union employee (Metro Smart Trip – Transportation Benefit). Every month the employees are allotted $25 to commute to work based on contractual agreement. This interface/file is used to record the expense. This is needed for DIFS for an inbound accounting data into Oracle GL. | Medium | Monthly | Yes | Existing | Batch | Create Journal Entries | 6 | Global | Permanent | Phase1 | Sprint4 | B2R-146 | Currently an Extract is sent manually and converted into DAFRIN manually before loading them into SOAR. For DIFS cross-walks needs to happen before FBDI upload. | WMATA | NA | OCFO | ERP | Yes | Need to check with Accounting operations during implementation | OIC & SFTP | This is a semi automated interface. Based on OIC capability (file & ftp adapters, mapping ect.) and file size limitations OIC is best suited. | Manual upload Process | TBD
I006 | Budget To Report | WMATA - Benefits Interface Debit | Inbound | Semi-Automated | Yes | Record the unused portion of the $25 benefit that employees receive. Every month the employees are allotted $25 to commute to work based on contractual agreement. This interface/file is used to reduce the expenditure for the unused portion. This is needed for DIFS for an inbound accounting data into Oracle GL | Medium | Monthly | Yes | Existing | Batch | Create Journal Entries | 6 | Global | Permanent | Phase1 | Sprint4 | B2R-147 | Currently an Extract is sent manually and converted into DAFRIN manually before loading them into SOAR. For DIFS cross-walks needs to happen before FBDI upload. | WMATA | NA | OCFO | ERP | Yes | Need to check with Accounting operations during implementation | OIC & SFTP | This is a semi automated interface. Based on OIC capability (file & ftp adapters, mapping etc.) and file size limitations OIC is best suited. | Manual upload Process | TBD
I007 | Budget To Report | PeopleSoft - Health Fees Allocation Refund of charges | Inbound | Semi-Automated | Yes | Allocate Health Fees back to agency budgets and to federal grants. Peoplesoft has over-collected health fees (if they are grants, projects they need to be reallocated). It's cross agency-intra district. Its just a journal entry. This needs to be automated if possible in the new DIFS system. This is needed for DIFS for an inbound accounting data into Oracle GL | Medium | Annually | Yes | Existing | Batch | Create Journal Entries | 6 | Global | Permanent | Phase1 | Sprint4 | B2R-148 | Currently an Extract is sent manually and converted into DAFRIN manually before loading them into SOAR. This will need calculation of over-collection and implementing business rules for re-allocation. | OCTO | PeopleSoft | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | This is a semi automated interface. Based on OIC capability (file & ftp adapters, mapping etc.) and file size limitations OIC is best suited. | Manual upload Process | TBD
I008 | Budget To Report | GSC - Leave Allocation | Inbound | Semi-Automated | Yes | Allocation of Employee Leave. Leave Allocation of Financial Management GSC. This is needed for DIFS for an inbound accounting data into Oracle GL. This is agency specific and belongs to cluster GSC. | Medium | Monthly | Yes | Existing | Batch | Create Journal Entries | 6 | Global | Permanent | Phase1 | Sprint4 | B2R-149 | Currently an Extract is sent manually and converted into DAFRIN manually before loading them into SOAR | GSC | NA | OCFO | ERP | Yes | Need to check with Ginny Brant (KT0)during implementation | OIC & SFTP | This is a semi automated interface. Based on OIC capability (file & ftp adapters, mapping etc.) and file size limitations OIC is best suited. | N/A | TBD
I009 | Order To Cash | iNOVAH - Cash Collection | Inbound | Automated | No | Receive cash collection data from all agencies into iNOVAH which sends this data everyday to SOAR. They send two files, the first file which comes at 7pm everyday. The second file comes after 15 minutes of the first file and has any missing transactions. Both files/interfaces have the same data format and data. This data needs to come to DIFS going forward. Merged the two files as one interface | High | Daily | Yes | Existing | Batch | Create Journal Entries | 6 | Global | Permanent | Phase1 | Sprint4 | O2C-137 O2C-054 O2C-071 O2C-041 | Merged the two iNOVAH files as one interface as they are the same format and have same data | OCFO/OFT | iNOVAH | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | Volume is not that high and based on OIC capability (file & ftp adapters, mapping etc.) and file size limitations OIC is best suited. | FTPS 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | TBD
I010 | Order To Cash | OFT DMS/DBC - Debt Service Payment Postings | Inbound | Automated | No | Crediting Cash and paying out expenditures Recorded as journal entries. Bookings for bonds, debt etc. Data Source DMS/DBC system from OFT. Potentially replaced by Kyriba Treasury. Need to confirm with JoseLuis if this will be replaced by Kyriba or the interface stays. | Medium | As Needed | Yes | Existing | Batch | Create Journal Entries | 6 | Global | Permanent | Phase1 | Sprint5 | O2C-151 | These are journal entry booking for bonds, debts etc. Need to confirm with JoseLuis If this will be in Kyriba. If it is then remove this interface. If not in Kyriba then this stays | OCFO/OFT | DMS/DBC | OCFO | ERP | Yes | Yes - We need it (further discussion needed to confirm integration between KYRIBA and ERP) | OIC & SFTP | Volume is not that high and based on OIC capability (file & ftp adapters, mapping etc.) and file size limitations OIC is best suited. | FTPS 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | TBD
I011 | Order To Cash | Banks - Bank Statements Reconciliation | Inbound | Automated | No | Receive daily bai2 files for bank account reconciliation. It comes from banks. It will be multiple banks. This has been updated from Kyriba to Banks as process has changed. The files from banks will be consumed by both Kyriba and ERP. | High | Daily | No | New | Batch | Create Bank Statement Lines | 10 | ATO | Permanent | Phase1 | Sprint5 | O2C-088 | Updated this from Kyriba to Banks. The flow has changed. These files from banks will be consumed by both Kyriba and ERP | OCFO | BANKS | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable and within OIC file size limitations | N/A | TBD
I012 | Order To Cash | Kyriba - GL Posting Entries | Inbound | Automated | No | Receive journal entry data for movement of cash between bank accounts of different agencies or payment made directly from Kyriba. | Medium | Daily | No | New | Batch | Create Journal Entries | 6 | ATO | Permanent | Phase1 | Sprint5 | O2C-151 |  | OCFO | KYRIBA | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable and within OIC file size limitations | N/A | TBD
I013 | Order To Cash | MITS - Tax Revenue Collection | Inbound | Automated | No | Receive tax revenue collected by MITS and enter as journal entries (manual JV). This needs to be automated as currently it's entered manually in SOAR. | High | Daily | No | Existing | Webservice | Create Journal Entries | 6 | ATO | Permanent | Phase1 | Sprint5 | O2C-078 O2C-070 | Currently a manual process- to be automated | OCFO/OFT | MITS | OCFO | ERP | Yes | Yes - We need it (need to discuss with functional team) | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable and within OIC file size limitations | N/A | TBD
I014 | Order To Cash | Wells Fargo - Remote Deposit and Lockbox | Inbound | Automated | No | Record the checks deposited using Wells Fargo Remote Deposit Application and Lockboxes. A notification be sent out to respective AR Personnel for the status of the deposits. | High | Daily | No | New | Batch | Create Receipts | 15 | Global | Permanent | Phase1 | Sprint4 Sprint5 | O2C-072 O2C-073 |  | Wells Fargo | NA | OCFO | ERP | Yes | Yes - We need it (further discussion needed to confirm integration between KYRIBA and ERP) | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable and within OIC file size limitations | N/A | TBD
I015 | Order To Cash | Well Fargo - Record Interest Income | Inbound | Automated | No | Record Interest income in an automated manner upon receipt and processing of Bank Statements. | Medium | Daily | No | New | Batch | Create Receipts | 15 | ATO | Permanent | Phase1 | Sprint4 | O2C-074 |  | Wells Fargo | NA | OCFO | ERP | Yes | Yes - We need it (further discussion needed to confirm integration between KYRIBA and ERP) | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable and within OIC file size limitations | N/A | TBD
I016 | Order To Cash | MITS - Real Property Tax Revenue & Lockbox Payments | Inbound | Automated | No | Receive real property tax revenue and lockbox payments from MITS new real property system. Its manual right now but needs to be automated in DIFS. Legacy system is county fusion. | Medium | Daily | No | New | Webservice | Create Journal Entries | 6 | ATO | Permanent | Phase1 | Sprint5 | O2C-091 | Currently a manual process- to be automated. Merged Real Property Lockbox payments interface with this one. | OCFO/OFT | MITS | OCFO | ERP | Yes | Yes - We need it (need to discuss with functional team) | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I017 | Budget | QuickBase - Performance Plans (KPI) | Inbound | Automated | No | Performance Plan Data (KPI) from agencies goes into Oracle Planning. The data is from the QuickBase app. | Medium | Daily | No | Existing | Batch | Create Performance Plans | 13 | Global | Permanent | Phase2 | Sprint8 | BUD-061 |  | Mayor/OCTO | QuickBase | OCFO | Oracle Planning | Yes | Yes - We need it | OIC & SFTP | Data volume is not that high. OIC is best suited with it's file, ftp adapter, mapping and transformation capabilities.This is as per what we know as of now. | N/A | TBD
I018 | Budget | PeopleSoft - Position Data | Inbound | Automated | No | Position data from PeopleSoft to Oracle Planning. ALL Active and Inactive positions within the HCM system; includes both filled and vacant. | High | Daily | No | New | Batch | Sync Position Master Data | 18 | Global | Permanent | Phase2 | Sprint5 | BUD-150 BUD-151 | Need to convert PeopleSoft data into Oracle Planning format and there is crosswalk | OCTO | PeopleSoft | OCFO | Oracle Planning | Yes | Yes - We need it | OIC, DBCS & SFTP | Based on the Positon design discussion and requirements. Data volume is not high and files will be in CSV format. DBCS to store and compare previous run batch data. | Manual upload Process BFA | TBD
I019 | Budget | PeopleSoft - Employee Data | Inbound | Automated | No | Employee Master Data from PeopleSoft to Oracle Planning | High | Daily | No | New | Batch | Sync Employee Master Data | 17 | Global | Permanent | Phase2 | Sprint5 | BUD-150 BUD-151 | Need to convert PeopleSoft data into Oracle Planning format and there is crosswalk | OCTO | PeopleSoft | OCFO | Oracle Planning | Yes | Yes - We need it | OIC, DBCS, & SFTP | Based on the Employee design discussion and requirements. Data volume is not high and files will be in CSV format. DBCS to store and compare previous run batch data. | Manual upload Process BFA | TBD
I020 | Budget | PeopleSoft - Salary Data | Inbound | Automated | No | Salary Master Data from PeopleSoft to Oracle Planning | High | Daily | No | New | Batch | Sync Salary Master Data | 19 | Global | Permanent | Phase2 | Sprint5 | BUD-150 BUD-151 | Need to convert PeopleSoft data into Oracle Planning format and there is crosswalk | OCTO | PeopleSoft | OCFO | Oracle Planning | Yes | Yes - We need it | OIC, DBCS & SFTP | Based on the previous Positon & design discussion and requirements. Data volume is not high and files will be in CSV format. DBCS to store and compare previous run batch data. | Manual upload Process BFA | TBD
I021 | Budget | Oracle Planning - Award Funding Update | Outbound | Automated | No | Update award fund, funding amount and funding amount summary from Oracle Planning to Oracle PPM. Decision based on proms and grams replacement. Need to be valdated for phase1 or phase2 | High | Daily | No | New | Webservice | Create Award Funding | 21 | Global | Permanent | Phase2 | Sprint2 | P&G-135 P&G-002 BUD-162 | Transformation will be required to create the PPM data in ERP format ; Needed for Budget Execution; When we do BF, we are formulating on FY22. The second interface of funding amount summary merged with this one as per Rohan's feedback as he feels its one webservice. Preconstruction - As per the feedback during preconstruction this interface is needed. Accoridng to the email from Rohan on 10/28. | OCFO | Oracle Planning | OCFO | ERP | Yes | Yes - We need it | OIC | OIC is best suited as this will be implemented using the out of box Webservice REST APIs. REST Adapter and Transformation/Mapping capability of OIC will be leveraged to implement this interface. | N/A | TBD
I025 | Budget | ERP - GL Actuals | Outbound | Automated | No | GL actuals (excluding project and award) data from Oracle ERP GL to Oracle Planning. This is via in-built adapter | Low | Daily | No | New | Webservice | Send GL Actuals and Budget | 23 | Global | Permanent | Phase1 | Sprint4 | BUD-029 BUD-153 | Confirmed by Chris and Randall that this is needed. | OCFO | ERP | OCFO | Oracle Planning | Yes | Yes - We need it | Built-In-Adapter | Built In Adapter from Oracle. Involves configuration and testing in both EPM and ERP. | N/A | TBD
I023 | Budget | ERP - Projects Actuals | Outbound | Automated | No | Projects Actuals data from Oracle PPM to Oracle Planning. Oracle released a built adapter recently. Need to figure out if custom development is needed or not | High | Daily | No | New | Webservice | Create Project Actuals | 24 | Global | Permanent | Phase1 | Sprint5 | BUD-029 | This includes the PS and NPS details. The PS details would have employee and position information, adding to the complexity. | OCFO | ERP | OCFO | Oracle Planning | Yes | Yes - We need it | OIC & SFTP | Internal integration between DIFS Oracle Cloud apps. OIC is best suited as in the future we may have built-in adatpers and easier to transition if needed. | N/A | TBD
I024 | Budget | ERP - Chart of Accounts | Outbound | Automated | No | Chart of accounts segments data from ERP to Oracle Planning | Low | Daily | No | New | Batch | Sync COA | 31 | Global | Permanent | Phase1 | Sprint4 | BUD-154 | Multiple interfaces needed for the CoA segments. Made it low as most of the dev done in preconstruction. Need to update for one or two segments during implementation | OCFO | ERP | OCFO | Oracle Planning | Yes | Yes - We need it | OIC & SFTP | Based on the internal design discussion and requirements. Data volume is not high and files will be in CSV format. Incremental data will be low volume. | N/A | TBD
I027 | Budget | Oracle Planning - Approved GL Budget | Outbound | Automated | No | Approved GL budget from Oracle Planning to Oracle ERP GL. This is via in-built adapter. This needs to go-live after budget is formulated in Oracle Planning. This interface will also be used for reprogramming and modifications. | Low | Daily | No | New | Batch | Send GL Actuals and Budget | 23 | Global | Permanent | Phase1 | Sprint5 | BUD-154 |  | OCFO | Oracle Planning | OCFO | ERP | Yes | Yes - We need it | Built-In-Adatper | Built In Adatper from Oracle. Involves configuration and testing in both EPM and ERP. | N/A | TBD
I026 | Budget | Oracle Planning - Project Budget | Outbound | Automated | No | Project Budget data from Oracle Planning to Oracle ERP PPM. This needs to go-live after budget is formulated in Oracle Planning. This interface will also be used for reprogramming and modifications. Oracle released recently a built-in adapter for this. Need to check if adapter or custom. | High | Daily | No | New | Batch | Create Project Budget | 25 | Global | Permanent | Phase1 | Sprint5 | BUD-154 | This could be multiple interfaces because of the different budget allotment and authority (6 and 1) figures. Transformation will be required to create the PPM load file in the FBDI format. | OCFO | Oracle Planning | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | Internal integration between DIFS Oracle Cloud apps. OIC is best suited as in the future we may have built-in adapters and easier to transition if needed. | N/A | TBD
I051 | Procure To Pay | OSSE EGMS - Intra District Funds Transfer | Inbound | Automated | No | Intra district funds transfer and payment data (daycare, academy's and institutions) from EGMS OSSE. This may need to be split into two (funds transfer & payments) | High | Daily | Yes | Existing | Batch | Create Invoice/Credit Memo and Create Journal Entries | 7 | Agency | Permanent | Phase1 | TBD | P2P-213 P2P-215 |  | OSSE | EGMS | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | Existing interface. Volume is manageable within OIC | FTPS soaregms.seo.dc.gov 10.201.1.196 port: 21 | TBD
I028 | Budget | CARSS - Requested Budget | Outbound | Automated | No | Requested budget for all capital projects from Oracle Planning to CARSS. Currently this data goes from PROMS to CARSS. Once proms and grams decision is made need to be validated if phase1 or phase2 | Medium | Monthly | No | Existing | Batch | Send Budget Data | 28 | Global | Permanent | Phase2 | Sprint6 | BUD-148 BUD-364 | This needed as per confirmation from Budget team. | OCFO | Oracle Planning | OCFO | CARSS | Yes | Yes - We need it | OIC & SFTP | Manageable volume of data | N/A | TBD
I029 | Budget | QuickBase - Budget | Inbound | Semi-Automated | No | Budget from QuickBase DCPS to Oracle Planning. Sushant to confirm if phase1 or phase2. | Medium | Daily | No | Existing | Batch | Create Budget Data | 11 | Agency | Permanent | Phase2 | Sprint5 | BUD-117 |  | DCPS | QuickBase | OCFO | Oracle Planning | Yes | Yes - We need it | OIC & SFTP | Data volume is not that high. This is as per what we know as of now. | N/A | TBD
I030 | Projects & Grants | Peoplesoft - Payroll Costs | Inbound | Automated | No | Payroll costs (payroll, deductions, expenses) should go into PPM from PeopleSoft | Medium | Bi-Weekly By Pay Group | No | New | Batch | Accumulate Labor Costs | 8 | Global | Permanent | Phase1 | Sprint3 | P&G-108 | Complexity medium as we have three separate interfaces for P2P and B2R and additionally needs to go to this module. | OCTO | PeopleSoft | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I031 | Projects & Grants | PeopleSoft - Employee Data | Inbound | Automated | No | Employee Master Data from PeopleSoft to ERP PPM along with Employee expenditures. | Medium | Daily | No | New | Batch | Sync Employee Master Data | 17 | Global | Permanent | Phase1 | Sprint3 | P&G-044 | Employee data comes from PeopleSoft for both Oracle Planning and ERP. Needs to split and load here as well. Moved to Phase1 after discussion with team. | OCTO | PeopleSoft | OCFO | ERP | Yes | Yes - We need it / 485 Rpt????? | OIC | Based on the design discussion and requirements with the team. Data volume is not high and Webservice will be implemtented. | N/A | TBD
I032 | Projects & Grants | EGMS - Events Revenue & Billing | Inbound | Automated | No | EGMS (OSSE) – Electronic Grants Management System expenditures. The reimbursable portion needs to be billed and revenue be generated. | Medium | Daily | No | New | Batch | Accumulate Labor Costs | 8 | Agency | Permanent | Phase1 | Sprint 3 | P&G-118 | New interface added for P&G. We need this new interface. It was confirmed during Preconstruction validation | OSSE | EGMS | OCFO | ERP | Yes | Yes, We need it. | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I033 | Acquire To Retire | CARSS - Assets Extract | Outbound | Automated | No | Takes data from all these systems and formulates budget plan for asset. DIFS needs to feed asset data to CARSS. | Medium | Monthly | No | Existing | Batch | Send Asset Data | 27 | Global | Permanent | Phase1 | TBD | A2R-111 |  | OCFO | ERP | OCFO | CARSS | Yes | YES - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I034 | Procure To Pay | OSSE OECD - Day Care Grant Vendor Payment | Inbound | Automated | No | Grant vendor voucher data from OSSE OECD system. The data is not in DAFRIN format. SOAR converts the incoming data into DAFRIN before loading into the system. | Medium | Daily | No | Existing | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-206 |  | OSSE | OECD | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTP 10.83.3.67 | TBD
I035 | Procure To Pay | MMIS - Medicaid Vendor Payment | Inbound | Automated | No | Medicaid payables daily data from DHCF. Medicaid Payments including for alliance vendor. It's not in DAFRIN but gets converted in soar. The data which comes is not in one record. It's in 3 lines. Three records constitute one transaction. Merged the alliance vendor file with this one as same file format. Two files are being sent by MMIS. One for all vendors and one for alliance. They also send one time vendors and these need to be created in DIFS as well along with create invoice. | High | Daily | No | Existing | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-207 P2P-081 | Currently it's only inbound with SOAR but for DIFS DHCF wants an outbound Payment status update. Merged the alliance vendor file with this one as same file format. Two files are being sent by MMIS. One for all vendors and one for alliance. | DHCF | MMIS | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTP 192.168.202.20 (Mainframe) | TBD
I036 | Procure To Pay | MMIS - Medicaid Vendor Payment Response | Outbound | Automated | No | Payment status response back to MMIS. This is currently no there in SOAR but will be implemented going forward. | Medium | Daily | No | Existing | Batch | Send Payment Status | 37 | Agency | Permanent | Phase1 | TBD | P2P-207 P2P-224 | Added the outbound as separate interface instead of one row as both (Updated outbound interface from "New" to "Existing" as part of pre-construction phase analysis. - Ashis on 08/28/20) | OCFO | ERP | DHCF | MMIS | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTP 192.168.202.20 (Mainframe) | TBD
I037 | Procure To Pay | CFSA Faces - Child Care Provider Payment | Inbound | Automated | No | Child care provider payment data from CFSA. Payment status files go back to CFSA for updates. They also send one time vendors and these need to be created in DIFS as well along with create invoice. | High | Daily | No | Existing | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-208 |  | CFSA | Faces | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | Creating Tape in OCTO Mainframe | TBD
I038 | Procure To Pay | CFSA Faces - Child Care Provider Payment Response | Outbound | Automated | No | Payment status response back to CFSA | Medium | Daily | No | Existing | Batch | Send Payment Status | 37 | Agency | Permanent | Phase1 | TBD | P2P-208 P2P-224 |  | OCFO | ERP | CFSA | Faces | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC |  | TBD
I039 | Procure To Pay | DDS RSA - Grant Vendor Payment | Inbound | Automated | No | Grant vendor payment request data from Department of Disability Services. It is managed by their Vendor Libera and system is RSA | Medium | Weekly | Yes | Existing | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-209 |  | DDS | RSA | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTP dcrsa-vrapp.libera.com 52.61.164.182 port: 21 | TBD
I040 | Procure To Pay | DDS RSA - Grant Vendor Payment Response | Outbound | Automated | No | Payment status response back to DDS RSA | Medium | Weekly | Yes | Existing | Batch | Send Payment Status | 37 | Agency | Permanent | Phase1 | TBD | P2P-209 P2P-224 | Added outbound | OCFO | ERP | DDS | RSA | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTP dcrsa-vrapp.libera.com 52.61.164.182 port: 21 | TBD
I041 | Procure To Pay | DMV Destiny- Refund of Traffic Fines | Inbound | Automated | No | Receive traffic fines refund data and issue payments to DC residents | Medium | Weekly | Yes | Existing | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-280 |  | DMV | Destiny | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | TBD
I042 | Procure To Pay | DMV Destiny- Refund of Traffic Fines Response | Outbound | Automated | No | Payment status back to DMV from DIFS for the traffic fines refund payments. | Medium | Weekly | Yes | Existing | Batch | Send Payment Status | 37 | Agency | Permanent | Phase1 | TBD | P2P-280 P2P-224 |  | OCFO | ERP | DMV | Destiny | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | TBD
I043 | Procure To Pay | OFT - Unclaimed Property | Inbound | Automated | No | Unclaimed Property data from OFT's Third party vendor system by Kelmar. Payment requests to issue checks | High | Daily | Yes | Existing | Batch | Create Invoice | 5 | ATO | Permanent | Phase1 | Sprint5 | P2P-255 | Making it high as building framework for payment requests for rest of payment interfaces excluding Ariba. Need to find out the system name as Kelmar is the Vendor. | OCFO/OFT | Kelmar | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | TBD
I044 | Procure To Pay | OSSE ONEAPP - University Payments | Inbound | Automated | No | Payment request data from OSSE for universities | Medium | Twice Per Week | Yes | Existing | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-211 |  | OSSE | ONEAPP | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS Ftps.osse.dc.gov 10.83.3.67 port: 21 | TBD
I045 | Procure To Pay | OSSE ONEAPP - University Payments Response | Outbound | Automated | No | Payment status response to OSSE | Medium | Twice Per Week | Yes | Existing | Batch | Send Payment Status | 37 | Agency | Permanent | Phase1 | TBD | P2P-211 P2P-224 |  | OCFO | ERP | OSSE | ONEAPP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS Ftps.osse.dc.gov 10.83.3.67 port: 21 | TBD
I046 | Procure To Pay | OSSE NSCAPS - Nutrition Services Payment Request | Inbound | Automated | No | Payment request data from OSSE for nutrition services | Medium | Twice Per Week | Yes | Existing | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-212 |  | OSSE | NSACPS | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS 10.83.3.67 port: 21 | TBD
I047 | Procure To Pay | OSSE NSCAPS - Nutrition Services Payment Response | Outbound | Automated | No | Payment status response data from ERP to OSSE for nutrition services | Medium | Twice Per Week | Yes | Existing | Batch | Send Payment Status | 37 | Agency | Permanent | Phase1 | TBD | P2P-212 P2P-224 |  | OCFO | ERP | OSSE | NSACPS | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS 10.83.3.67 port: 21 | TBD
I048 | Procure To Pay | DOES - Employers Unemployment Contribution Refunds | Inbound | Automated | No | Receive employer unemployment contribution refund data from DOES | Medium | Daily | Yes | Existing | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-213 | System name TBD. | DOES | DUTAS (District Unemployment Tax Accounting System) | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | OCTO mainframe - copy file into SOAR dataset | TBD
I049 | Procure To Pay | OSSE BITSEE- Special Education Not Encumbered Payment Requests | Inbound | Automated | No | Payment Request for special education services from OSSE BITSEE system. | Medium | As Needed | Yes | Existing | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-265 |  | OSSE | BITSEE | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS 10.83.3.67 port: 21 | TBD
I050 | Procure To Pay | OSSE BITSEE- Special Education Not Encumbered Payment Response | Outbound | Automated | No | Payment status response for special education services back to OSSE BITSEE system. | Medium | As Needed | Yes | Existing | Batch | Send Payment Status | 37 | Agency | Permanent | Phase1 | TBD | P2P-265 P2P-224 |  | OCFO | ERP | OSSE | BITSEE | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS 10.83.3.67 port: 21 | TBD
I052 | Procure To Pay | MITS - State Income Liability Offset (SITLP) | Inbound | Automated | No | State Income Liability Offset. This data comes from MITS system (SITLP). This will record in O2C also as revenue collection. | Very High | Daily | Yes | Existing | Batch | Create Invoice/Credit Memo and Create Journal Entries | 7 | ATO | Permanent | Phase1 | Sprint5 | P2P-205 O2C-061 O2C-082 |  | OCFO/OFT | MITS | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | Mainframe dataset has been created by MITS/ITS - copy file into SOAR dataset | TBD
I053 | Procure To Pay | MITS - DC Vendor Offset | Inbound | Automated | No | DC Vendor Offset Data from MITS. After the offset, SOAR sends back 3 status files to MITS. After the offset ITS legacy system sends notices to the vendor. This will record in O2C as well. Offset receivable balance in AR and notice back to MITS to send it to vendor | High | Biweekly | No | Existing | Batch | Create Invoice/Credit Memo and Create Journal Entries | 7 | ATO | Permanent | Phase1 | Sprint5 | P2P-205 O2C-061 O2C-082 |  | OCFO/OFT | MITS | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | Mainframe dataset has been created by MITS/ITS - copy file into SOAR dataset | TBD
I055 | Procure To Pay | TOP - State Federal Liability Offset | Inbound | Automated | No | State Federal Liability Offset - MITS/TOP. This interface has many files going back and forth between MITS/TOP and ERP with multiple steps. Updated the direction to both as files have to go back to TOP as well. | Very High | Daily | No | Existing | Batch | Create Invoice/Credit Memo and Create Journal Entries | 7 | Global | Permanent | Phase1 | Sprint5 | P2P-205 O2C-061 O2C-082 |  | OCFO/OFT | MITS/TOP | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | TBD
I054 | Procure To Pay | MITS - DC Vendor Offset Response | Outbound | Automated | No | Outbound response to MITS for DC Vendor Offset | High | Biweekly | No | Existing | Batch | DC Vendor Liability Offset Response | 38 | ATO | Permanent | Phase1 | Sprint5 | P2P-205 O2C-061 O2C-082 | We need to explore if DIFS can print NPO file (Notice) | OCFO | ERP | OCFO/OFT | MITS | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | Mainframe datasets / Reports have been created by SOAR and sent to MITS/ITS | TBD
I059 | Procure To Pay | IRS - 1099M Processing | Outbound | Automated | No | Send 1099 yearly data. This is a report in Oracle. | Low | Year End | No | Existing | Batch | Create Report - 1099 | 26 | Global | Permanent | Phase1 | Sprint4 | P2P-219 |  | OCFO | ERP | IRS | NA | Yes | YES - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | Mainframe file sent to OFOS | TBD
I056 | Procure To Pay | TOP - State Federal Liability Offset Response | Outbound | Automated | No | State Federal Liability Offset - MITS/TOP response to MITS from ERP. This interface has many files going back and forth between MITS/TOP and ERP with multiple steps. Updated the direction to both as files have to go back to TOP as well. | High | Daily | No | Existing | Batch | TOP Liability Offset Response | 39 | Global | Permanent | Phase1 | Sprint5 | P2P-205 O2C-061 O2C-082 | We need to explore if DIFS can print NPO file (Notice) | OCFO | ERP | OCFO/OFT | MITS/TOP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS 10.16.12.216 Port: 990 (OCIO Go-Anywhere Server) | TBD
I057 | Procure To Pay | Banks - ACH Payments | Outbound | Automated | No | Send ACH payment data to Wells Fargo and Citibank | High | Daily | No | Existing | Batch | Create ACH Payment File | 20 | Global | Permanent | Phase1 | Sprint5 | P2P-109 | ACH payments will be generated in DIFS and sent to Bnak through Kyriba. Kyriba will work as a payment hub. | OCFO | ERP | OCFO/OFT | KYRIBA | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS safetrans.wellsfargo.com Port: 21 PFTPS-CITI.MS.GXS.COM Port: 2121 | TBD
I058 | Procure To Pay | Checkwrite - Warrant and Invoice file | Outbound | Automated | No | Send Payments checks via the check write system | High | Daily | Yes | Existing | Batch | Create Check Payment File | 22 | Global | Permanent | Phase1 | Sprint5 | P2P-218 | During pre-construction phase, System has been chnged from Check-write ti Kyriba. All pyment transaction from DIFS that includes both checks and ACH will be routed to Bank through Kyriba. | OCFO | ERP | OCFO/OFT | KYRIBA | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | Files created in Mainfram are accessed by checkwrite system that also runs in Mainfram | TBD
I083 | Order To Cash | Kyriba - Transactions Cash Forecasting | Outbound | Automated | No | Send all cash related transactions that can be used for cash forecasting, cash reconciliation and cash balances from ERP to Kyriba | Medium | Daily | No | New | Batch | Send Payments, Deposits, Cash Transfers & Journal Entries | 29 | ATO | Permanent | Phase1 | Sprint5 | O2C-151 |  | OCFO | ERP | OCFO | KYRIBA | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I060 | Procure To Pay | E-Risk - PSWCP Vendor Payments | Inbound | Automated | No | Payment request data from PSWCP from E-Risk system | Medium | Daily | Yes | Existing | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-221 |  | ORM | ERISK | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS ent-ftps.dc.gov 10.86.26.91 port: 21 | TBD
I061 | Procure To Pay | E-Risk - PSWCP Vendor Payment Response | Outbound | Automated | No | Payment status response data from ERP to PSWCP E-Risk system | Medium | Daily | Yes | Existing | Batch | Send Payment Status | 37 | Agency | Permanent | Phase1 | TBD | P2P-221 |  | OCFO | ERP | ORM | ERISK | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS ent-ftps.dc.gov 10.86.26.91 port: 21 | TBD
I062 | Procure To Pay | PeopleSoft - Payroll Tax Deductions | Inbound | Automated | No | Payroll tax deduction payment request data from PeopleSoft. These are payments to IRS, States etc. | Medium | By Payroll | Yes | Existing | Batch | Create Invoice | 5 | Global | Permanent | Phase1 | Sprint5 | P2P-223 | Not combining with PeopleSoft Expenses interface as these are two different files. Tax deductions and Expenses are treated differently in PeopleSoft | OCTO | PeopleSoft | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | Manual upload Process | TBD
I022 | Budget | ERP - P&G Master Data | Outbound | Automated | No | Projects and Grants Master data from Oracle ERP PPM to Oracle Planning. Depends on proms and grams replacement if phase1 or phase2 | High | Daily | No | New | Batch | Sync P&G Master Data | 33 | Global | Permanent | Phase2 | Sprint6 | BUD-152 | These interfaces will be used to build the Projects and Awards hierarchy in Oracle Planning. Multiple interfaces would be needed to load the active projects and awards and remove the closed ones. | OCFO | ERP | OCFO | Oracle Planning | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I064 | Procure To Pay | PeopleSoft - Union Dues Refund | Inbound | Semi-Automated | Yes | Over-collected union dues refunds to employees from PeopleSoft. | Medium | By Payroll | Yes | Existing | Batch | Create Invoice | 5 | Global | Permanent | Phase1 | Sprint5 | P2P-226 | Currently an Extract is sent manually and converted into DAFRIN manually before loading them into SOAR; Possible Consolidation with tax payments interface during design phase. | OCTO | PeopleSoft | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | Manual upload Process | TBD
I065 | Procure To Pay | Banks - PCard Allocation | Inbound | Automated | No | The process in DIFS is changing. Bank will send a card transaction file daily and DIFS will create payment request and send it to the bank to issue checks. Moving forward with the assumption that we will use Expenses in Oracle and hence is required. | Medium | Monthly | No | Existing | Batch | Create Expense Items | 12 | Global | Permanent | Phase1 | TBD | P2P-073 | Currently an Extract is sent manually and converted into DAFRIN manually before loading them into SOAR. Updated this from TBD to In-Scope as per new project direction. Moving forward with the assumption that on that we will use Expenses in Oracle, and hence this to required. | OCP/Banks | NA | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | Manual upload Process | TBD
I066 | Procure To Pay | ARIBA OnPrem - ERP Create and Update (chg/cancel) Requisitions On Prem | Inbound With ACK | Automated | No | Create and Update (change/cancel) Requisitions in ERP from Ariba OnPrem. Merged Funds Check here as it is part of this interface. | Very High | Near real time | No | Existing | Webservice | Create and Update Requisitions | 3 | Global | Temporary | Phase1 | Sprint3 | P2P-056 P2P-057 P2P-181 P2P-188 P2P-160 |  | OCP | ARIBA-OnPrem | OCFO | ERP | Yes | Yes - We need it | OIC | All ARIBA-OnPrem integrations will be near real time webservices. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | Oracle SOA and CICS adapter | TBD
I067 | Procure To Pay | ARIBA Cloud - ERP Create and Update Requisitions | Inbound With ACK | Automated | No | Create and Update Requisitions in ERP from Ariba Cloud. Merged Funds Check here as it is part of this interface. | Medium | On Demand | No | Existing | Webservice | Create and Update Requisitions | 3 | Global | Permanent | TBD | Sprint3 | P2P-275 P2P-276 P2P-279 P2P-056 P2P-057 P2P-181 P2P-160 |  | OCP | ARIBA-Cloud | OCFO | ERP | Yes | On hold for future implementation | TBD | Future implementation. Will be decided when ARIBA Cloud is being implemented. | N/A | TBD
I068 | Procure To Pay | ARIBA OnPrem - ERP Create and Update Purchase Orders | Inbound With ACK | Automated | No | Create and Update Purchase Orders in ERP from Ariba OnPrem. Merged Funds Check here as it is part of this interface. | Very High | On Demand | No | Existing | Webservice | Create and Update Purchase Orders (PO) | 2 | Global | Temporary | Phase1 | Sprint3 | P2P-060 P2P-183 P2P-184 P2P-188 P2P-189 |  | OCP | ARIBA-OnPrem | OCFO | ERP | Yes | Yes - We need it | OIC | All ARIBA-OnPrem integrations will be near real time webservices. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | Oracle SOA and CICS adapter | TBD
I069 | Procure To Pay | ARIBA Cloud - ERP Create and Update Purchase Orders | Inbound With ACK | Automated | No | Create and Update Purchase Orders in ERP from Ariba Cloud. Merged Funds Check here as it is part of this interface. | Medium | On Demand | No | Existing | Webservice | Create and Update Purchase Orders (PO) | 2 | Global | Permanent | TBD | Sprint3 | P2P-272 P2P-275 P2P-277 P2P-279 |  | OCP | ARIBA-Cloud | OCFO | ERP | Yes | On hold for future implementation | TBD | Future implementation. Will be decided when ARIBA Cloud is being implemented. | N/A | TBD
I070 | Procure To Pay | ARIBA OnPrem - ERP Create and Update Suppliers | Inbound | Automated | No | Create and Update Suppliers in ERP from Ariba OnPrem. | High | Daily | No | Existing | Webservice | Create and Update Suppliers | 4 | Global | Temporary | Phase1 | Sprint4 Sprint2 | P2P-146 P2P-201 P2P-203 |  | OCP | ARIBA-OnPrem | OCFO | ERP | Yes | Yes - We need it | OIC | All ARIBA-OnPrem integrations will be near real time webservices. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | Oracle SOA and CICS adapter | TBD
I071 | Procure To Pay | ARIBA Cloud - ERP Create and Update Suppliers | Inbound | Automated | No | Create and Update Suppliers in ERP from Ariba Cloud. | Medium | Daily | No | Existing | Webservice | Create and Update Suppliers | 4 | Global | Permanent | TBD | Sprint4 Sprint2 | P2P-274 P2P-203 |  | OCP | ARIBA-Cloud | OCFO | ERP | Yes | On hold for future implementation | TBD | Future implementation. Will be decided when ARIBA Cloud is being implemented. | N/A | TBD
I072 | Procure To Pay | ERP - ARIBA Cloud Create and Update Invoices | Outbound | Automated | No | Create and Update Invoices in Ariba OnPrem from ERP. Added this as per new project direction and some functionality from ARIBA OnPrem is being brought over to ERP. Currently they don't do have an outbound interface with SOAR. | High | Daily | No | New | Webservice | Sync Invoices | 32 | Global | Permanent | TBD | Sprint4 | P2P-256 P2P-199 | Updated to outbound from Oracle to PASS-ARIBA. | OCFO | ERP | OCP | ARIBA-Cloud | Yes | On hold for future implementation | TBD | Future implementation. Will be decided when ARIBA Cloud is being implemented. | N/A | TBD
I073 | Procure To Pay | ERP - ARIBA OnPrem Procurement Payment Status | Outbound | Automated | No | Update Payment Status back in ARIBA OnPrem. ARIBA OnPrem is getting payment status from CFO$OLVE. With new project direction we need this. Currently they don't do have an outbound interface with SOAR. | High | Daily | No | New | Webservice | Sync Procurement Payment Status | 34 | Global | Temporary | Phase1 | Sprint5 | P2P-256 P2P-199 |  | OCFO | ERP | OCP | ARIBA-OnPrem | Yes | Yes - We need it | OIC | All ARIBA-OnPrem integrations will be near real time webservices. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | Oracle SOA and CICS adapter | TBD
I074 | Procure To Pay | ERP - ARIBA Cloud Procurement Payment Status | Outbound | Automated | No | Update Payment Status back in ARIBA Cloud. Added this as per new project direction and some functionality from ARIBA OnPrem is being brought over to ERP. Currently they don't do have an outbound interface with SOAR. | High | Daily | No | New | Webservice | Sync Procurement Payment Status | 34 | Global | Permanent | TBD | Sprint5 | P2P-256 |  | OCFO | ERP | OCP | ARIBA-Cloud | Yes | On hold for future implementation | TBD | Future implementation. Will be decided when ARIBA Cloud is being implemented. | N/A | TBD
I075 | Procure To Pay | ERP- Ariba OnPrem Sync COA Master Data | Outbound | Automated | No | Send COA Segment data to Ariba OnPrem. Currently ARIBA pulls this data from SOAR tables on a daily basis. This data is sent as part of the request from ARIBA OnPrem to SOAR. | High | Daily | No | Existing | Webservice | Sync COA | 31 | Global | Temporary | Phase1 | TBD | P2P-267 | Added as per new project direction. Out of scope as this will taken care by a new extension. All consumers will consume data from the reverse cross walk extension. Added back as in-scope. PASS team wants to move to new DIFS COA. OCP has to confirm | OCFO | ERP | OCP | ARIBA-OnPrem | Yes | Yes - We need it | OIC | All ARIBA-OnPrem integrations will be near real time webservices. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | Oracle SOA and CICS adapter | TBD
I076 | Procure To Pay | ERP - Ariba Cloud Sync COA Master Data | Outbound | Automated | No | Send COA Segment data to Ariba Cloud. This data is needed when ARIBA ia creating Req's and PO's in DIFS. | Medium | Daily | No | Existing | Webservice | Sync COA | 31 | Global | Permanent | TBD | TBD | P2P-266 |  | OCFO | ERP | OCP | ARIBA-Cloud | Yes | On hold for future implementation | TBD | Future implementation. Will be decided when ARIBA Cloud is being implemented. | N/A | TBD
I077 | Procure To Pay | ERP - ARIBA OnPrem Sync Projects & Grants Master Data | Outbound | Automated | No | Projects and Grants master data from Oracle ERP PPM to ARIBA Cloud. Currently ARIBA pulls this data from SOAR tables on a daily basis. This data is sent as part of the request from ARIBA OnPrem to SOAR. | High | Daily | No | New | Webservice | Sync P&G Master Data | 33 | Global | Temporary | Phase1 | TBD | P2P-269 P2P-264 | Added as per new project direction. Out of scope as this will taken care by a new extension. All consumers will consume data from the reverse cross walk extension. Added back as in-scope. PASS team wants to move to new DIFS COA. OCP has to confirm | OCFO | ERP | OCP | ARIBA-OnPrem | Yes | Yes - We need it | OIC | All ARIBA-OnPrem integrations will be near real time webservices. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | Oracle SOA and CICS adapter | TBD
I078 | Procure To Pay | ERP - ARIBA Cloud Sync Projects & Grants Master Data | Outbound | Automated | No | Projects and Grants master data from Oracle ERP PPM to ARIBA Cloud. This is needed as there will be no PCA/Index in DIFS and this data should part of the request. | Medium | Daily | No | New | Webservice | Sync P&G Master Data | 33 | Global | Permanent | TBD | TBD | P2P-268 P2P-264 |  | OCFO | ERP | OCP | ARIBA-Cloud | Yes | On hold for future implementation | TBD | Future implementation. Will be decided when ARIBA Cloud is being implemented. | N/A | TBD
I079 | Budget To Report | UDC & Retirement Board - Payroll Reclass | Inbound | Semi-Automated | Yes | Reclassifying UDC and retirement board payroll from expenditures to receivables. The receivables comes to ATO. | Medium | Monthly | Yes | Existing | Batch | Create Journal Entries | 6 | Agency | Permanent | Phase1 | Sprint4 | B2R-150 | Currently an Extract is sent manually and converted into DAFRIN manually before loading them into SOAR. This will involve calculating UDC and retirement board payroll expenditures that needs to be classified as a receivable based on business rules. | UDC | NA | OCFO | ERP | Yes | UDC process needs to be evaluated before integration has been created. | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | Manual upload Process | TBD
I080 | Budget To Report | ERP - DW Master Data | Outbound | Automated | No | Updating this as per new direction for reporting. Master data from ERP to DW. Below is not applicable anymore Extract all Oracle ERP Cloud master data daily to CFO$OLVE for reporting. This is the full dump as per current functionality. This involves all crosswalk, transformation and lookup into the SOAR format which CFO$OLVE is expecting. This is a reporting interface. Updated the process area column as per Scott's request. | Very High | Daily/Weekly | No | Existing | Batch | Send ERP Master Data | 40 | Global | Permanent | Phase1 | Sprint5 | P2P-222 B2R-151 | Updated as per new project direction to DW not CFO$OLVE. Preconstruction - Related to EDW dashboards for Workstream 11 - Establish OCFO ER strategy. During implementation we will decide the number of extracts/details and if this is needed based on the ER strategy. This was updated during Preconstruction Interface validation. Based on the meeting with District on 1/12/21 as part of preconstruction these have been updated as optional. | OCFO | ERP | OCFO | DW | Optional | Optional | ODI, DBCS & SFTP | Large volume of data with complex data mapping and COA translations. This is to Datawarehouse and ODI ETL tool is best suited for this. | FTP 10.16.12.78 | TBD
I081 | Budget To Report | ERP - DW Transactional Data | Outbound | Automated | No | Updating this as per new direction for reporting. Transactional data from ERP to DW. Below is not applicable anymore Extract daily all incremental transactional data from ERP to CFO$OLVE for reporting. All transactions which have been posted, deleted and pending (suspense) in the ERL GL subledger. This is the incremental dump as per current functionality. This involves all crosswalk, transformation and lookup into the SOAR format which CFO$OLVE is expecting. Updated the process area column as per Scott's request. | Very High | Daily/Weekly | No | Existing | Batch | Send ERP Transactional Data | 41 | Global | Permanent | Phase1 | Sprint5 | P2P-222 B2R-152 | Updated as per new project direction to DW not CFO$OLVE. Preconstruction - Related to EDW dashboards for workstream 11 - Establish OCFO ER strategy. During implementation we will decide the number of extracts/details and if this is needed based on the ER strategy. This was updated during Preconstruction Interface validation. Based on the meeting with District on 1/12/21 as part of preconstruction these have been updated as optional | OCFO | ERP | OCFO | DW | Optional | Optional | ODI, DBCS & SFTP | Large volume of data with complex data mapping and COA translations. This is to Datawarehouse and ODI ETL tool is best suited for this. | FTP 10.16.12.78 | TBD
I082 | Budget To Report | Oracle Planning - DW Transactional & Master Data | Outbound | Automated | No | Updating this as per new direction for reporting. Master & Transactional data from Oracle Planning to DW. Below is not applicable anymore, Extract daily all incremental transactional and master data from ERP PPM to CFO$OLVE for reporting. All PPM transactions which have been posted, deleted and pending (suspense) in the ERP GL subledger and PPM master data. This is the incremental dump as per current functionality. This involves all crosswalk, transformation and lookup into the SOAR format which CFO$OLVE is expecting. SOAR was sending GRAMS data to CFO$OLVE for this. Updated the process area column as per Scott's request. | Very High | Daily/Weekly | No | Existing | Batch | Send Oracle Planning Transactional Data | 42 | Global | Permanent | Phase1 | Sprint5 | P2P-222 B2R-153 | Updated as per new project direction to DW not CFO$OLVE. Preconstruction - Related to EDW dashboards for workstream 11 - Establish OCFO ER strategy. During implementation we will decide the number of extracts/details and if this is needed based on the ER strategy. This was updated during Preconstruction Interface validation. Based on the meeting with District on 1/12/21 as part of preconstruction these have been updated as optional | OCFO | ERP | OCFO | DW | Optional | Optional | ODI, DBCS & SFTP | Large volume of data with complex data mapping and COA translations. This is to Datawarehouse and ODI ETL tool is best suited for this. | FTP 10.16.12.78 | TBD
I063 | Procure To Pay | ERP - Vendor Master | Outbound | Automated | No | Vendor Master Feed from DIFS to PeopleSof, ARIBA, PDMS and other interested agencies such as CFSA, OSSE to keep vendor data in-sync. These updates need to go to parties who send payment invoices. | High | Daily | No | New | Webservice | Sync Supplier Data | 35 | Global | Permanent | Phase1 | TBD | P2P-225 | Need to build a framework to send vendor updates to all agencies who send payment invoice requests. Such as MMIS, CFSA, OSSE, PeopleSoft etc. | OCFO | ERP | OCTO/DHCF | PSFT/ARIBA/PDMS | Yes | Yes - We need it | OIC | This will be implemented as near real time webservice. OIC REST, SOAP and Async services are best suited for this integration. | N/A | TBD
I084 | Budget To Report | DOES - Paid Family Leave (PFL) Benefit Program Accounting Entries | Inbound | Automated | No | Paid Family leave (PFL) benefit program for all small business. Beneficiaries are paid directly by DOES. It is only recording GL accounting entries in DIFS/SOAR. New interface being developed with SOAR. This is as per details from Ashis after his meeting with DOES on 12/17 | Medium | Daily | No | Existing | Batch | Create Journal Entries | 6 | Agency | Permanent | Phase1 | TBD | B2R-153 | New Interface being developed by SOAR with DOES. Not yet in production. The interface is in production now. | DOES | PFLBAS (PFL-Benefit) | OCFO | ERP | Yes | YES - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS DOESPFLTFTP.does.dcgov.priv Port: 990 | TBD
I085 | Procure To Pay | DOES - Paid Family Leave (PFL) Benefit Program Employer Tax Refunds | Inbound | Automated | No | Paid Family leave (PFL) benefit program for all small business. Refund payments to small businesses for any payments. New interface being developed with SOAR. More details from Ashis after his meeting with DOES on 12/17 | Medium | Daily | No | Existing | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-268 P2P-270 | New Interface being developed by SOAR with DOES. Not yet in production. The interface is in production now. | DOES | NEOSURANCE (PFL-TAX) | OCFO | ERP | Yes | YES - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS DOESPFLTFTP.does.dcgov.priv Port: 990 | TBD
I086 | Procure To Pay | PeopleSoft - Payroll Expenses | Inbound | Automated | No | Payroll expenses payment request data from PeopleSoft. These are payments for employee expenses (insurance and other expenses) to different providers. | High | By Payroll | Yes | Existing | Batch | Create Invoice | 5 | Global | Permanent | Phase1 | Sprint5 | P2P-226 | Making it high as building framework for payment requests for rest of payment interfaces except the unclaimed property and excluding Ariba. Keeping it separate as Expenses and Tax Deductions are being sent as separate files. This is after discussions with PeopleSoft team. | OCTO | PeopleSoft | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTP psoft-sftp.dc.gov 10.86.36.102 port: 21 | TBD
I087 | Procure To Pay | ARIBA OnPrem - ERP Create and Update PO Receipts | Inbound With ACK | Automated | No | Create and Update PO Receipts in ERP from Ariba OnPrem. On-Prem ARIBA to ERP will be only inbound as per current ARIBA-SOAR implementation. This will take care of PO timesheets as well. | Very High | On Demand | No | Existing | Webservice | Create and Update PO Receipts | 1 | Global | Temporary | Phase1 | Sprint3 | P2P-068 P2P-186 | This integration will take care of PO Timesheets as well. Increasing the complexity as very high as PO timesheets is merged into this one. | OCP | ARIBA-OnPrem | OCFO | ERP | Yes | Yes - We need it | OIC | All ARIBA-OnPrem integrations will be near real time webservices. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | Oracle SOA and CICS adapter | TBD
I088 | Procure To Pay | ARIBA Cloud - ERP Create and Update PO Receipts | Inbound With ACK | Automated | No | Create and Update PO Receipts in ERP from Ariba Cloud. | Medium | On Demand | No | Existing | Webservice | Create and Update PO Receipts | 1 | Global | Permanent | TBD | Sprint3 | P2P-278 |  | OCP | ARIBA-Cloud | OCFO | ERP | Yes | On hold for future implementation | TBD | Future implementation. Will be decided when ARIBA Cloud is being implemented. | N/A | TBD
I089 | Procure To Pay | ERP - ARIBA Cloud Update PO Receipts | Outbound | Automated | No | Update PO Receipts from ERP to Ariba Cloud. | Very High | On Demand | No | Existing | Webservice | Sync PO Receipts | 36 | Global | Permanent | TBD | Sprint3 | P2P-278 |  | OCFO | ERP | OCP | ARIBA-Cloud | Yes | On hold for future implementation | TBD | Future implementation. Will be decided when ARIBA Cloud is being implemented. | N/A | TBD
I090 | Procure To Pay | E-Invoice Portal - Create and Update Invoices | Inbound With ACK | Automated | No | Create and Update Invoices in ERP from E-Invoice Portal. This is needed in Phase2 as per new project direction and will not be needed in Phase3. During preconstruction validation it was decided it's not needed. | High | Daily | No | New | Webservice | Create and Update Invoice | #N/A | Global | Temporary | Phase1 | TBD | P2P-271 | InScope as per new project direction and is temporary as this will be not needed in Phase3. During preconstruction validation it was decided it's not needed. | OCP | E-Invoice-Portal | OCFO | ERP | No | We don't need it | OIC | All ARIBA-OnPrem integrations will be near real time webservices. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | N/A | TBD
I091 | Projects & Grants | DDOT - FMIS Budget Reallocation | Inbound | Automated | No | Moves budget from one project to another for grants from Federal Highway Trust Funds. DC pays 20% and Feds 80%. This is currently manual by entering data into SOAR. Excel and other documents are emailed to Alex. As per Dave the current manual interface from DDOT FMIS should be automated. Alex is the point of contact for this | Medium | Monthly | No | Existing | Batch | Budget Adjustment | 9 | Agency | Permanent | Phase1 | TBD | P&G-137 | As per District team request the current manual interface from FMIS should be automated. Currently it's manual-online. | DDOT | FMIS | OCFO | ERP | Yes | YES - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I092 | Budget | Oracle Planning - Approved Project Requests | Inbound | Automated | No | Approved project requests from Oracle Planning to Oracle ERP PPM. This is needed as part of the project creation process requirement. Depends on proms and grams replacement if phase1 or phase2. | High | Daily | No | New | Batch | Create Project Requests | 14 | Global | Permanent | Phase2 | Sprint6 | BUD-363 | More details from Sushant will be shared after the design is finalized | OCFO | Oracle Planning | OCFO | ERP | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I093 | Budget | Oracle Planning - New Capital Project Requests | Outbound | Automated | No | New Capital project requests from Oracle Planning to CARSS. This is needed as part of the project creation process requirement. This data currently goes from PROMS to CARSS. Depends on proms and grams replacement if phase1 or phase2 | Medium | Daily | No | New | Batch | Sync New Capital Project Requests | 30 | Global | Permanent | Phase2 | Sprint6 | BUD-364 | Needed for new draft project creation process. | OCFO | Oracle Planning | OCFO | CARSS | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I094 | Budget | CARSS - Approved Capital Project Requests | Inbound | Automated | No | Approved Capital project requests from CARSS to Oracle Planning. This is needed as part of the project creation process requirement. Depends on proms and grams replacement if phase1 or phase2. | Medium | Daily | No | New | Batch | Sync Approved Capital Project Requests | 16 | Global | Permanent | Phase2 | Sprint6 | BUD-365 | Needed for new draft project creation process. | OCFO | CARSS | OCFO | Oracle Planning | Yes | Yes - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I098 | Acquire To Retire | FASTER - Assets | Outbound | Automated | No | Faster system - Manages all fleet vehicles. Financial transactions need to be entered and managed in DIFS. Need to be confirmed If they need this during implementation phase. Jake is still confirming if we need this or not. | Medium | Monthly | No | New |  | Send Asset Data | 27 | Agency | Permanent | Phase1 | TBD | A2R-113 | This is optional. During implementation need to find out if this is really needed. This is optional as per Preconstruction validation. During implementation team will decide if this will be automated or manual. | OCFO | ERP | DDOT/DPW | FASTER | Optional | Optional. | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I099 | Procure To Pay | BOE - Poll Workers Payment | Inbound | Semi-Automated | No | Poll Workers Payment Request. Currently it’s a manual/semi-automated process | Medium | As Needed | Yes | Existing |  | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | P2P-216 | Manual process today, could be automated | Board of Elections | NA | OCFO | ERP | Optional | Optional. Need to check with OFOS | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | Manual upload Process | TBD
I106 | Budget To Report | ICS - Lottery Gaming | Inbound | Automated | No | Taking summed up transaction data and inputting into ERP GL. The transactions are people buying lotteries, sports betting etc. | Medium | Monthly | No | New | Batch | Create Journal Entries | 6 | Agency | Permanent | Phase1 | NA | NA | Office of lottery and gaming. Current manual process; automated process is not live. This feeds a separate legal entity | DC0 | ICS | OCFO | ERP | Optional | YES - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | N/A | TBD
I107 | Budget To Report | DOES - Payroll Data | Inbound | Automated | No | DOES Payroll data. This will be recorded as journal entries in DIFS. This is a new SOAR interface currently in production | Medium | Daily | No | Existing | Batch | Create Journal Entries | 6 | Agency | Permanent | Phase1 | TBD | TBD | New Interface being developed by SOAR with DOES. | DOES | PeopleFirst Payroll System | OCFO | ERP | Yes | YES - We need it | OIC & SFTP | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | FTPS doesintf.does.dcgov.priv Port:21 | TBD
I108 | Procure To Pay | DIFS - PASS Create and Update Invoices | Outbound | Automated | No | Create and Update Invoices from ERP to ARIBA. This was during Preconstruction validaiton. Invoices will be created and updated in ERP which will sent to ARIBA. The interface from E-Invoice Portal to ERP is not needed as invoices will be created/updated in DIFS | Very High | Near Real-time | No | New | Webservice | Send Invoice | 43 | Global | Permanent | Phase1 | TBD | P2P-271 | InScope as per new project direction. This was added during Preconstruction validation after consulting functional and tech teams | OCFO | ERP | OCP | ARIBA-OnPrem | Yes | Yes - We need it | OIC | All ARIBA-OnPrem integrations will be near real time webservices. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | N/A | TBD
I109 | Procure To Pay | ARIBA OnPrem - ERP Create and Update PO Receipts (Timesheets) | Inbound With ACK | Automated | No | Create and Update PO timesheet Receipts in ERP from Ariba OnPrem. This was added as part of preconstructiob validation. During the design phase need to look into if this can be merged with the PO receipts interface | High | Near Real-time | No | New | Webservice | Create and Update PO Receipts | 1 | Global | Temporary | Phase1 | Sprint3 | P2P-068 P2P-186 | Added as part of PreConstruction validation. This will taken care by ARIBA PO Receipts interface. Not needed as a separate integration. | OCP | ARIBA-OnPrem | OCFO | ERP | No | Yes - We need it | OIC | All ARIBA-OnPrem integrations will be near real time webservices. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | N/A | TBD
I110 | Procure To Pay | OFT - Unclaimed Property Response | Outbound | Automated | No | Unclaimed Property data response to OFT's Third party vendor system by Kelmar. Response to payment requests to issue checks. This is an existing interface and added during preconstruction validation | Medium | Monthly | Yes | Exisiting | Batch | Send Payment Status | 37 | Global | Permanent | Phase1 | TBD | TBD | Added as part of PreConstruction validation. | OCFO | ERP | OCFO/OFT | Kelmar | Yes | Yes - We need it | OIC | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | TBD | TBD
I111 | Procure To Pay | MMIS PDMS - Create and Update Vendors | Inbound With ACK | Automated | No | New Interface, In the future interface medicaid provider information along with banking information directly from DHCF PDMS to DIFS. Medicaid providers (vendors) currently use DHCF PDMS system to create and update their info along with banking information.This is currently sent to PASS manually and then is interfaced to SOAR. In the future it needs to go directly from PDMS to DIFS. | High | Daily | No | New | Webservice | Create and Update Suppliers | 4 | Agency | Permanent | Phase1 | TBD | P2P-146 P2P-201 P2P-203 | Added as during pre-construction | DHCF | PDMS | OCFO | DIFS | Yes | Yes - We need it | OIC | This will be near real-time webservice. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | NA | TBD
I112 | Procure To Pay | DIFS - PDMS Supplier Sync | Outbound | Automated | No | New interface, vendor updates from DIFS to DHCF PDMS. Keeping most of the P2P as bi-directional. During implementation need to figure out if outbound is needed or just inbound if enough. PDMS is the source system where medicaid providers are created/updated along with their banking information. | Medium | Daily | No | New | Webservice | Sync Supplier Data | 35 | Agency | Permanent | Phase1 | TBD | P2P-146 P2P-201 P2P-203 | Added during pre-construction | OCFO | ERP | DHCF | PDMS | No | Yes - We need it | OIC | This will be near real-time webservice. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | NA | TBD
I114 | B2R | Department Of Corrections (DOC) - DIFS Journal Entries | Inbound | Automated | No | Potential new interface with Department of Corrections (DOC). DOC has shown interest in integrating with DIFS. They currently manual enter their journal transactions. The approxinate load is 6-10 records. Making it this optional after discussing with the team. | Medium | Daily | No | New | Batch | Create Journal Entries | 6 | Agency | Permanent | Phase1 | TBD | TBD | Added during pre-construction and made it optional after discussing with District team. During implementation need to revisit to see if this needs to be implemented or not. | DOC | TBD | OCFO | ERP | Optional | Optional | OIC | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | NA | TBD
I115 | B2R | HSEMA - DIFS Journal Entries | Inbound | Automated | No | Potential new interface with Homeland Security Emergency Agency (HSEMA). DIFS may potentially have to manage with HSEMA. HSEMA's central tracking system is currently siloed and is going to be integrated to DIFS per Mayor's recommendation. Making it optional after discussing it with the District team | High | Daily | No | New | Batch | Create Journal Entries | 6 | Agency | Permanent | Phase1 | TBD | TBD | Added during pre-construction and made it optional after discussing with District team. During implementation need to revisit to see if this needs to be implemented or not. | HSEMA | TBD | OCFO | ERP | Optional | Optional | OIC | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | NA | TBD
I116 | Procure To Pay | TOPS Metering System - DIFS Refunds | Inbound | Automated | No | Potential new interface with TOPS and the Parking Meter System. Both are revenue tracking systems currently being used by the District (a central tool for tracking the status of re-programmings). This integration is for refunds. Making it optional after discussing it with the District team | High | Daily | No | New | Batch | Create Invoice | 5 | Agency | Permanent | Phase1 | TBD | TBD | Added during pre-construction and made it optional after discussing with District team. During implementation need to revisit to see if this needs to be implemented or not. | DCMayor | TOPS | OCFO | ERP | Optional | Optional | OIC | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | NA | TBD
I117 | Procure To Pay | DIFS - PASS OnPrem Sync Suppliers | Outbound | Automated | No | Any changes to suppliers in DIFS need to be updated back PASS. | Medium | Daily | No | New | Webservice | Sync Supplier Data | 35 | Global | Permanent | Phase1 | Sprint4 Sprint2 | P2P-146 P2P-201 P2P-203 | Added during pre-construction (2/11/21) | OCFO | ERP | OCFP | ARIBA-OnPrem | No | Yes - We need it | OIC | All ARIBA-OnPrem integrations will be near real time webservices. OIC is best suited as it has REST and SOAP adapters to implement near real time webservices. | NA | TBD
I118 | Budget | EPM - BFA Project Structure | Outbound | Automated | No | Project structure along with implementing Agency, phases with Programs and Cost Centers, real project number and associated Awards with owning Agency and Fund information. Project Profile information for budget book reporting. Approved project information will be sent to BFA since BFA will be used for budgeting for FY23 and FY24 | High | Daily | No | New | Batch | Sync Project Structure | 14 | Global | Temporary | Phase1 |  | TBD | Added as PROMS/GRAMS is being replaced | OCFO | EPM | OCFO | BFA | Yes | Yes - We need it | OIC | OIC is best suited with it's file and ftp adapters. The data volume is manageable within OIC | NA | TBD

## Interface Tracker
Object Type | Interface
Years | Quarters | Planned Functional Specification Start Date | Process Area | Rice ID | DIFS Object Name | Functional Specification Status | Years2 | Quarters2 | Planned Technical Specification Start Date | Technical Specification Status
2021 | Qtr1 | Mar | Technical | I095 | Common Error Handling & Setup | 100% - Complete | 2021 | Qtr1 | Mar | 100% - Complete
|  |  |  | I096 | DIFS Transformation Hub and Crosswalk | 100% - Complete | 2021 | Qtr1 | Mar | 100% - Complete
| Qtr2 | Apr | Budget to Report | I001 | PeopleSoft - Payroll Costs | 100% - Complete | 2021 | Qtr2 | May | 100% - Complete
|  |  |  | I004 | Peoplesoft - COA Data | 100% - Complete | 2021 | Qtr2 | Apr | 100% - Complete
|  |  |  | I084 | DOES - Paid Family Leave (PFL) Benefit Program Accounting Entries | 100% - Complete | 2021 | Qtr2 | May | 100% - Complete
|  |  |  | I107 | DOES - Payroll Data | 100% - Complete | 2021 | Qtr2 | Apr | 100% - Complete
|  |  | Procure to Pay | I048 | DOES - Employers Unemployment Contribution Refunds | 100% - Complete | 2021 | Qtr2 | Apr | 100% - Complete
|  |  |  | I049 | OSSE BITSEE- Special Education Not Encumbered Payment Requests | 100% - Complete | 2021 | Qtr2 | May | 100% - Complete
|  |  |  | I050 | OSSE BITSEE- General and Special Education Payment Response | 100% - Complete | 2021 | Qtr2 | May | 100% - Complete
|  |  |  | I063 | ERP - Vendor Master | 100% - Complete | 2021 | Qtr2 | May | 0% - Not Started
|  |  |  | I066 | ARIBA OnPrem - ERP Create and Update (chg/cancel) Requisitions On Prem | 100% - Complete | 2021 | Qtr2 | Jun | 75% - In Review
|  |  |  | I070 | ARIBA OnPrem - ERP Create and Update Suppliers | 100% - Complete | 2021 | Qtr2 | Apr | 100% - Complete
|  |  |  | I085 | DOES - Paid Family Leave (PFL) Benefit Program Employer Tax Refunds | 100% - Complete | 2021 | Qtr2 | Apr | 100% - Complete
|  |  | Projects & Grants | I031 | PeopleSoft - Employee Data | 100% - Complete | 2021 | Qtr2 | Apr | 100% - Complete
|  | May | Procure to Pay | I046 | OSSE NSCAPS - Nutrition Services Payment Request | 100% - Complete | 2021 | Qtr2 | Jun | 75% - In Review
|  |  |  | I047 | OSSE NSCAPS - Nutrition Services Payment Response | 100% - Complete | 2021 | Qtr2 | Jun | 100% - Complete
|  |  |  | I052 | MITS - State Income Liability Offset (SITLP) | 100% - Complete | 2021 | Qtr2 | May | 75% - In Review
|  |  |  | I053 | MITS - DC Vendor Offset | 25% - In Progress | 2021 | Qtr2 | Jun | 0% - Not Started
|  |  |  | I055 | TOP - State Federal Liability Offset | 25% - In Progress | 2021 | Qtr3 | Jul | 0
|  |  |  | I062 | PeopleSoft - Payroll Tax Deductions | 100% - Complete | 2021 | Qtr2 | Jun | 25% - In Progress
|  |  |  | I068 | ARIBA OnPrem - ERP Create and Update Purchase Orders | 75% - In Review | 2021 | Qtr2 | Jun | 0
|  |  |  | I086 | PeopleSoft - Payroll Expenses | 100% - Complete | 2021 | Qtr2 | Jun | 75% - In Review
|  |  | Projects & Grants | I030 | PeopleSoft - Payroll Costs | 100% - Complete | 2021 | Qtr2 | Jun | 100% - Complete
|  | Jun | Budget | I022 | ERP - P&G Master & Award Data | 0% - Not Started | 2021 | Qtr2 | Jun | 0% - Not Started
|  |  |  | I092 | Oracle Planning - Approved Project Requests | 0% - Not Started | 2021 | Qtr2 | Jun | 0
|  |  |  | I118 | EPM - BFA Project Structure | 0 | 2021 | Qtr2 | Jun | 0
|  |  | Procure to Pay | I044 | OSSE ONEAPP - University Payments | 100% - Complete | 2021 | Qtr3 | Jul | 0
|  |  |  | I045 | OSSE ONEAPP - University Payments Response | 75% - In Review | 2021 | Qtr3 | Jul | 0
|  |  |  | I054 | MITS - DC Vendor Offset Response | 25% - In Progress | 2021 | Qtr3 | Jul | 0
|  |  |  | I056 | TOP - State Federal Liability Offset Response | 25% - In Progress | 2021 | Qtr3 | Sep | 0
|  |  |  | I087 | ARIBA OnPrem - ERP Create and Update PO Receipts | 0 | 2021 | Qtr3 | Aug | 0
| Qtr3 | Jul | Budget | I023 | ERP - Projects Actuals | 0 | 2021 | Qtr3 | Jul | 0
|  |  |  | I026 | Oracle Planning - Project Budget | 0 | 2021 | Qtr3 | Sep | 0
|  |  | Order to Cash | I013 | MITS - Tax Revenue Collection | 0 | 2021 | Qtr3 | Aug | 0
|  |  | Procure to Pay | I057 | Banks - ACH Payments | 0 | 2021 | Qtr3 | Jul | 0
|  |  |  | I108 | DIFS - Create and Update Invoices | 0 | 2021 | Qtr3 | Sep | 0
|  | Aug | Budget | I028 | CARSS - Requested Budget | 0 | 2021 | Qtr3 | Aug | 0
|  |  |  | I093 | Oracle Planning - New Capital Project Requests | 0 | 2021 | Qtr3 | Sep | 0
|  |  | Order to Cash | I016 | MITS - Real Property Tax Revenue & Lockbox Payments | 0 | 2021 | Qtr3 | Sep | 0
|  |  | Procure to Pay | I034 | OSSE OECD - Day Care Grant Vendor Payment | 0 | 2021 | Qtr3 | Sep | 0
|  |  |  | I035 | MMIS - Medicaid Vendor Payment | 0 | 2021 | Qtr3 | Sep | 0
|  |  |  | I036 | MMIS - Medicaid Vendor Payment Response | 0 | 2021 | Qtr4 | Oct | 0
|  |  |  | I051 | OSSE EGMS - Intra District Funds Transfer | 0 | 2021 | Qtr3 | Aug | 0
|  |  |  | I058 | Checkwrite - Warrant and Invoice file | 0 | 2021 | Qtr3 | Aug | 0
|  | Sep | Acquire to Retire | I033 | CARSS - Assets Extract | 0 | 2021 | Qtr4 | Oct | 0
|  |  | Budget | I027 | Oracle Planning - Approved GL Budget | 0 | 2021 | Qtr4 | Oct | 0
|  |  |  | I094 | CARSS - Approved Capital Project Requests | 0 | 2021 | Qtr3 | Sep | 0
|  |  | Budget to Report | I080 | ERP - CFO$OLVE/DW Master Data | 0 | 2022 | Qtr1 | Jan | 0
|  |  |  | I081 | ERP - CFO$OLVE/DW Transactional Data | 0 | 2021 | Qtr4 | Nov | 0
|  |  | Order to Cash | I012 | Kyriba - GL Posting Entries | 0 | 2021 | Qtr4 | Oct | 0
|  |  |  | I014 | Wells Fargo - Remote Deposit and Lockbox | 0 | 2021 | Qtr4 | Oct | 0
|  |  |  | I083 | Kyriba - Transactions Cash Forecasting | 0 | 2021 | Qtr3 | Sep | 0
|  |  | Procure to Pay | I037 | CFSA Faces - Child Care Provider Payment | 0 | 2021 | Qtr4 | Dec | 0
|  |  |  | I038 | CFSA Faces - Child Care Provider Payment Response | 0 | 2022 | Qtr1 | Jan | 0
|  |  |  | I039 | DDS RSA - Grant Vendor Payment | 0 | 2021 | Qtr4 | Oct | 0
|  |  |  | I040 | DDS RSA - Grant Vendor Payment Response | 0 | 2021 | Qtr4 | Nov | 0
|  |  |  | I060 | E-Risk - PSWCP Vendor Payments | 0 | 2021 | Qtr4 | Nov | 0
| Qtr4 | Oct | Budget to Report | I082 | EPM - CFO$OLVE/DW Transactional & Master Data | 0 | 2021 | Qtr4 | Nov | 0
|  |  | Order to Cash | I015 | Well Fargo - Record Interest Income | 0 | 2021 | Qtr4 | Nov | 0
|  |  | Procure to Pay | I043 | OFT - Unclaimed Property | 0 | 2021 | Qtr4 | Nov | 0
|  |  |  | I061 | E-Risk - PSWCP Vendor Payment Response | 0 | 2021 | Qtr4 | Nov | 0
|  |  |  | I073 | ERP - ARIBA OnPrem Procurement Payment Status | 0 | 2021 | Qtr4 | Oct | 0
|  |  |  | I110 | OFT - Unclaimed Property Response | 0 | 2021 | Qtr4 | Dec | 0
|  |  |  | I111 | MMIS PDMS - Create and Update Vendors | 0 | 2021 | Qtr4 | Nov | 0
|  |  | Projects & Grants | I032 | EGMS - Events Revenue & Billing | 0 | 2021 | Qtr4 | Nov | 0
|  |  |  | I091 | DDOT - FMIS Budget Reallocation | 0 | 2021 | Qtr4 | Nov | 0
|  | Nov | Order to Cash | I010 | OFT DMS/DBC - Debt Service Payment Postings | 0 | 2021 | Qtr4 | Dec | 0
|  |  | Procure to Pay | I041 | DMV Destiny- Refund of Traffic Fines | 0 | 2022 | Qtr1 | Feb | 0
|  |  |  | I064 | PeopleSoft - Union Dues Refund | 0 | 2021 | Qtr4 | Dec | 0
|  |  |  | I065 | Banks - PCard Allocation | 0 | 2021 | Qtr4 | Dec | 0
|  |  |  | I075 | ERP- Ariba OnPrem Sync COA Master Data | 0 | 2021 | Qtr4 | Dec | 0% - Not Started
|  |  |  | I077 | ERP - ARIBA OnPrem Sync Projects & Grants Master Data | 0 | 2021 | Qtr4 | Dec | 0
|  |  |  | I112 | DIFS - PDMS Supplier Sync | 0 | 2021 | Qtr4 | Dec | 0
|  | Dec | Order to Cash | I009 | iNOVAH - Cash Collection | 0 | 2021 | Qtr4 | Dec | 0
|  |  |  | I011 | Banks - Bank Statements Reconciliation | 0 | 2022 | Qtr1 | Jan | 0
|  |  | Procure to Pay | I042 | DMV Destiny- Refund of Traffic Fines Response | 0 | 2021 | Qtr4 | Dec | 0
|  |  |  | I059 | IRS - 1099M Processing | 0 | 2022 | Qtr1 | Jan | 0
Grand Total

## Values (hidden)
[11 empty] | Release | Sprint
Tech Resource Name | Vendor | Test Status | Status |  | Object Type |  | Complexity | Type | 0 | 0- None | TBD | 1
Rajbir Virk | Sub | N/A | N/A |  | Extension |  | Low | FRS | 1 | 1-Low | Phase 2 | 2
Pavan Pemavath | Sub | Not Started | 0% - Not Started |  | Workflow |  | Medium | Smartview | 2 | 2-Medium | Phase 3 | 3
ShashiKumar Govindaiah | Sub | Ready For Test | 25% - In Progress |  | Interface |  | High | OTBI | 3 | 3-High | Pre-Construction | 4
Developer 4 | Deloitte | Bug Fixing | 50% - In Progress |  | Report |  | Very High | BI Publisher | 4 | 4-Severe | Phase 1 | 5
Developer 5 | Deloitte | Complete | 75% - In Review |  | Conversion |  |  | Batch |  |  |  | 6
Developer 6 | Deloitte | Signed-off | 100% - Complete |  | Infrastructure |  |  | Online |  |  |  | 7
Developer 7 | Deloitte | [10 empty] | 8
Developer 8 | Deloitte
Developer 9 | Deloitte
Developer 10 | Deloitte
Developer 11 | Deloitte
Developer 12 | Deloitte
|  | Reg. Test Status |  | Defect Status |  | Process Area |  | MoSCoW |  | Owner | Entry Type
|  | Not Started |  | Not Started |  | A2R | Acquire to Retire | Must Have |  | District Owned | Manual
Func Resource Name | Vendor | In Progress |  | In Progress |  | B2R | Budget to Report | Should Have |  | Deloitte Owned | Drop-Down
Jagannathan Viswanathan | Sub | Failed |  | Fixed |  | Budget | EPM Cloud | Could Have |  |  | Auto-Generated
Andrew Fedoris | Deloitte | Bug Fixing In Progress |  | Ready For Test |  | P2P | Procure to Pay | Won't Have
Prasad Potturi | Deloitte | Out Of Scope |  |  |  | P&G | Projects and Grants
Jake Loughridge | Deloitte | On Hold |  |  |  | O2C | Order to Cash
Anil Yemmanuru | Sub | Complete |  |  |  | Intra-District | Intra-District
Trinh Trinh | Sub | [5 empty] | Budget
Functional 7 | Deloitte | [5 empty] | Budget Formulation
Functional 8 | Deloitte | [5 empty] | Budget Execution
Functional 9 | Deloitte | [5 empty] | Technical
Functional 10 | Deloitte | [5 empty] | Conversion
Functional 11 | Deloitte | Systems |  | Overall Status |  |  | Core HR
|  | ERP Cloud |  | Sprinted
|  | EPM Cloud |  | Tested
|  | Narrative Reporting |  | Deployed
EDW
Direction
|  | Pillar |  | Inbound
|  | CCG |  | Outbound
|  | ESM |  | Bidirectional
FP&A